## Grid-Guard Dataset
⚡ GRID-GUARD AI — Transmission Project Delay Prediction Dataset
Ministry of Power, GoI ¦ CEA Grid-Guard System ¦ Records: 2000 ¦ Causal Logic: Rules-Based ¦ AI/ML Delay Prediction Training Dataset
Project_ID | Project_Type | Region | Budget_Cr | Line_Length_CKM | Planned_Duration_Months | Physical_Progress_Pct | Land_RoW_Status | Forest_Clearance_Status | Vendor_Status | Site_Engineer_Remark | Actual_Delay_Months | Risk_Level
GRID-0001 | 220kV D/C Line | Northern | 117.51 | 105 | 19 | 63.6 | Clear | Stage-II Awaited | On Track | Physical progress is at 63.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0002 | 765kV Transmission Line | Northern | 2265.23 | 351.6 | 36 | 21.2 | Disputed | Approved | Insolvent | Physical progress is at 21.2%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0003 | 765kV Transmission Line | Eastern | 2690.88 | 246.6 | 60 | 43.9 | Pending Local | Approved | On Track | Physical progress is at 43.9%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0004 | 220kV D/C Line | Southern | 664.99 | 195.9 | 29 | 17.3 | Clear | Stage-I Awaited | On Track | Physical progress is at 17.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0005 | 220kV D/C Line | Western | 593.2 | 59.2 | 19 | 55.2 | Pending Local | Approved | On Track | Physical progress is at 55.2%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-0006 | 220kV D/C Line | Southern | 213.86 | 121.1 | 33 | 14.3 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 14.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0007 | 400kV Substation | Eastern | 623.94 | 93.3 | 46 | 29.2 | Disputed | Approved | Insolvent | Physical progress is at 29.2%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0008 | 765kV Transmission Line | Southern | 2904.08 | 219.9 | 54 | 32.1 | Disputed | Stage-I Awaited | On Track | Physical progress is at 32.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0009 | 400kV Substation | Western | 595.95 | 60.5 | 32 | 34.9 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 34.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0010 | 765kV Transmission Line | Northern | 2034.94 | 248 | 57 | 43.8 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 43.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0011 | 400kV Substation | North-Eastern | 1332.94 | 11 | 47 | 26 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 26.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0012 | 400kV Substation | Western | 844.47 | 95.8 | 47 | 31.9 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 31.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0013 | 220kV D/C Line | Western | 206.99 | 202.5 | 29 | 10.5 | Disputed | Approved | Insolvent | Physical progress is at 10.5%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0014 | 765kV Transmission Line | Northern | 2343.05 | 370.2 | 38 | 25.1 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 25.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0015 | 400kV Substation | North-Eastern | 1346.92 | 48.1 | 30 | 34.9 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 34.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0016 | 220kV D/C Line | Eastern | 184.7 | 94.9 | 22 | 15.5 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 15.5%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0017 | 765kV Transmission Line | Northern | 4668.97 | 457.9 | 38 | 41.6 | Disputed | Approved | Equipment Delayed | Physical progress is at 41.6%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0018 | 400kV Substation | Eastern | 528.49 | 18.7 | 37 | 26.8 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 26.8%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0019 | 220kV D/C Line | Southern | 660.41 | 71.9 | 18 | 27.3 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 27.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0020 | 765kV Transmission Line | Eastern | 4328.08 | 456.8 | 39 | 33.2 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 33.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0021 | 400kV Substation | Eastern | 877.63 | 87.8 | 25 | 16.6 | Clear | Stage-I Awaited | On Track | Physical progress is at 16.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0022 | 400kV Substation | Eastern | 1135.91 | 75.7 | 41 | 15.4 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 15.4%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0023 | 765kV Transmission Line | Northern | 3544.62 | 350.9 | 52 | 54.1 | Clear | Approved | Insolvent | Physical progress is at 54.1%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0024 | 220kV D/C Line | Northern | 572.65 | 97 | 15 | 12 | Disputed | Approved | Insolvent | Physical progress is at 12.0%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0025 | 765kV Transmission Line | Southern | 2335.4 | 318.7 | 57 | 21.5 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 21.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0026 | 220kV D/C Line | Southern | 192.72 | 119.8 | 14 | 30.8 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 30.8%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0027 | 220kV D/C Line | North-Eastern | 309.57 | 182.7 | 16 | 62.1 | Pending Local | Approved | On Track | Physical progress is at 62.1%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0028 | 400kV Substation | North-Eastern | 552.76 | 40.9 | 45 | 11.3 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 11.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 33 | High
GRID-0029 | 765kV Transmission Line | Southern | 4198.92 | 391.1 | 44 | 24.5 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 24.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0030 | 220kV D/C Line | Northern | 684.22 | 166.5 | 16 | 54.6 | Pending Local | Approved | On Track | Physical progress is at 54.6%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0031 | 400kV Substation | Western | 1118.48 | 70 | 35 | 14.1 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 14.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 30 | High
GRID-0032 | 765kV Transmission Line | Southern | 4238.35 | 323.5 | 57 | 35.3 | Disputed | Approved | Equipment Delayed | Physical progress is at 35.3%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0033 | 765kV Transmission Line | Western | 4358.05 | 338.1 | 45 | 73.9 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 73.9% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 0 | Low
GRID-0034 | 220kV D/C Line | North-Eastern | 379.77 | 246.2 | 29 | 47.1 | Pending Local | Approved | On Track | Physical progress is at 47.1%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0035 | 765kV Transmission Line | Northern | 3588 | 303.7 | 46 | 14.8 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 14.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0036 | 765kV Transmission Line | North-Eastern | 4739.51 | 361.5 | 59 | 11.7 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 11.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0037 | 220kV D/C Line | Northern | 603.83 | 110.1 | 21 | 14.8 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 14.8%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0038 | 400kV Substation | North-Eastern | 1300.47 | 37.3 | 30 | 21.1 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 21.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0039 | 220kV D/C Line | Western | 561.2 | 106.8 | 33 | 15.6 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 15.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0040 | 765kV Transmission Line | Western | 4943.78 | 383.4 | 60 | 28 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 28.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0041 | 400kV Substation | Western | 477.09 | 71.9 | 48 | 52.2 | Clear | Stage-I Awaited | On Track | Physical progress is at 52.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0042 | 765kV Transmission Line | North-Eastern | 2372.19 | 454.5 | 50 | 24.9 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 24.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0043 | 220kV D/C Line | Eastern | 728.05 | 198.7 | 27 | 22.1 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 22.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0044 | 400kV Substation | Northern | 1156.25 | 31.1 | 34 | 49.3 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 49.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0045 | 220kV D/C Line | Western | 144.96 | 131.5 | 29 | 19.7 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 19.7%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0046 | 400kV Substation | Eastern | 307.08 | 41.7 | 48 | 22.2 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 22.2%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0047 | 765kV Transmission Line | Eastern | 2676.45 | 403.7 | 48 | 56.3 | Disputed | Approved | Equipment Delayed | Physical progress is at 56.3%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0048 | 220kV D/C Line | Eastern | 194.99 | 142.3 | 13 | 18.4 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 18.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0049 | 400kV Substation | Northern | 864.37 | 77.4 | 25 | 33.9 | Pending Local | Approved | Insolvent | Physical progress is at 33.9%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0050 | 765kV Transmission Line | Western | 4437.3 | 386.4 | 43 | 33.7 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 33.7%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0051 | 400kV Substation | Western | 1027.07 | 96.7 | 46 | 63.1 | Clear | Approved | Equipment Delayed | Physical progress is at 63.1%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0052 | 220kV D/C Line | Eastern | 377.66 | 193 | 14 | 29.3 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 29.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0053 | 400kV Substation | North-Eastern | 814.05 | 43.4 | 40 | 12.6 | Disputed | Stage-I Awaited | On Track | Physical progress is at 12.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0054 | 220kV D/C Line | Western | 404.84 | 196.8 | 32 | 30.6 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 30.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0055 | 765kV Transmission Line | Northern | 2476.25 | 335.2 | 60 | 22.4 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 22.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0056 | 765kV Transmission Line | Southern | 4292.41 | 302.1 | 55 | 16 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 16.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0057 | 220kV D/C Line | Eastern | 552.13 | 148.2 | 12 | 27.3 | Clear | Stage-I Awaited | On Track | Physical progress is at 27.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0058 | 220kV D/C Line | North-Eastern | 358.31 | 160.7 | 23 | 21.3 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 21.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0059 | 765kV Transmission Line | Western | 2604.42 | 422.9 | 60 | 69.5 | Disputed | Approved | On Track | Physical progress is at 69.5%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0060 | 220kV D/C Line | North-Eastern | 783.62 | 154.9 | 21 | 54.4 | Clear | Approved | Equipment Delayed | Physical progress is at 54.4%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0061 | 765kV Transmission Line | North-Eastern | 1943.04 | 213.7 | 37 | 31.8 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 31.8%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0062 | 400kV Substation | Southern | 521.24 | 14.6 | 39 | 43 | Clear | Approved | Equipment Delayed | Physical progress is at 43.0%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0063 | 765kV Transmission Line | Western | 4339 | 484.7 | 38 | 20.4 | Clear | Approved | Insolvent | Physical progress is at 20.4%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0064 | 220kV D/C Line | Eastern | 415.36 | 138.5 | 30 | 34 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 34.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0065 | 400kV Substation | Northern | 488.47 | 25.6 | 26 | 67.6 | Clear | Approved | Equipment Delayed | Physical progress is at 67.6%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0066 | 400kV Substation | Northern | 577.77 | 73.6 | 46 | 29.7 | Pending Local | Approved | Insolvent | Physical progress is at 29.7%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0067 | 400kV Substation | Northern | 953.47 | 68.3 | 32 | 87.7 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 87.7% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 0 | Low
GRID-0068 | 220kV D/C Line | Southern | 589.81 | 238.5 | 28 | 28.4 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 28.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0069 | 765kV Transmission Line | North-Eastern | 3554.93 | 206.2 | 60 | 23 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 23.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0070 | 220kV D/C Line | Eastern | 544.35 | 148.3 | 14 | 31.4 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 31.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0071 | 400kV Substation | Eastern | 1276.28 | 59.5 | 38 | 34.3 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 34.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0072 | 220kV D/C Line | North-Eastern | 423.38 | 60.8 | 28 | 30.7 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 30.7%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0073 | 220kV D/C Line | Eastern | 185 | 244.6 | 31 | 62 | Clear | Stage-II Awaited | On Track | Physical progress is at 62.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0074 | 400kV Substation | Northern | 569.64 | 85.7 | 27 | 33.3 | Pending Local | Approved | Insolvent | Physical progress is at 33.3%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0075 | 400kV Substation | Eastern | 1476.29 | 31.9 | 41 | 22.7 | Clear | Stage-I Awaited | On Track | Physical progress is at 22.7%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0076 | 765kV Transmission Line | Southern | 4204.36 | 456.3 | 46 | 30.9 | Disputed | Stage-I Awaited | On Track | Physical progress is at 30.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0077 | 400kV Substation | North-Eastern | 881.21 | 39.9 | 48 | 24.3 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 24.3%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0078 | 400kV Substation | Eastern | 1146.27 | 83 | 36 | 25 | Disputed | Stage-II Awaited | On Track | Physical progress is at 25.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0079 | 765kV Transmission Line | Eastern | 1848.99 | 473.1 | 36 | 38.8 | Disputed | Approved | Equipment Delayed | Physical progress is at 38.8%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0080 | 220kV D/C Line | Eastern | 554.89 | 220.4 | 33 | 15.9 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 15.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0081 | 400kV Substation | Northern | 1212.44 | 73.4 | 27 | 11.1 | Pending Local | Approved | Insolvent | Physical progress is at 11.1%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0082 | 400kV Substation | Southern | 816.82 | 32 | 37 | 23.2 | Disputed | Stage-II Awaited | On Track | Physical progress is at 23.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0083 | 400kV Substation | North-Eastern | 471.74 | 51.5 | 32 | 26.9 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 26.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0084 | 400kV Substation | North-Eastern | 658.99 | 96.6 | 46 | 12.7 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 12.7%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0085 | 220kV D/C Line | Southern | 794.88 | 109 | 33 | 29.5 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 29.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0086 | 220kV D/C Line | Eastern | 682.99 | 230.6 | 36 | 44.8 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 44.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0087 | 220kV D/C Line | Northern | 732.38 | 179.3 | 21 | 13.3 | Pending Local | Approved | Insolvent | Physical progress is at 13.3%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0088 | 220kV D/C Line | Eastern | 222.95 | 76.4 | 29 | 32.9 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 32.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0089 | 765kV Transmission Line | Eastern | 4870.13 | 242.2 | 43 | 29.8 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 29.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0090 | 400kV Substation | Southern | 1107.39 | 70.5 | 42 | 38.9 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 38.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0091 | 220kV D/C Line | Western | 553.36 | 177.1 | 26 | 11.1 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 11.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0092 | 765kV Transmission Line | Northern | 2321.8 | 361.3 | 48 | 28.6 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 28.6%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0093 | 400kV Substation | North-Eastern | 789.74 | 95.6 | 25 | 33.8 | Disputed | Stage-I Awaited | On Track | Physical progress is at 33.8%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0094 | 220kV D/C Line | Southern | 481.13 | 245.6 | 23 | 33.7 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.7%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0095 | 220kV D/C Line | Western | 549.19 | 169.4 | 12 | 51.5 | Clear | Stage-I Awaited | On Track | Physical progress is at 51.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0096 | 765kV Transmission Line | North-Eastern | 2225.05 | 264.8 | 43 | 31.5 | Pending Local | Approved | Insolvent | Physical progress is at 31.5%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0097 | 220kV D/C Line | Southern | 658.96 | 72 | 12 | 63.6 | Clear | Approved | Equipment Delayed | Physical progress is at 63.6%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0098 | 765kV Transmission Line | Southern | 1683.4 | 422.5 | 52 | 37.9 | Clear | Stage-II Awaited | On Track | Physical progress is at 37.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0099 | 220kV D/C Line | North-Eastern | 176.34 | 150.8 | 31 | 26.1 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 26.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0100 | 400kV Substation | Eastern | 811.53 | 19.7 | 46 | 64.3 | Pending Local | Approved | On Track | Physical progress is at 64.3%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0101 | 765kV Transmission Line | Southern | 3685.11 | 375.6 | 58 | 22.6 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 22.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0102 | 220kV D/C Line | North-Eastern | 604.59 | 93 | 26 | 20.4 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 20.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0103 | 400kV Substation | Southern | 1098.13 | 43.7 | 28 | 12.3 | Disputed | Stage-I Awaited | On Track | Physical progress is at 12.3%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0104 | 765kV Transmission Line | North-Eastern | 1709.93 | 487 | 53 | 54.9 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 54.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0105 | 765kV Transmission Line | Southern | 3601.44 | 305.5 | 54 | 29 | Disputed | Approved | On Track | Physical progress is at 29.0%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0106 | 400kV Substation | North-Eastern | 741.07 | 78.6 | 42 | 26.9 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 26.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0107 | 765kV Transmission Line | Western | 2456.45 | 428.7 | 46 | 62.7 | Pending Local | Approved | On Track | Physical progress is at 62.7%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-0108 | 765kV Transmission Line | Western | 4093.39 | 491.5 | 38 | 21.3 | Disputed | Stage-II Awaited | On Track | Physical progress is at 21.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0109 | 400kV Substation | Southern | 1232.2 | 61.1 | 26 | 83.6 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 83.6% with all statutory clearances in place. | 0 | Low
GRID-0110 | 220kV D/C Line | Eastern | 389.93 | 93.1 | 28 | 27 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 27.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0111 | 765kV Transmission Line | Western | 2883.42 | 379.8 | 36 | 50.6 | Clear | Stage-I Awaited | On Track | Physical progress is at 50.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0112 | 400kV Substation | Northern | 309.28 | 77.2 | 29 | 24 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 24.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0113 | 400kV Substation | Northern | 823.46 | 51.4 | 26 | 17.2 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 17.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0114 | 765kV Transmission Line | North-Eastern | 3110.34 | 406.9 | 47 | 37.4 | Clear | Stage-I Awaited | On Track | Physical progress is at 37.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0115 | 220kV D/C Line | Northern | 377.04 | 112.1 | 22 | 40.4 | Clear | Stage-I Awaited | On Track | Physical progress is at 40.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0116 | 220kV D/C Line | North-Eastern | 235.73 | 205.2 | 23 | 25.9 | Disputed | Stage-II Awaited | On Track | Physical progress is at 25.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0117 | 220kV D/C Line | Western | 632.15 | 181.1 | 17 | 31.6 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 31.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0118 | 765kV Transmission Line | Eastern | 3047.73 | 290.8 | 44 | 38.5 | Disputed | Approved | Equipment Delayed | Physical progress is at 38.5%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0119 | 400kV Substation | Southern | 392.08 | 87.8 | 26 | 23.9 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 23.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0120 | 220kV D/C Line | Western | 325.07 | 145.1 | 16 | 59.3 | Clear | Stage-I Awaited | On Track | Physical progress is at 59.3%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0121 | 220kV D/C Line | Western | 127.4 | 191.5 | 26 | 32.9 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 32.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0122 | 220kV D/C Line | North-Eastern | 136.66 | 176.2 | 22 | 27 | Clear | Stage-I Awaited | On Track | Physical progress is at 27.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0123 | 400kV Substation | North-Eastern | 1347.94 | 40 | 42 | 13.2 | Disputed | Approved | Equipment Delayed | Physical progress is at 13.2%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0124 | 220kV D/C Line | Eastern | 550.45 | 115.7 | 16 | 19 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 19.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-0125 | 765kV Transmission Line | Southern | 4816.84 | 345.9 | 43 | 73.8 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 73.8% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 1 | Medium
GRID-0126 | 220kV D/C Line | Western | 518.07 | 80.9 | 17 | 36.4 | Disputed | Stage-II Awaited | On Track | Physical progress is at 36.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0127 | 400kV Substation | North-Eastern | 641.91 | 77.4 | 38 | 78.6 | Clear | Stage-II Awaited | On Track | Physical progress is at 78.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0128 | 765kV Transmission Line | Southern | 3874.07 | 371.1 | 50 | 34.2 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 34.2%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0129 | 400kV Substation | Northern | 1069.41 | 88.7 | 41 | 12.1 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 12.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0130 | 400kV Substation | North-Eastern | 476.82 | 49.4 | 31 | 19.9 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 19.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0131 | 400kV Substation | Northern | 749.9 | 12.5 | 27 | 17.2 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 17.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0132 | 400kV Substation | North-Eastern | 306.3 | 17.1 | 32 | 25.2 | Clear | Approved | Insolvent | Physical progress is at 25.2%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0133 | 765kV Transmission Line | Southern | 2331.74 | 236.6 | 43 | 30.9 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 30.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0134 | 220kV D/C Line | North-Eastern | 502.53 | 193.7 | 21 | 24.3 | Pending Local | Approved | Insolvent | Physical progress is at 24.3%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0135 | 220kV D/C Line | Southern | 147.38 | 155.2 | 28 | 11.1 | Disputed | Stage-II Awaited | On Track | Physical progress is at 11.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0136 | 400kV Substation | Northern | 728.51 | 16.1 | 31 | 11.1 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 11.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0137 | 220kV D/C Line | Eastern | 786.57 | 145.7 | 17 | 33.6 | Clear | Approved | Insolvent | Physical progress is at 33.6%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0138 | 400kV Substation | Western | 352.57 | 28 | 25 | 16.3 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 16.3%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0139 | 765kV Transmission Line | Southern | 2456.26 | 439.8 | 49 | 22.4 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 22.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0140 | 765kV Transmission Line | Eastern | 1776.24 | 380.7 | 41 | 26.5 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 26.5%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0141 | 765kV Transmission Line | Eastern | 2730.41 | 212.7 | 47 | 19.1 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 19.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0142 | 220kV D/C Line | Eastern | 124.36 | 63.4 | 36 | 27 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 27.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0143 | 765kV Transmission Line | North-Eastern | 1981.93 | 310.1 | 46 | 28.4 | Disputed | Stage-I Awaited | On Track | Physical progress is at 28.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0144 | 220kV D/C Line | Northern | 283.24 | 102.1 | 26 | 24.9 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 24.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0145 | 765kV Transmission Line | Eastern | 4990.42 | 443.2 | 46 | 31.3 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 31.3%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0146 | 765kV Transmission Line | Western | 4272.23 | 271 | 51 | 21.7 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 21.7%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-0147 | 765kV Transmission Line | Southern | 2893.56 | 415.1 | 51 | 34.3 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 34.3%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0148 | 220kV D/C Line | North-Eastern | 341.16 | 225.6 | 36 | 22.6 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 22.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0149 | 400kV Substation | Western | 494.36 | 94.1 | 31 | 45.4 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 45.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0150 | 220kV D/C Line | Southern | 530.1 | 68.7 | 32 | 26.5 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 26.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0151 | 220kV D/C Line | Northern | 677.67 | 55.7 | 13 | 22.5 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 22.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0152 | 400kV Substation | Western | 1265.63 | 71.6 | 33 | 21 | Pending Local | Approved | Insolvent | Physical progress is at 21.0%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0153 | 765kV Transmission Line | Southern | 3623.31 | 293.8 | 58 | 22.9 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 22.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0154 | 400kV Substation | Northern | 620.97 | 32.3 | 27 | 16.2 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 16.2%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0155 | 220kV D/C Line | Southern | 232.88 | 81.9 | 28 | 33.6 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0156 | 220kV D/C Line | Southern | 134.06 | 106.3 | 31 | 20.8 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 20.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0157 | 400kV Substation | Northern | 780.7 | 61.3 | 30 | 50.6 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 50.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0158 | 765kV Transmission Line | Northern | 2878.66 | 438.5 | 46 | 22.5 | Disputed | Stage-I Awaited | On Track | Physical progress is at 22.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0159 | 765kV Transmission Line | Southern | 4313.88 | 355.8 | 40 | 14.1 | Disputed | Stage-II Awaited | On Track | Physical progress is at 14.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0160 | 220kV D/C Line | Southern | 455.12 | 151.9 | 27 | 18.3 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 18.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0161 | 220kV D/C Line | Northern | 517.84 | 103.1 | 32 | 26.8 | Disputed | Stage-II Awaited | On Track | Physical progress is at 26.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0162 | 765kV Transmission Line | Western | 1610.5 | 484.5 | 39 | 56.8 | Clear | Approved | Equipment Delayed | Physical progress is at 56.8%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0163 | 220kV D/C Line | Western | 387.26 | 205 | 27 | 42.4 | Disputed | Stage-II Awaited | On Track | Physical progress is at 42.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0164 | 220kV D/C Line | Eastern | 319.63 | 84.6 | 29 | 14.8 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 14.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0165 | 765kV Transmission Line | Southern | 4199.11 | 411.5 | 58 | 17.2 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 17.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0166 | 765kV Transmission Line | Southern | 1647.23 | 486.6 | 38 | 15.3 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 15.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0167 | 765kV Transmission Line | Northern | 3654.87 | 376 | 43 | 15.8 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 15.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0168 | 400kV Substation | Eastern | 420.65 | 79.4 | 24 | 26.3 | Disputed | Approved | Equipment Delayed | Physical progress is at 26.3%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0169 | 400kV Substation | Northern | 1389.52 | 18.1 | 42 | 20.4 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 20.4%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0170 | 400kV Substation | Eastern | 523.57 | 77.4 | 33 | 77.1 | Clear | Approved | Equipment Delayed | Physical progress is at 77.1%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0171 | 400kV Substation | Eastern | 1486.92 | 58.9 | 39 | 52.4 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 52.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0172 | 220kV D/C Line | Eastern | 553.8 | 193.7 | 12 | 25.3 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 25.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0173 | 765kV Transmission Line | Eastern | 3842.4 | 255.4 | 40 | 35.3 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 35.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0174 | 400kV Substation | Southern | 998.95 | 61.6 | 32 | 13 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 13.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0175 | 220kV D/C Line | North-Eastern | 746.17 | 227.6 | 36 | 44.6 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 44.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0176 | 400kV Substation | Western | 845.97 | 99 | 35 | 26.6 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 26.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-0177 | 220kV D/C Line | Eastern | 469.72 | 122.4 | 30 | 15.1 | Clear | Approved | Insolvent | Physical progress is at 15.1%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0178 | 765kV Transmission Line | Southern | 4490.7 | 332.6 | 57 | 32.5 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 32.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0179 | 400kV Substation | Western | 915.9 | 51.1 | 25 | 16.4 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 16.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0180 | 765kV Transmission Line | Eastern | 2705.85 | 219.1 | 37 | 36.4 | Clear | Stage-I Awaited | On Track | Physical progress is at 36.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0181 | 220kV D/C Line | Eastern | 362.12 | 228.3 | 26 | 26.3 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 26.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0182 | 765kV Transmission Line | North-Eastern | 2875.71 | 238.2 | 43 | 66.9 | Clear | Approved | Equipment Delayed | Physical progress is at 66.9%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0183 | 220kV D/C Line | Eastern | 676.35 | 99.5 | 23 | 21.3 | Clear | Stage-I Awaited | On Track | Physical progress is at 21.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0184 | 220kV D/C Line | Northern | 268.47 | 63.5 | 31 | 28.5 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 28.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0185 | 765kV Transmission Line | North-Eastern | 2260.44 | 459.1 | 37 | 43.1 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 43.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0186 | 765kV Transmission Line | Southern | 4566.9 | 495.7 | 52 | 23.9 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 23.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0187 | 220kV D/C Line | Eastern | 132.82 | 118.9 | 32 | 13.7 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 13.7%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 30 | High
GRID-0188 | 765kV Transmission Line | Western | 2552.58 | 412.3 | 50 | 35.5 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 35.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0189 | 400kV Substation | Northern | 1406.67 | 86.2 | 26 | 35.1 | Disputed | Stage-II Awaited | On Track | Physical progress is at 35.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0190 | 765kV Transmission Line | Western | 4316.28 | 376.3 | 57 | 32.1 | Disputed | Approved | Equipment Delayed | Physical progress is at 32.1%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0191 | 765kV Transmission Line | Northern | 4114.08 | 426.3 | 43 | 23.8 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 23.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0192 | 220kV D/C Line | Southern | 315.9 | 121.9 | 27 | 31 | Pending Local | Approved | Insolvent | Physical progress is at 31.0%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0193 | 400kV Substation | Eastern | 354.86 | 87.8 | 47 | 51.8 | Clear | Approved | Equipment Delayed | Physical progress is at 51.8%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0194 | 400kV Substation | Western | 755.81 | 85 | 39 | 30.5 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 30.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0195 | 765kV Transmission Line | Southern | 2092.43 | 416.1 | 51 | 10.8 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 10.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0196 | 765kV Transmission Line | Eastern | 1981.22 | 389.2 | 38 | 60.2 | Disputed | Approved | On Track | Physical progress is at 60.2%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0197 | 765kV Transmission Line | North-Eastern | 3732.05 | 480.2 | 51 | 10.3 | Disputed | Stage-I Awaited | On Track | Physical progress is at 10.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0198 | 765kV Transmission Line | North-Eastern | 4346.05 | 402.2 | 41 | 16 | Clear | Approved | Insolvent | Physical progress is at 16.0%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0199 | 400kV Substation | Southern | 1253.92 | 17.1 | 36 | 47.4 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 47.4%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0200 | 220kV D/C Line | Northern | 165.45 | 125.9 | 29 | 14.3 | Pending Local | Approved | Insolvent | Physical progress is at 14.3%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0201 | 220kV D/C Line | Southern | 496.1 | 221.6 | 15 | 76.1 | Disputed | Approved | On Track | Physical progress is at 76.1%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0202 | 400kV Substation | Northern | 1408.99 | 71.6 | 32 | 17.9 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 17.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-0203 | 765kV Transmission Line | Southern | 2068.58 | 272.1 | 48 | 22.5 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 22.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0204 | 400kV Substation | Western | 1306.41 | 40.7 | 48 | 29.6 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 29.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0205 | 400kV Substation | North-Eastern | 1429.37 | 48.9 | 45 | 27.8 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 27.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0206 | 400kV Substation | Western | 1187.59 | 38.5 | 27 | 54.4 | Clear | Approved | Equipment Delayed | Physical progress is at 54.4%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0207 | 765kV Transmission Line | Western | 1805.54 | 329.3 | 53 | 34.2 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 34.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0208 | 765kV Transmission Line | Southern | 2948.34 | 433.8 | 59 | 19.5 | Disputed | Approved | Insolvent | Physical progress is at 19.5%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0209 | 400kV Substation | Southern | 891.75 | 15.7 | 37 | 16.3 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 16.3%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0210 | 220kV D/C Line | North-Eastern | 236.88 | 71.4 | 21 | 30.1 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 30.1%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0211 | 400kV Substation | Eastern | 1278.57 | 87.4 | 43 | 22 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 22.0%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0212 | 400kV Substation | Southern | 1181.85 | 67 | 42 | 19.1 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 19.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0213 | 220kV D/C Line | North-Eastern | 118.84 | 195.4 | 34 | 26.8 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 26.8%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0214 | 765kV Transmission Line | Southern | 3805.32 | 414.6 | 48 | 20 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 20.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-0215 | 400kV Substation | North-Eastern | 1012.58 | 92.3 | 27 | 26.2 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 26.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0216 | 400kV Substation | Eastern | 427.13 | 18.9 | 31 | 19.8 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 19.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0217 | 765kV Transmission Line | Eastern | 1865.92 | 324.8 | 38 | 52.5 | Clear | Stage-II Awaited | On Track | Physical progress is at 52.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0218 | 765kV Transmission Line | North-Eastern | 3190.24 | 342.8 | 50 | 11.1 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 11.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0219 | 400kV Substation | Northern | 1112.57 | 24.8 | 47 | 53.2 | Clear | Stage-II Awaited | On Track | Physical progress is at 53.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0220 | 400kV Substation | Western | 1257.31 | 66.7 | 29 | 21.2 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 21.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0221 | 220kV D/C Line | Western | 244.05 | 200.5 | 14 | 18.1 | Disputed | Approved | Insolvent | Physical progress is at 18.1%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0222 | 400kV Substation | Eastern | 933.26 | 67.5 | 43 | 53.8 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 53.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0223 | 220kV D/C Line | North-Eastern | 159.33 | 76.8 | 15 | 34.9 | Clear | Stage-I Awaited | On Track | Physical progress is at 34.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0224 | 220kV D/C Line | Eastern | 392.77 | 77.6 | 24 | 42.2 | Pending Local | Approved | Equipment Delayed | Physical progress is at 42.2%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0225 | 765kV Transmission Line | Western | 2601.03 | 335.3 | 37 | 72.6 | Pending Local | Approved | Equipment Delayed | Physical progress is at 72.6%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0226 | 400kV Substation | Eastern | 798.76 | 85.6 | 39 | 51.8 | Clear | Approved | Insolvent | Physical progress is at 51.8%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0227 | 400kV Substation | Northern | 629.82 | 58.4 | 29 | 12.8 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 12.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0228 | 220kV D/C Line | Northern | 632 | 138.3 | 18 | 16.2 | Pending Local | Approved | Insolvent | Physical progress is at 16.2%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0229 | 400kV Substation | Southern | 1334.64 | 17.8 | 27 | 27.2 | Clear | Approved | Insolvent | Physical progress is at 27.2%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0230 | 765kV Transmission Line | North-Eastern | 1987.32 | 262 | 42 | 32.9 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 32.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0231 | 400kV Substation | North-Eastern | 620.81 | 87.2 | 45 | 79.7 | Clear | Approved | Equipment Delayed | Physical progress is at 79.7%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0232 | 220kV D/C Line | Western | 274.77 | 192.3 | 19 | 19.4 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 19.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0233 | 220kV D/C Line | Southern | 586.29 | 225.5 | 26 | 28.3 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 28.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0234 | 765kV Transmission Line | North-Eastern | 2892.01 | 490.4 | 42 | 24.2 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 24.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0235 | 765kV Transmission Line | Northern | 3691.63 | 451 | 36 | 40 | Clear | Approved | Equipment Delayed | Physical progress is at 40.0%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0236 | 765kV Transmission Line | Western | 4587.52 | 290.6 | 44 | 34.9 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 34.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0237 | 765kV Transmission Line | Eastern | 3689.61 | 417.8 | 60 | 12.4 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 12.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0238 | 765kV Transmission Line | Western | 3577.88 | 355.8 | 50 | 30.4 | Clear | Approved | Insolvent | Physical progress is at 30.4%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0239 | 220kV D/C Line | Western | 434.39 | 95.8 | 14 | 34.7 | Disputed | Approved | On Track | Physical progress is at 34.7%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0240 | 765kV Transmission Line | Eastern | 4207.11 | 425.9 | 40 | 44.4 | Disputed | Stage-II Awaited | On Track | Physical progress is at 44.4%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0241 | 400kV Substation | Western | 1053.7 | 23.6 | 37 | 25.6 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 25.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0242 | 400kV Substation | Southern | 1249.29 | 32.3 | 44 | 25 | Clear | Approved | Insolvent | Physical progress is at 25.0%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0243 | 220kV D/C Line | Northern | 693.52 | 181.7 | 21 | 19.8 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 19.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0244 | 765kV Transmission Line | Eastern | 2850.6 | 272.3 | 56 | 33.3 | Disputed | Approved | Insolvent | Physical progress is at 33.3%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0245 | 220kV D/C Line | Eastern | 355.79 | 186.6 | 36 | 42.7 | Pending Local | Approved | On Track | Physical progress is at 42.7%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0246 | 765kV Transmission Line | Northern | 4729.03 | 484.6 | 48 | 27.5 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 27.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 32 | High
GRID-0247 | 765kV Transmission Line | Southern | 1776.58 | 476.3 | 40 | 27.5 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 27.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0248 | 765kV Transmission Line | Eastern | 1905.95 | 383.7 | 37 | 27.7 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 27.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0249 | 400kV Substation | Southern | 927.61 | 80.5 | 47 | 69.3 | Pending Local | Approved | Equipment Delayed | Physical progress is at 69.3%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0250 | 400kV Substation | Eastern | 626.38 | 15.7 | 46 | 22.8 | Disputed | Stage-II Awaited | On Track | Physical progress is at 22.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0251 | 220kV D/C Line | Western | 357.38 | 101 | 15 | 22.7 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 22.7%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0252 | 765kV Transmission Line | Eastern | 2773.92 | 476.1 | 41 | 18 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 18.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0253 | 400kV Substation | Northern | 985.84 | 20.7 | 45 | 93.4 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 93.4% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 0 | Low
GRID-0254 | 400kV Substation | Northern | 963.71 | 10.7 | 30 | 43.7 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 43.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0255 | 765kV Transmission Line | Northern | 4763.39 | 207.2 | 53 | 29 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 29.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0256 | 765kV Transmission Line | Western | 3354.35 | 271.5 | 51 | 12.3 | Clear | Approved | Insolvent | Physical progress is at 12.3%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0257 | 220kV D/C Line | Eastern | 590.59 | 124.5 | 35 | 65.5 | Clear | Stage-II Awaited | On Track | Physical progress is at 65.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0258 | 765kV Transmission Line | North-Eastern | 3487.37 | 330.5 | 40 | 27.5 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 27.5%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0259 | 400kV Substation | Southern | 580.33 | 94.9 | 28 | 46.6 | Disputed | Approved | On Track | Physical progress is at 46.6%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0260 | 400kV Substation | Eastern | 444.88 | 42.2 | 48 | 31.3 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 31.3%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0261 | 220kV D/C Line | Southern | 678.47 | 189.4 | 13 | 48.4 | Clear | Stage-I Awaited | On Track | Physical progress is at 48.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0262 | 400kV Substation | North-Eastern | 358.74 | 36.9 | 29 | 12.4 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 12.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0263 | 765kV Transmission Line | Northern | 1715.84 | 434.3 | 43 | 67.5 | Clear | Approved | Equipment Delayed | Physical progress is at 67.5%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0264 | 220kV D/C Line | North-Eastern | 281.17 | 212.5 | 12 | 30.2 | Clear | Approved | Insolvent | Physical progress is at 30.2%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0265 | 400kV Substation | Northern | 351.24 | 51.5 | 29 | 19.6 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 19.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0266 | 765kV Transmission Line | Western | 2462.44 | 333.8 | 40 | 17.4 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 17.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0267 | 765kV Transmission Line | Northern | 2479.22 | 241.2 | 42 | 51.3 | Disputed | Stage-II Awaited | On Track | Physical progress is at 51.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0268 | 220kV D/C Line | Eastern | 340.82 | 163.1 | 22 | 43.9 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 43.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0269 | 765kV Transmission Line | Eastern | 3353.01 | 430.1 | 43 | 69.3 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 69.3% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 0 | Low
GRID-0270 | 765kV Transmission Line | Western | 2327.93 | 295.4 | 59 | 24.1 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 24.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0271 | 765kV Transmission Line | Eastern | 1632.87 | 216.9 | 55 | 10 | Clear | Approved | Insolvent | Physical progress is at 10.0%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0272 | 765kV Transmission Line | Southern | 4009.28 | 475.6 | 46 | 87.1 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 87.1% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 0 | Low
GRID-0273 | 220kV D/C Line | Northern | 335.59 | 114.5 | 17 | 27.7 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 27.7%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0274 | 400kV Substation | Southern | 1180.79 | 36.5 | 29 | 34.9 | Disputed | Approved | Insolvent | Physical progress is at 34.9%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0275 | 220kV D/C Line | Southern | 744.73 | 243.5 | 19 | 18.3 | Disputed | Stage-II Awaited | On Track | Physical progress is at 18.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0276 | 400kV Substation | Southern | 501.46 | 89.7 | 26 | 16.6 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 16.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0277 | 400kV Substation | Northern | 1164.5 | 14.3 | 38 | 32 | Disputed | Stage-I Awaited | On Track | Physical progress is at 32.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0278 | 765kV Transmission Line | Eastern | 4260.55 | 373.4 | 60 | 22.9 | Disputed | Approved | On Track | Physical progress is at 22.9%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0279 | 400kV Substation | Northern | 682.46 | 95.6 | 26 | 61.9 | Pending Local | Approved | Equipment Delayed | Physical progress is at 61.9%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0280 | 220kV D/C Line | North-Eastern | 725.26 | 190.9 | 25 | 11.3 | Disputed | Approved | Insolvent | Physical progress is at 11.3%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0281 | 765kV Transmission Line | Eastern | 3940.19 | 416.6 | 59 | 12.4 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 12.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0282 | 765kV Transmission Line | Southern | 1513.35 | 226.3 | 57 | 28.3 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 28.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0283 | 400kV Substation | Northern | 670.02 | 45.8 | 39 | 14.6 | Disputed | Stage-I Awaited | On Track | Physical progress is at 14.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0284 | 765kV Transmission Line | Eastern | 1656.16 | 331.9 | 44 | 28.8 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 28.8%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0285 | 220kV D/C Line | Southern | 665.73 | 132.8 | 36 | 19.7 | Disputed | Approved | Insolvent | Physical progress is at 19.7%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0286 | 220kV D/C Line | Western | 433.38 | 65.8 | 34 | 33.7 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 33.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0287 | 765kV Transmission Line | Western | 4329.61 | 237.9 | 49 | 53.4 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 53.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0288 | 220kV D/C Line | Northern | 160.92 | 161.3 | 29 | 27.5 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 27.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0289 | 765kV Transmission Line | Western | 3483.08 | 374.8 | 39 | 74.7 | Clear | Stage-II Awaited | On Track | Physical progress is at 74.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0290 | 400kV Substation | Southern | 759.65 | 53.7 | 43 | 56.1 | Pending Local | Approved | On Track | Physical progress is at 56.1%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0291 | 220kV D/C Line | Eastern | 127.15 | 227.9 | 22 | 56.8 | Disputed | Approved | On Track | Physical progress is at 56.8%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0292 | 765kV Transmission Line | Southern | 4360.85 | 290.9 | 44 | 17.5 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 17.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0293 | 400kV Substation | Eastern | 1025.97 | 18 | 38 | 22.9 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 22.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0294 | 220kV D/C Line | Western | 145.93 | 191.9 | 24 | 14.8 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 14.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0295 | 765kV Transmission Line | Northern | 3097.57 | 475.4 | 58 | 25.9 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 25.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0296 | 765kV Transmission Line | Southern | 3210.75 | 333.8 | 51 | 28.7 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 28.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0297 | 765kV Transmission Line | Eastern | 1673.78 | 456.1 | 60 | 26.9 | Clear | Approved | Insolvent | Physical progress is at 26.9%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0298 | 220kV D/C Line | Eastern | 459.3 | 222.9 | 36 | 44 | Disputed | Approved | Equipment Delayed | Physical progress is at 44.0%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0299 | 400kV Substation | North-Eastern | 1266.1 | 37.5 | 46 | 16.3 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 16.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0300 | 220kV D/C Line | Northern | 105.14 | 249.9 | 23 | 12.7 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 12.7%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0301 | 220kV D/C Line | Southern | 703.04 | 102.2 | 34 | 32.5 | Disputed | Stage-I Awaited | On Track | Physical progress is at 32.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0302 | 220kV D/C Line | Western | 604.9 | 181.1 | 21 | 24.6 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 24.6%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0303 | 220kV D/C Line | North-Eastern | 546.82 | 145.1 | 33 | 31.8 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 31.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0304 | 220kV D/C Line | North-Eastern | 634.04 | 86.6 | 33 | 28.9 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 28.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0305 | 400kV Substation | Southern | 612.67 | 36.5 | 27 | 33.6 | Pending Local | Approved | Insolvent | Physical progress is at 33.6%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0306 | 765kV Transmission Line | North-Eastern | 1919.36 | 404.2 | 52 | 59.7 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 59.7%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0307 | 220kV D/C Line | Eastern | 200.26 | 222.5 | 17 | 25.9 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 25.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0308 | 400kV Substation | Western | 1213.43 | 25.2 | 48 | 44.6 | Clear | Stage-I Awaited | On Track | Physical progress is at 44.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0309 | 400kV Substation | Eastern | 1458.39 | 44.5 | 25 | 32.3 | Disputed | Approved | Insolvent | Physical progress is at 32.3%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0310 | 220kV D/C Line | Northern | 538.68 | 99.8 | 34 | 40.1 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 40.1%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0311 | 765kV Transmission Line | Northern | 2543.71 | 287.2 | 59 | 34.9 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 34.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0312 | 765kV Transmission Line | Western | 4818.3 | 475.5 | 48 | 67.4 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 67.4% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 0 | Low
GRID-0313 | 400kV Substation | Northern | 750.23 | 67.6 | 48 | 46.1 | Disputed | Stage-II Awaited | On Track | Physical progress is at 46.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0314 | 220kV D/C Line | Northern | 391.74 | 126.1 | 29 | 27.1 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 27.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-0315 | 220kV D/C Line | Northern | 563.74 | 104 | 31 | 31.3 | Disputed | Approved | Equipment Delayed | Physical progress is at 31.3%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0316 | 765kV Transmission Line | North-Eastern | 2199.12 | 278.9 | 52 | 14 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 14.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0317 | 220kV D/C Line | Eastern | 331.42 | 50.5 | 33 | 22.4 | Clear | Approved | Insolvent | Physical progress is at 22.4%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0318 | 220kV D/C Line | Northern | 606.49 | 70.3 | 20 | 38.6 | Disputed | Approved | Equipment Delayed | Physical progress is at 38.6%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0319 | 765kV Transmission Line | Southern | 2760.75 | 403 | 49 | 40.4 | Disputed | Approved | On Track | Physical progress is at 40.4%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0320 | 220kV D/C Line | Western | 330.06 | 228.9 | 31 | 27.3 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 27.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0321 | 400kV Substation | Southern | 1302.85 | 72.1 | 39 | 67.8 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 67.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0322 | 765kV Transmission Line | Eastern | 4689.29 | 344.8 | 54 | 29.5 | Disputed | Stage-I Awaited | On Track | Physical progress is at 29.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0323 | 400kV Substation | Eastern | 435.52 | 47 | 25 | 27.6 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 27.6%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0324 | 220kV D/C Line | North-Eastern | 581.77 | 173.6 | 25 | 26.6 | Disputed | Stage-II Awaited | On Track | Physical progress is at 26.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0325 | 765kV Transmission Line | North-Eastern | 4622.22 | 383.9 | 36 | 22.4 | Disputed | Approved | Insolvent | Physical progress is at 22.4%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0326 | 400kV Substation | Southern | 589.07 | 97.3 | 25 | 30.4 | Disputed | Approved | Insolvent | Physical progress is at 30.4%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0327 | 400kV Substation | North-Eastern | 837.72 | 87.1 | 38 | 44.1 | Pending Local | Approved | Equipment Delayed | Physical progress is at 44.1%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0328 | 220kV D/C Line | North-Eastern | 100.12 | 68.2 | 31 | 19.1 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 19.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0329 | 400kV Substation | North-Eastern | 1220.9 | 64 | 46 | 29 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 29.0%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-0330 | 400kV Substation | Southern | 957.23 | 43.7 | 27 | 72.9 | Clear | Approved | Equipment Delayed | Physical progress is at 72.9%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0331 | 765kV Transmission Line | Southern | 3637.98 | 256.3 | 48 | 24.3 | Clear | Stage-I Awaited | On Track | Physical progress is at 24.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0332 | 765kV Transmission Line | North-Eastern | 1931.27 | 467.5 | 50 | 23.3 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 23.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0333 | 220kV D/C Line | Western | 584.27 | 84.7 | 16 | 32.1 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 32.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0334 | 220kV D/C Line | Western | 291.52 | 242.7 | 21 | 64.1 | Pending Local | Approved | On Track | Physical progress is at 64.1%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0335 | 220kV D/C Line | Southern | 690.15 | 159.6 | 22 | 25.6 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 25.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0336 | 220kV D/C Line | Western | 452.73 | 188.9 | 22 | 26.9 | Disputed | Approved | Equipment Delayed | Physical progress is at 26.9%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0337 | 765kV Transmission Line | North-Eastern | 1872.65 | 314.3 | 37 | 50 | Disputed | Approved | On Track | Physical progress is at 50.0%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0338 | 400kV Substation | Southern | 475.71 | 15.6 | 33 | 72.6 | Clear | Stage-II Awaited | On Track | Physical progress is at 72.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0339 | 220kV D/C Line | North-Eastern | 705.39 | 198.5 | 29 | 27.3 | Pending Local | Approved | Insolvent | Physical progress is at 27.3%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0340 | 400kV Substation | Eastern | 1448.04 | 97.8 | 34 | 28.1 | Disputed | Approved | On Track | Physical progress is at 28.1%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0341 | 765kV Transmission Line | Southern | 4142.88 | 364 | 55 | 58 | Clear | Stage-II Awaited | On Track | Physical progress is at 58.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0342 | 765kV Transmission Line | Western | 4868.66 | 420.5 | 39 | 25.2 | Pending Local | Approved | Equipment Delayed | Physical progress is at 25.2%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0343 | 765kV Transmission Line | Southern | 3132.16 | 481.2 | 37 | 33.3 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 33.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-0344 | 220kV D/C Line | North-Eastern | 350.66 | 206.8 | 22 | 71.5 | Disputed | Approved | On Track | Physical progress is at 71.5%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0345 | 400kV Substation | North-Eastern | 944.44 | 18.3 | 31 | 31.7 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 31.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0346 | 220kV D/C Line | Northern | 180.31 | 119.2 | 19 | 32.1 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 32.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0347 | 400kV Substation | North-Eastern | 1168.77 | 12.2 | 40 | 17.4 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 17.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0348 | 220kV D/C Line | Northern | 763.75 | 83.5 | 36 | 46.8 | Disputed | Stage-II Awaited | On Track | Physical progress is at 46.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0349 | 765kV Transmission Line | Western | 3382.14 | 410.8 | 59 | 58.4 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 58.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0350 | 765kV Transmission Line | Northern | 1689.94 | 438.3 | 53 | 56.3 | Clear | Stage-II Awaited | On Track | Physical progress is at 56.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0351 | 220kV D/C Line | Eastern | 403.12 | 53.4 | 33 | 70.2 | Clear | Stage-II Awaited | On Track | Physical progress is at 70.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0352 | 765kV Transmission Line | Northern | 2751.95 | 350.9 | 45 | 33.2 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 33.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 30 | High
GRID-0353 | 400kV Substation | Western | 940.16 | 22.3 | 36 | 32.2 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 32.2%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 30 | High
GRID-0354 | 765kV Transmission Line | Northern | 1517.6 | 379 | 53 | 28.5 | Disputed | Approved | Equipment Delayed | Physical progress is at 28.5%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0355 | 765kV Transmission Line | Western | 3659.1 | 275.8 | 39 | 28.8 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 28.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0356 | 220kV D/C Line | North-Eastern | 151.2 | 184.3 | 20 | 22.2 | Clear | Approved | Insolvent | Physical progress is at 22.2%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0357 | 400kV Substation | Western | 1105.55 | 31.1 | 33 | 39.4 | Disputed | Approved | On Track | Physical progress is at 39.4%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0358 | 220kV D/C Line | Southern | 585.42 | 80.5 | 30 | 16.2 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 16.2%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0359 | 400kV Substation | Southern | 461.17 | 76 | 39 | 14.4 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 14.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0360 | 220kV D/C Line | Western | 284.26 | 227.3 | 14 | 72.5 | Disputed | Approved | On Track | Physical progress is at 72.5%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0361 | 220kV D/C Line | Western | 734.41 | 160.3 | 29 | 15.6 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 15.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0362 | 220kV D/C Line | North-Eastern | 163.39 | 122.8 | 12 | 22.9 | Disputed | Approved | Insolvent | Physical progress is at 22.9%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0363 | 765kV Transmission Line | North-Eastern | 4820.49 | 397.8 | 40 | 29 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 29.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0364 | 400kV Substation | Western | 351.37 | 28.6 | 35 | 12.6 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 12.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0365 | 220kV D/C Line | North-Eastern | 499.11 | 125.3 | 24 | 19.4 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 19.4%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0366 | 400kV Substation | Southern | 884.23 | 53.4 | 43 | 26.6 | Clear | Stage-II Awaited | On Track | Physical progress is at 26.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0367 | 220kV D/C Line | Southern | 248.06 | 87.4 | 23 | 30.3 | Disputed | Stage-II Awaited | On Track | Physical progress is at 30.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0368 | 400kV Substation | Eastern | 874.83 | 63.2 | 44 | 45.1 | Pending Local | Approved | On Track | Physical progress is at 45.1%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-0369 | 765kV Transmission Line | Western | 3703.39 | 211.8 | 54 | 76.9 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 76.9% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 1 | Medium
GRID-0370 | 765kV Transmission Line | Western | 3072.21 | 497.8 | 51 | 71.8 | Clear | Approved | Equipment Delayed | Physical progress is at 71.8%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0371 | 220kV D/C Line | North-Eastern | 285.16 | 194.8 | 22 | 19.6 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 19.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0372 | 220kV D/C Line | North-Eastern | 579.06 | 215.3 | 31 | 75.1 | Clear | Approved | Equipment Delayed | Physical progress is at 75.1%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0373 | 765kV Transmission Line | Eastern | 3807.87 | 470.6 | 53 | 20.5 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 20.5%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0374 | 765kV Transmission Line | Eastern | 4263.44 | 314.4 | 54 | 16.4 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 16.4%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0375 | 220kV D/C Line | North-Eastern | 386.05 | 87.8 | 34 | 10.2 | Disputed | Approved | Insolvent | Physical progress is at 10.2%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0376 | 400kV Substation | Southern | 427.9 | 48.3 | 42 | 25.3 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 25.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0377 | 220kV D/C Line | North-Eastern | 437.73 | 124 | 29 | 28.4 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 28.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0378 | 400kV Substation | Western | 420.33 | 55.8 | 34 | 34.1 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 34.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0379 | 400kV Substation | North-Eastern | 822.45 | 15.8 | 31 | 19.6 | Pending Local | Approved | Insolvent | Physical progress is at 19.6%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0380 | 220kV D/C Line | North-Eastern | 140.22 | 204.7 | 17 | 14.9 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 14.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0381 | 400kV Substation | Western | 1086.02 | 97.8 | 26 | 22.9 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 22.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0382 | 220kV D/C Line | North-Eastern | 740.51 | 119.6 | 20 | 57.2 | Clear | Stage-II Awaited | On Track | Physical progress is at 57.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0383 | 765kV Transmission Line | Southern | 2112.62 | 351.9 | 53 | 52.1 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 52.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0384 | 220kV D/C Line | Eastern | 776.24 | 162.6 | 36 | 22 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 22.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0385 | 400kV Substation | Western | 1112.3 | 30.7 | 34 | 30.8 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 30.8%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0386 | 400kV Substation | Southern | 391.23 | 93.8 | 39 | 14.6 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 14.6%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0387 | 220kV D/C Line | Western | 264.4 | 98.4 | 20 | 89.3 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 89.3% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 0 | Low
GRID-0388 | 765kV Transmission Line | Eastern | 3648.39 | 429.3 | 53 | 22.3 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 22.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0389 | 765kV Transmission Line | North-Eastern | 2480.93 | 266.6 | 54 | 20.6 | Clear | Approved | Insolvent | Physical progress is at 20.6%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0390 | 220kV D/C Line | Southern | 375.6 | 187.3 | 17 | 17.9 | Pending Local | Approved | Insolvent | Physical progress is at 17.9%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0391 | 220kV D/C Line | Western | 365.6 | 70.1 | 23 | 15.9 | Disputed | Stage-I Awaited | On Track | Physical progress is at 15.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0392 | 400kV Substation | Western | 898.52 | 28.9 | 46 | 24.3 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 24.3%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0393 | 765kV Transmission Line | North-Eastern | 3012.77 | 314.3 | 40 | 36.9 | Disputed | Approved | Equipment Delayed | Physical progress is at 36.9%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0394 | 400kV Substation | Southern | 601.17 | 87.3 | 25 | 15.4 | Pending Local | Approved | Insolvent | Physical progress is at 15.4%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0395 | 220kV D/C Line | Northern | 414.9 | 116.9 | 23 | 20.3 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 20.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0396 | 220kV D/C Line | North-Eastern | 554.91 | 157.7 | 36 | 32.2 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 32.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0397 | 400kV Substation | Western | 1341.91 | 67.7 | 34 | 14 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 14.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0398 | 220kV D/C Line | Southern | 597.3 | 171.1 | 24 | 20.3 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 20.3%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0399 | 220kV D/C Line | Western | 563.42 | 238.1 | 34 | 55.9 | Disputed | Approved | On Track | Physical progress is at 55.9%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0400 | 765kV Transmission Line | Eastern | 3419.52 | 207.9 | 48 | 44.7 | Disputed | Approved | On Track | Physical progress is at 44.7%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0401 | 220kV D/C Line | Eastern | 316.56 | 99.5 | 21 | 53.5 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 53.5%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0402 | 220kV D/C Line | Southern | 702.26 | 115 | 27 | 43.6 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 43.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0403 | 220kV D/C Line | North-Eastern | 316.76 | 119.4 | 29 | 54.6 | Clear | Approved | Equipment Delayed | Physical progress is at 54.6%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0404 | 765kV Transmission Line | Southern | 1536.95 | 357 | 60 | 27.2 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 27.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0405 | 400kV Substation | Northern | 1219.04 | 81.8 | 43 | 14.7 | Clear | Approved | Insolvent | Physical progress is at 14.7%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0406 | 400kV Substation | Western | 495.92 | 76.3 | 36 | 45 | Pending Local | Approved | Equipment Delayed | Physical progress is at 45.0%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0407 | 400kV Substation | North-Eastern | 1270.57 | 47.2 | 26 | 65.5 | Clear | Approved | Equipment Delayed | Physical progress is at 65.5%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0408 | 400kV Substation | North-Eastern | 890.4 | 38.9 | 28 | 78.9 | Clear | Stage-II Awaited | On Track | Physical progress is at 78.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0409 | 400kV Substation | Western | 1158.24 | 75.4 | 31 | 48.7 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 48.7% with all statutory clearances in place. | 1 | Medium
GRID-0410 | 400kV Substation | Northern | 696.3 | 85.9 | 28 | 14.5 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 14.5%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0411 | 765kV Transmission Line | Northern | 4911.09 | 414.4 | 48 | 21.5 | Pending Local | Approved | Insolvent | Physical progress is at 21.5%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0412 | 400kV Substation | Eastern | 1117.73 | 38.1 | 34 | 33.4 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 33.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0413 | 400kV Substation | Eastern | 1066.22 | 27.9 | 25 | 65.3 | Disputed | Approved | On Track | Physical progress is at 65.3%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0414 | 765kV Transmission Line | Western | 4280.37 | 375.4 | 48 | 67.5 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 67.5% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 1 | Medium
GRID-0415 | 765kV Transmission Line | Eastern | 1819.91 | 385.6 | 60 | 45.8 | Disputed | Approved | On Track | Physical progress is at 45.8%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0416 | 765kV Transmission Line | Eastern | 2314.36 | 494.5 | 56 | 19.4 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 19.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-0417 | 400kV Substation | Eastern | 970.83 | 58.8 | 39 | 52.9 | Clear | Stage-II Awaited | On Track | Physical progress is at 52.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0418 | 400kV Substation | North-Eastern | 1397.37 | 59.9 | 26 | 41.7 | Disputed | Approved | Equipment Delayed | Physical progress is at 41.7%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0419 | 220kV D/C Line | North-Eastern | 365.33 | 87.1 | 12 | 11.6 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 11.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 30 | High
GRID-0420 | 220kV D/C Line | Western | 529.13 | 114.5 | 32 | 66.4 | Pending Local | Approved | On Track | Physical progress is at 66.4%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0421 | 765kV Transmission Line | Western | 4557.22 | 260.6 | 51 | 66.3 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 66.3% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 1 | Medium
GRID-0422 | 220kV D/C Line | Northern | 109.16 | 234.2 | 32 | 54.4 | Pending Local | Approved | Equipment Delayed | Physical progress is at 54.4%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0423 | 400kV Substation | Northern | 1288.37 | 33.9 | 25 | 58.4 | Disputed | Approved | Equipment Delayed | Physical progress is at 58.4%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0424 | 220kV D/C Line | Western | 472.16 | 87.9 | 28 | 28.7 | Disputed | Approved | Insolvent | Physical progress is at 28.7%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0425 | 220kV D/C Line | North-Eastern | 350.57 | 141.7 | 33 | 62 | Pending Local | Approved | On Track | Physical progress is at 62.0%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-0426 | 400kV Substation | Western | 940.68 | 64 | 35 | 30.7 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 30.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0427 | 220kV D/C Line | North-Eastern | 249.75 | 203.1 | 35 | 28.2 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 28.2%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0428 | 220kV D/C Line | Western | 795.39 | 110.4 | 21 | 70.9 | Clear | Approved | Equipment Delayed | Physical progress is at 70.9%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0429 | 220kV D/C Line | North-Eastern | 489.43 | 235.2 | 16 | 46.2 | Clear | Approved | Equipment Delayed | Physical progress is at 46.2%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0430 | 400kV Substation | North-Eastern | 599.83 | 33.1 | 33 | 48.9 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 48.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0431 | 400kV Substation | North-Eastern | 1283.42 | 18.6 | 44 | 12 | Pending Local | Approved | Insolvent | Physical progress is at 12.0%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0432 | 400kV Substation | Eastern | 799.83 | 88.1 | 48 | 29.4 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 29.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0433 | 400kV Substation | North-Eastern | 349.42 | 58.6 | 28 | 26.8 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 26.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0434 | 765kV Transmission Line | Eastern | 2514.24 | 318.3 | 40 | 61.9 | Pending Local | Approved | Equipment Delayed | Physical progress is at 61.9%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0435 | 400kV Substation | North-Eastern | 821.39 | 72.8 | 48 | 19.9 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 19.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0436 | 765kV Transmission Line | Northern | 2431.9 | 329 | 57 | 36.9 | Disputed | Approved | On Track | Physical progress is at 36.9%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0437 | 765kV Transmission Line | Southern | 2705.84 | 396.6 | 60 | 44.9 | Pending Local | Approved | Equipment Delayed | Physical progress is at 44.9%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0438 | 765kV Transmission Line | Western | 3898.76 | 246.8 | 59 | 29.7 | Clear | Approved | Insolvent | Physical progress is at 29.7%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0439 | 400kV Substation | Northern | 711.93 | 82.4 | 33 | 28.5 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 28.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0440 | 220kV D/C Line | North-Eastern | 625.25 | 159.8 | 31 | 24.6 | Disputed | Approved | Insolvent | Physical progress is at 24.6%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0441 | 765kV Transmission Line | Northern | 2494.05 | 436.8 | 55 | 42.7 | Pending Local | Approved | Equipment Delayed | Physical progress is at 42.7%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0442 | 220kV D/C Line | Southern | 705 | 53.8 | 32 | 76.2 | Pending Local | Approved | Equipment Delayed | Physical progress is at 76.2%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0443 | 765kV Transmission Line | Western | 3252.28 | 337.4 | 58 | 53.3 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 53.3% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 1 | Medium
GRID-0444 | 400kV Substation | Southern | 726.45 | 37.2 | 40 | 32.3 | Pending Local | Approved | Insolvent | Physical progress is at 32.3%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0445 | 765kV Transmission Line | Western | 2696.25 | 317.9 | 40 | 29.6 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 29.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0446 | 400kV Substation | North-Eastern | 695.14 | 58.8 | 30 | 13.5 | Disputed | Approved | Insolvent | Physical progress is at 13.5%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0447 | 765kV Transmission Line | North-Eastern | 4709.89 | 295.2 | 53 | 53.6 | Disputed | Stage-II Awaited | On Track | Physical progress is at 53.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0448 | 400kV Substation | Eastern | 1453.44 | 37.3 | 47 | 13.3 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 13.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0449 | 220kV D/C Line | Western | 261.64 | 55.2 | 14 | 27.8 | Disputed | Stage-I Awaited | On Track | Physical progress is at 27.8%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0450 | 400kV Substation | Eastern | 868.62 | 24.7 | 31 | 58 | Clear | Stage-I Awaited | On Track | Physical progress is at 58.0%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0451 | 220kV D/C Line | Western | 630.44 | 63.2 | 26 | 20.7 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 20.7%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0452 | 400kV Substation | North-Eastern | 1426.97 | 61.5 | 41 | 21.4 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 21.4%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0453 | 220kV D/C Line | Northern | 490.39 | 153.2 | 32 | 55.9 | Clear | Approved | Equipment Delayed | Physical progress is at 55.9%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0454 | 400kV Substation | Eastern | 499.78 | 36.5 | 25 | 12.3 | Disputed | Stage-II Awaited | On Track | Physical progress is at 12.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0455 | 765kV Transmission Line | North-Eastern | 4782.45 | 408.8 | 40 | 21.3 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 21.3%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0456 | 400kV Substation | Southern | 1130.06 | 91.6 | 29 | 48.2 | Disputed | Stage-II Awaited | On Track | Physical progress is at 48.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0457 | 765kV Transmission Line | North-Eastern | 3975.48 | 418.1 | 52 | 50.7 | Disputed | Approved | Equipment Delayed | Physical progress is at 50.7%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0458 | 765kV Transmission Line | Western | 2126.03 | 413.6 | 49 | 14.5 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 14.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0459 | 220kV D/C Line | Southern | 108.55 | 149.5 | 27 | 15.4 | Disputed | Approved | Insolvent | Physical progress is at 15.4%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0460 | 400kV Substation | Eastern | 395.29 | 64 | 31 | 14.6 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 14.6%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0461 | 765kV Transmission Line | Northern | 3834.49 | 451.4 | 45 | 56.7 | Pending Local | Approved | On Track | Physical progress is at 56.7%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-0462 | 765kV Transmission Line | Southern | 3638.81 | 407.5 | 55 | 33.3 | Disputed | Stage-II Awaited | On Track | Physical progress is at 33.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0463 | 400kV Substation | Southern | 1377.04 | 83.8 | 48 | 25.4 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 25.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0464 | 400kV Substation | North-Eastern | 796.51 | 28.9 | 30 | 59.3 | Disputed | Approved | On Track | Physical progress is at 59.3%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0465 | 400kV Substation | North-Eastern | 1317.36 | 33.4 | 42 | 23 | Disputed | Stage-I Awaited | On Track | Physical progress is at 23.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0466 | 765kV Transmission Line | North-Eastern | 2314.53 | 287.1 | 42 | 65 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 65.0% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 1 | Medium
GRID-0467 | 400kV Substation | Northern | 700.55 | 60.4 | 44 | 27.3 | Clear | Approved | Insolvent | Physical progress is at 27.3%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0468 | 765kV Transmission Line | Southern | 2550.99 | 365 | 60 | 18.5 | Clear | Approved | Insolvent | Physical progress is at 18.5%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0469 | 765kV Transmission Line | Western | 2656.8 | 301.4 | 57 | 13.9 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 13.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0470 | 400kV Substation | Eastern | 1240.79 | 47.3 | 47 | 28.3 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 28.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0471 | 400kV Substation | Northern | 1463.54 | 35.2 | 24 | 25.1 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 25.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0472 | 400kV Substation | Southern | 1151.81 | 34.4 | 26 | 28.6 | Pending Local | Approved | Equipment Delayed | Physical progress is at 28.6%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0473 | 765kV Transmission Line | Southern | 4247.3 | 433.3 | 38 | 26.2 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 26.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0474 | 220kV D/C Line | North-Eastern | 317.25 | 115.5 | 36 | 28.1 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 28.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0475 | 220kV D/C Line | North-Eastern | 181.09 | 112.2 | 13 | 32.2 | Disputed | Stage-II Awaited | On Track | Physical progress is at 32.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0476 | 765kV Transmission Line | North-Eastern | 4154.73 | 391.7 | 42 | 51.1 | Pending Local | Approved | On Track | Physical progress is at 51.1%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0477 | 400kV Substation | Northern | 627.19 | 24.2 | 27 | 23.6 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 23.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0478 | 400kV Substation | Western | 1431.93 | 82.4 | 42 | 64.5 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 64.5% with all statutory clearances in place. | 1 | Medium
GRID-0479 | 765kV Transmission Line | Northern | 3147.57 | 402.6 | 39 | 55.7 | Pending Local | Approved | On Track | Physical progress is at 55.7%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0480 | 220kV D/C Line | North-Eastern | 540.63 | 188 | 26 | 34.3 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 34.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0481 | 220kV D/C Line | Eastern | 168.08 | 112.1 | 32 | 31.5 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 31.5%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0482 | 765kV Transmission Line | Southern | 4260.73 | 464.7 | 50 | 44.5 | Pending Local | Approved | On Track | Physical progress is at 44.5%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0483 | 400kV Substation | Western | 638.71 | 41.4 | 42 | 52.7 | Clear | Stage-II Awaited | On Track | Physical progress is at 52.7%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0484 | 400kV Substation | North-Eastern | 1079.34 | 81.3 | 41 | 16.1 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 16.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0485 | 765kV Transmission Line | Southern | 2228.83 | 408.2 | 49 | 49.6 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 49.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0486 | 765kV Transmission Line | North-Eastern | 3586.26 | 297.6 | 39 | 63.9 | Pending Local | Approved | Equipment Delayed | Physical progress is at 63.9%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0487 | 400kV Substation | Eastern | 1073.99 | 15.5 | 30 | 13.7 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 13.7%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0488 | 220kV D/C Line | Southern | 372.99 | 165.6 | 18 | 56.7 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 56.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0489 | 765kV Transmission Line | North-Eastern | 1528.42 | 495.9 | 48 | 56 | Clear | Stage-I Awaited | On Track | Physical progress is at 56.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0490 | 765kV Transmission Line | North-Eastern | 4372.64 | 307.8 | 45 | 65 | Clear | Approved | Equipment Delayed | Physical progress is at 65.0%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0491 | 400kV Substation | Eastern | 822.23 | 29 | 29 | 55.4 | Pending Local | Approved | On Track | Physical progress is at 55.4%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0492 | 400kV Substation | Western | 646.17 | 88.5 | 28 | 65 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 65.0% with all statutory clearances in place. | 0 | Low
GRID-0493 | 765kV Transmission Line | Western | 3747.85 | 324.8 | 50 | 23.8 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 23.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0494 | 765kV Transmission Line | Western | 2986.7 | 202.2 | 51 | 33.2 | Disputed | Approved | Insolvent | Physical progress is at 33.2%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0495 | 765kV Transmission Line | North-Eastern | 3191.44 | 310.6 | 54 | 49.3 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 49.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0496 | 220kV D/C Line | Northern | 466.35 | 172 | 19 | 23.5 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 23.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0497 | 400kV Substation | North-Eastern | 1234.23 | 52.2 | 40 | 34 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 34.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0498 | 765kV Transmission Line | North-Eastern | 4122.99 | 418.1 | 54 | 14.2 | Pending Local | Approved | Insolvent | Physical progress is at 14.2%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0499 | 220kV D/C Line | North-Eastern | 119.11 | 147 | 16 | 44.6 | Disputed | Approved | Equipment Delayed | Physical progress is at 44.6%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0500 | 765kV Transmission Line | Northern | 3613.38 | 473 | 59 | 30.5 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 30.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0501 | 400kV Substation | Western | 1259.25 | 87.6 | 34 | 13.9 | Clear | Approved | Insolvent | Physical progress is at 13.9%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0502 | 400kV Substation | Eastern | 585.54 | 49.6 | 44 | 31 | Clear | Approved | Insolvent | Physical progress is at 31.0%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0503 | 220kV D/C Line | Southern | 628.84 | 73.2 | 17 | 19.5 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 19.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0504 | 765kV Transmission Line | North-Eastern | 4545.97 | 203.6 | 50 | 58.2 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 58.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0505 | 400kV Substation | Southern | 620.51 | 18.8 | 44 | 26.9 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 26.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0506 | 220kV D/C Line | Northern | 682.18 | 52.4 | 15 | 15.5 | Disputed | Approved | Insolvent | Physical progress is at 15.5%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0507 | 765kV Transmission Line | Northern | 1582.95 | 227.6 | 55 | 33.9 | Disputed | Approved | Insolvent | Physical progress is at 33.9%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0508 | 400kV Substation | North-Eastern | 1263.84 | 26.6 | 27 | 26.5 | Disputed | Approved | Equipment Delayed | Physical progress is at 26.5%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0509 | 400kV Substation | Eastern | 1130.67 | 70.1 | 48 | 51.1 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 51.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0510 | 400kV Substation | Northern | 609.89 | 83.2 | 29 | 27.1 | Pending Local | Approved | Equipment Delayed | Physical progress is at 27.1%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0511 | 765kV Transmission Line | North-Eastern | 4190.48 | 265.5 | 56 | 10.9 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 10.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0512 | 400kV Substation | Northern | 1375.81 | 23.4 | 44 | 16.7 | Clear | Approved | Insolvent | Physical progress is at 16.7%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0513 | 400kV Substation | North-Eastern | 304.44 | 73.7 | 48 | 23.5 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 23.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0514 | 765kV Transmission Line | North-Eastern | 3373.56 | 497.5 | 46 | 23.4 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 23.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0515 | 400kV Substation | Western | 511.94 | 13.5 | 36 | 45.2 | Disputed | Approved | Equipment Delayed | Physical progress is at 45.2%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0516 | 765kV Transmission Line | Eastern | 4073.63 | 242 | 42 | 19.7 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 19.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0517 | 400kV Substation | North-Eastern | 1457.94 | 83.1 | 24 | 51.5 | Clear | Stage-I Awaited | On Track | Physical progress is at 51.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0518 | 400kV Substation | Northern | 554.01 | 68.8 | 40 | 15.8 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 15.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0519 | 400kV Substation | Northern | 865.46 | 92.6 | 25 | 14.3 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 14.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0520 | 765kV Transmission Line | Eastern | 3639.29 | 450.6 | 38 | 42.5 | Clear | Approved | Equipment Delayed | Physical progress is at 42.5%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0521 | 400kV Substation | Southern | 1273.83 | 98.4 | 45 | 13.4 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 13.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0522 | 220kV D/C Line | Western | 334.85 | 74.1 | 16 | 14.1 | Pending Local | Approved | Insolvent | Physical progress is at 14.1%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0523 | 765kV Transmission Line | Northern | 4268.68 | 389.7 | 48 | 40.3 | Clear | Approved | Equipment Delayed | Physical progress is at 40.3%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0524 | 765kV Transmission Line | North-Eastern | 4604.2 | 324.9 | 60 | 65.6 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 65.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0525 | 400kV Substation | Western | 1425.71 | 64.9 | 25 | 33.8 | Disputed | Approved | Insolvent | Physical progress is at 33.8%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0526 | 400kV Substation | Northern | 969.25 | 27.3 | 40 | 50.8 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 50.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0527 | 400kV Substation | Northern | 532.46 | 81.7 | 45 | 33.1 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 33.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0528 | 400kV Substation | Southern | 551.51 | 32.6 | 43 | 42.1 | Pending Local | Approved | On Track | Physical progress is at 42.1%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0529 | 765kV Transmission Line | Western | 4249.22 | 345.5 | 39 | 24.8 | Clear | Approved | Insolvent | Physical progress is at 24.8%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0530 | 400kV Substation | Western | 1196.5 | 90.9 | 31 | 29.5 | Clear | Stage-I Awaited | On Track | Physical progress is at 29.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0531 | 765kV Transmission Line | Eastern | 4619.78 | 222.1 | 54 | 77.1 | Pending Local | Approved | Equipment Delayed | Physical progress is at 77.1%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0532 | 400kV Substation | Southern | 463.69 | 74.8 | 44 | 10.8 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 10.8%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0533 | 765kV Transmission Line | Northern | 4480.78 | 337.6 | 41 | 51.6 | Pending Local | Approved | Equipment Delayed | Physical progress is at 51.6%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0534 | 220kV D/C Line | North-Eastern | 698.5 | 67.3 | 28 | 21.6 | Pending Local | Approved | Insolvent | Physical progress is at 21.6%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0535 | 220kV D/C Line | Western | 273.48 | 136.8 | 19 | 34.5 | Disputed | Approved | Insolvent | Physical progress is at 34.5%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0536 | 220kV D/C Line | North-Eastern | 123.53 | 156.2 | 27 | 23.3 | Disputed | Approved | Equipment Delayed | Physical progress is at 23.3%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0537 | 765kV Transmission Line | Western | 2754.42 | 271.7 | 38 | 27.6 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 27.6%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0538 | 400kV Substation | Western | 1349.04 | 46.5 | 35 | 32.3 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 32.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-0539 | 400kV Substation | Southern | 1137.67 | 65.1 | 42 | 69.4 | Clear | Stage-II Awaited | On Track | Physical progress is at 69.4%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0540 | 220kV D/C Line | Southern | 721.58 | 72.2 | 23 | 27 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 27.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0541 | 765kV Transmission Line | North-Eastern | 3982.68 | 261.4 | 46 | 49.5 | Clear | Stage-II Awaited | On Track | Physical progress is at 49.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0542 | 220kV D/C Line | Western | 627.22 | 202.2 | 22 | 11.6 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 11.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0543 | 220kV D/C Line | North-Eastern | 680.69 | 144 | 29 | 14.7 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 14.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0544 | 400kV Substation | Western | 646.05 | 96.1 | 27 | 39.9 | Clear | Stage-I Awaited | On Track | Physical progress is at 39.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0545 | 220kV D/C Line | Northern | 305.22 | 243.9 | 29 | 28.4 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 28.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0546 | 765kV Transmission Line | Northern | 1577.13 | 440.6 | 52 | 22.2 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 22.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0547 | 220kV D/C Line | Western | 728.8 | 111.3 | 20 | 13.7 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 13.7%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0548 | 765kV Transmission Line | North-Eastern | 4734.46 | 413.5 | 45 | 32.6 | Clear | Approved | Insolvent | Physical progress is at 32.6%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0549 | 765kV Transmission Line | Western | 1909.21 | 498.1 | 54 | 15.1 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 15.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0550 | 400kV Substation | Western | 747.5 | 58.6 | 29 | 33.3 | Disputed | Stage-I Awaited | On Track | Physical progress is at 33.3%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0551 | 400kV Substation | Western | 305.15 | 76.5 | 40 | 34.2 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 34.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0552 | 220kV D/C Line | Eastern | 337.08 | 72.5 | 27 | 12.9 | Clear | Approved | Insolvent | Physical progress is at 12.9%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0553 | 400kV Substation | North-Eastern | 1309.05 | 50.1 | 26 | 24.6 | Pending Local | Approved | Insolvent | Physical progress is at 24.6%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0554 | 765kV Transmission Line | Northern | 1792.56 | 454.8 | 57 | 22.3 | Disputed | Approved | Insolvent | Physical progress is at 22.3%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0555 | 400kV Substation | Western | 1159.16 | 48.5 | 36 | 32.3 | Pending Local | Approved | Equipment Delayed | Physical progress is at 32.3%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0556 | 765kV Transmission Line | Eastern | 4095.35 | 324.7 | 50 | 32.4 | Pending Local | Approved | Insolvent | Physical progress is at 32.4%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0557 | 765kV Transmission Line | Western | 2561.31 | 496.5 | 52 | 10.2 | Pending Local | Approved | Insolvent | Physical progress is at 10.2%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0558 | 400kV Substation | Western | 966.98 | 73.9 | 48 | 51.6 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 51.6% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 1 | Medium
GRID-0559 | 400kV Substation | North-Eastern | 1187.83 | 30.2 | 24 | 26.3 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 26.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0560 | 765kV Transmission Line | Eastern | 4673.78 | 393.4 | 36 | 24.5 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 24.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0561 | 220kV D/C Line | Eastern | 781.98 | 213.7 | 23 | 24.5 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 24.5%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0562 | 220kV D/C Line | Western | 350.17 | 60.6 | 23 | 41.2 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 41.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0563 | 220kV D/C Line | Western | 635.28 | 169.8 | 17 | 12.4 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 12.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0564 | 765kV Transmission Line | North-Eastern | 2484.96 | 433.6 | 49 | 46.2 | Pending Local | Approved | On Track | Physical progress is at 46.2%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-0565 | 765kV Transmission Line | North-Eastern | 3647 | 449.4 | 52 | 32.9 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 32.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0566 | 400kV Substation | Southern | 673.89 | 42.6 | 38 | 28.6 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 28.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0567 | 220kV D/C Line | Western | 581.63 | 111.5 | 18 | 43.1 | Clear | Approved | Equipment Delayed | Physical progress is at 43.1%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0568 | 400kV Substation | Northern | 535.62 | 13 | 45 | 56.3 | Disputed | Stage-II Awaited | On Track | Physical progress is at 56.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0569 | 400kV Substation | Northern | 1205.46 | 80.4 | 43 | 66.8 | Clear | Stage-II Awaited | On Track | Physical progress is at 66.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0570 | 765kV Transmission Line | Western | 4460.52 | 482.6 | 54 | 25.3 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 25.3%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0571 | 220kV D/C Line | Northern | 470.19 | 193.2 | 21 | 77 | Clear | Stage-II Awaited | On Track | Physical progress is at 77.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0572 | 220kV D/C Line | Eastern | 356.52 | 167.9 | 26 | 59.3 | Disputed | Approved | On Track | Physical progress is at 59.3%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0573 | 765kV Transmission Line | North-Eastern | 2296.44 | 233.9 | 46 | 13.4 | Clear | Stage-I Awaited | On Track | Physical progress is at 13.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0574 | 220kV D/C Line | Southern | 489.99 | 58.1 | 22 | 44 | Pending Local | Approved | Equipment Delayed | Physical progress is at 44.0%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0575 | 765kV Transmission Line | North-Eastern | 2925.49 | 495.5 | 49 | 47.2 | Clear | Approved | Equipment Delayed | Physical progress is at 47.2%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0576 | 220kV D/C Line | Northern | 377.46 | 154.5 | 33 | 56 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 56.0% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 1 | Medium
GRID-0577 | 400kV Substation | Western | 706.36 | 63.5 | 36 | 51.1 | Clear | Approved | Equipment Delayed | Physical progress is at 51.1%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0578 | 220kV D/C Line | Eastern | 349.27 | 183.3 | 24 | 24.9 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 24.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0579 | 220kV D/C Line | Western | 120.81 | 197.6 | 14 | 44.2 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 44.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0580 | 400kV Substation | North-Eastern | 1047.88 | 78.4 | 45 | 22.3 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 22.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0581 | 765kV Transmission Line | Eastern | 4580.44 | 235.7 | 50 | 14.4 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 14.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0582 | 400kV Substation | Eastern | 461.39 | 74.4 | 39 | 23.8 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 23.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0583 | 400kV Substation | North-Eastern | 1325.22 | 55.6 | 36 | 18.8 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 18.8%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 29 | High
GRID-0584 | 765kV Transmission Line | North-Eastern | 1657.91 | 451.1 | 47 | 12.4 | Disputed | Stage-II Awaited | On Track | Physical progress is at 12.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0585 | 400kV Substation | Southern | 367.74 | 32 | 31 | 17.6 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 17.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0586 | 220kV D/C Line | Southern | 126.16 | 181.6 | 25 | 24.7 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 24.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0587 | 400kV Substation | North-Eastern | 417.27 | 54 | 46 | 14.2 | Disputed | Approved | Equipment Delayed | Physical progress is at 14.2%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0588 | 400kV Substation | Western | 896.34 | 86.3 | 26 | 31.9 | Disputed | Approved | Equipment Delayed | Physical progress is at 31.9%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0589 | 220kV D/C Line | Northern | 602.39 | 165.6 | 30 | 21.9 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 21.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0590 | 765kV Transmission Line | Southern | 3266.24 | 290 | 57 | 16.3 | Disputed | Stage-I Awaited | On Track | Physical progress is at 16.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0591 | 765kV Transmission Line | North-Eastern | 4519.48 | 373.1 | 42 | 23.1 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 23.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0592 | 765kV Transmission Line | Western | 4112.52 | 429.7 | 49 | 16.7 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 16.7%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0593 | 765kV Transmission Line | Southern | 3903.99 | 270.8 | 43 | 68.6 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 68.6% with all statutory clearances in place. | 0 | Low
GRID-0594 | 400kV Substation | Northern | 542.39 | 34.5 | 24 | 31.3 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 31.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0595 | 765kV Transmission Line | Southern | 3605.6 | 460.2 | 49 | 28.1 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 28.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0596 | 220kV D/C Line | North-Eastern | 753.05 | 154.4 | 30 | 29.3 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 29.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0597 | 220kV D/C Line | Western | 754.85 | 93.6 | 15 | 56.3 | Clear | Approved | Equipment Delayed | Physical progress is at 56.3%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0598 | 400kV Substation | North-Eastern | 749.65 | 95.4 | 34 | 19.1 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 19.1%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0599 | 220kV D/C Line | North-Eastern | 124.37 | 197.9 | 13 | 17.7 | Disputed | Stage-II Awaited | On Track | Physical progress is at 17.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0600 | 220kV D/C Line | Northern | 474.44 | 97.3 | 26 | 23.6 | Pending Local | Approved | Equipment Delayed | Physical progress is at 23.6%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0601 | 765kV Transmission Line | Western | 4705.62 | 389.4 | 60 | 30.6 | Disputed | Stage-I Awaited | On Track | Physical progress is at 30.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0602 | 220kV D/C Line | Eastern | 748.55 | 116.5 | 25 | 22.7 | Clear | Approved | Insolvent | Physical progress is at 22.7%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0603 | 400kV Substation | North-Eastern | 1175.08 | 59.3 | 34 | 45.7 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 45.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0604 | 220kV D/C Line | Western | 102.15 | 90 | 21 | 50 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 50.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0605 | 765kV Transmission Line | North-Eastern | 3900.14 | 437.8 | 46 | 27.2 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 27.2%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0606 | 765kV Transmission Line | Eastern | 2786.6 | 318 | 48 | 76.9 | Disputed | Approved | On Track | Physical progress is at 76.9%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0607 | 765kV Transmission Line | Eastern | 2193.93 | 410.4 | 41 | 16.5 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 16.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-0608 | 765kV Transmission Line | North-Eastern | 1910.73 | 415.6 | 49 | 27.6 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 27.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0609 | 400kV Substation | Western | 817.57 | 28.6 | 30 | 20.2 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 20.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0610 | 400kV Substation | Western | 1041.22 | 91.7 | 35 | 21.7 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 21.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0611 | 220kV D/C Line | Eastern | 595.92 | 197.2 | 20 | 22.1 | Clear | Approved | Insolvent | Physical progress is at 22.1%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0612 | 400kV Substation | Southern | 1496.09 | 94.5 | 43 | 40.2 | Disputed | Stage-II Awaited | On Track | Physical progress is at 40.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0613 | 400kV Substation | Southern | 458.69 | 90.3 | 25 | 57.2 | Disputed | Approved | Equipment Delayed | Physical progress is at 57.2%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0614 | 765kV Transmission Line | Southern | 3985.89 | 329.9 | 44 | 40 | Clear | Stage-I Awaited | On Track | Physical progress is at 40.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0615 | 220kV D/C Line | Southern | 748.37 | 106.6 | 20 | 17.9 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 17.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0616 | 765kV Transmission Line | Western | 2020.17 | 269 | 37 | 12.9 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 12.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0617 | 400kV Substation | Southern | 1486.58 | 60.5 | 38 | 18.7 | Pending Local | Approved | Insolvent | Physical progress is at 18.7%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0618 | 765kV Transmission Line | Western | 4124.78 | 446.8 | 54 | 36.7 | Disputed | Stage-II Awaited | On Track | Physical progress is at 36.7%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0619 | 400kV Substation | Northern | 1364.84 | 12.3 | 45 | 53.5 | Disputed | Approved | Equipment Delayed | Physical progress is at 53.5%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0620 | 765kV Transmission Line | Eastern | 4407.45 | 397.9 | 50 | 26.4 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 26.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-0621 | 765kV Transmission Line | Northern | 4305.45 | 284.9 | 37 | 20 | Disputed | Approved | Insolvent | Physical progress is at 20.0%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0622 | 400kV Substation | Northern | 324.61 | 28.7 | 36 | 22.3 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 22.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0623 | 220kV D/C Line | North-Eastern | 191.9 | 183.1 | 23 | 21.9 | Disputed | Approved | Equipment Delayed | Physical progress is at 21.9%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0624 | 400kV Substation | Southern | 1036.64 | 49.1 | 37 | 34.3 | Clear | Approved | Insolvent | Physical progress is at 34.3%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0625 | 220kV D/C Line | Western | 751.47 | 155.5 | 32 | 12 | Disputed | Approved | Equipment Delayed | Physical progress is at 12.0%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0626 | 765kV Transmission Line | Western | 3895.1 | 290.1 | 43 | 32.9 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 32.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0627 | 765kV Transmission Line | Eastern | 3812.99 | 370.5 | 44 | 12.8 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 12.8%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0628 | 400kV Substation | Northern | 399.95 | 88.9 | 33 | 25.6 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 25.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0629 | 765kV Transmission Line | Western | 1773.77 | 494.7 | 44 | 35.8 | Disputed | Approved | Equipment Delayed | Physical progress is at 35.8%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0630 | 220kV D/C Line | Eastern | 422.11 | 131 | 33 | 30.3 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 30.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0631 | 400kV Substation | Northern | 450.11 | 11.2 | 27 | 48.4 | Clear | Stage-II Awaited | On Track | Physical progress is at 48.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0632 | 765kV Transmission Line | Western | 3025.26 | 387.8 | 53 | 45.9 | Clear | Approved | Equipment Delayed | Physical progress is at 45.9%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0633 | 765kV Transmission Line | Northern | 2081.37 | 245.7 | 58 | 15 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 15.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0634 | 765kV Transmission Line | Northern | 3706.43 | 413.9 | 49 | 20 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 20.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0635 | 765kV Transmission Line | Northern | 3349.08 | 326.6 | 46 | 12.9 | Disputed | Approved | Equipment Delayed | Physical progress is at 12.9%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0636 | 220kV D/C Line | Eastern | 114.56 | 107.6 | 18 | 24.7 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 24.7%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0637 | 765kV Transmission Line | Southern | 4030.48 | 317.1 | 49 | 34.3 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 34.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0638 | 220kV D/C Line | Northern | 566.94 | 75.8 | 18 | 57.7 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 57.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0639 | 765kV Transmission Line | Western | 3448.91 | 499.8 | 47 | 31.5 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 31.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0640 | 400kV Substation | Northern | 1041.08 | 20.9 | 31 | 32.4 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 32.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0641 | 400kV Substation | Eastern | 1455.18 | 78 | 27 | 26.7 | Disputed | Stage-II Awaited | On Track | Physical progress is at 26.7%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0642 | 400kV Substation | Western | 1174.02 | 73.7 | 48 | 19.1 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 19.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0643 | 400kV Substation | Eastern | 1223.06 | 10.6 | 39 | 19.3 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 19.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0644 | 765kV Transmission Line | North-Eastern | 2976.03 | 268.5 | 49 | 33.6 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0645 | 220kV D/C Line | North-Eastern | 760.55 | 67 | 22 | 50.4 | Pending Local | Approved | Equipment Delayed | Physical progress is at 50.4%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0646 | 220kV D/C Line | Northern | 784.41 | 246 | 33 | 32.7 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 32.7%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0647 | 220kV D/C Line | Eastern | 412.33 | 91 | 29 | 29.5 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 29.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0648 | 765kV Transmission Line | Northern | 3381.02 | 317 | 59 | 12.3 | Disputed | Approved | Insolvent | Physical progress is at 12.3%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0649 | 220kV D/C Line | Western | 116.4 | 228.1 | 29 | 34.7 | Disputed | Stage-I Awaited | On Track | Physical progress is at 34.7%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0650 | 400kV Substation | Southern | 1052.39 | 41.9 | 25 | 38.1 | Disputed | Approved | Equipment Delayed | Physical progress is at 38.1%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0651 | 400kV Substation | Southern | 641.44 | 80.6 | 46 | 12.6 | Disputed | Stage-II Awaited | On Track | Physical progress is at 12.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0652 | 400kV Substation | Eastern | 417.59 | 74 | 37 | 75.5 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 75.5% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 1 | Medium
GRID-0653 | 400kV Substation | North-Eastern | 783.3 | 60.3 | 48 | 34.9 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 34.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0654 | 765kV Transmission Line | Western | 3270.25 | 345.4 | 50 | 15.3 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 15.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0655 | 220kV D/C Line | Western | 760.85 | 123.9 | 15 | 24.3 | Disputed | Stage-I Awaited | On Track | Physical progress is at 24.3%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0656 | 765kV Transmission Line | Southern | 2567.24 | 312.3 | 45 | 71.4 | Pending Local | Approved | On Track | Physical progress is at 71.4%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-0657 | 765kV Transmission Line | Southern | 4611.7 | 264.7 | 59 | 53.9 | Pending Local | Approved | On Track | Physical progress is at 53.9%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0658 | 400kV Substation | Eastern | 987.67 | 60.9 | 34 | 13.5 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 13.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 29 | High
GRID-0659 | 765kV Transmission Line | Southern | 1812.6 | 387.4 | 55 | 23.5 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 23.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0660 | 400kV Substation | Northern | 1339.14 | 73.6 | 42 | 58.2 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 58.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0661 | 400kV Substation | North-Eastern | 1376.24 | 20.8 | 41 | 49.8 | Clear | Approved | Equipment Delayed | Physical progress is at 49.8%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0662 | 765kV Transmission Line | North-Eastern | 3623.99 | 320.5 | 37 | 56.6 | Pending Local | Approved | Equipment Delayed | Physical progress is at 56.6%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0663 | 400kV Substation | Southern | 409.23 | 98.2 | 41 | 30.2 | Clear | Stage-I Awaited | On Track | Physical progress is at 30.2%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0664 | 765kV Transmission Line | Southern | 4832.58 | 403.6 | 37 | 17.5 | Disputed | Stage-I Awaited | On Track | Physical progress is at 17.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0665 | 765kV Transmission Line | Eastern | 4625.54 | 277.4 | 39 | 77.3 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 77.3% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 0 | Low
GRID-0666 | 400kV Substation | Eastern | 963.75 | 15.9 | 24 | 62.2 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 62.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0667 | 765kV Transmission Line | Western | 4170.42 | 395.5 | 40 | 51.3 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 51.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0668 | 765kV Transmission Line | North-Eastern | 4834.14 | 488.4 | 53 | 78.4 | Pending Local | Approved | On Track | Physical progress is at 78.4%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0669 | 400kV Substation | Western | 300.65 | 94 | 39 | 24.6 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 24.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0670 | 765kV Transmission Line | North-Eastern | 3470.79 | 290.2 | 48 | 55.1 | Disputed | Approved | On Track | Physical progress is at 55.1%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0671 | 220kV D/C Line | North-Eastern | 770.19 | 113.7 | 33 | 26.6 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 26.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0672 | 400kV Substation | North-Eastern | 694.15 | 92.3 | 28 | 32.5 | Disputed | Approved | Insolvent | Physical progress is at 32.5%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0673 | 220kV D/C Line | Eastern | 633.73 | 157.6 | 32 | 30.4 | Disputed | Approved | Insolvent | Physical progress is at 30.4%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0674 | 400kV Substation | Eastern | 1292.96 | 42.2 | 29 | 34.8 | Disputed | Approved | On Track | Physical progress is at 34.8%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0675 | 400kV Substation | Northern | 565.82 | 11.8 | 32 | 30.2 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 30.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0676 | 400kV Substation | Northern | 636.91 | 91.4 | 46 | 79.4 | Disputed | Approved | On Track | Physical progress is at 79.4%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0677 | 765kV Transmission Line | Southern | 3491.86 | 348.2 | 53 | 24.7 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 24.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0678 | 765kV Transmission Line | Southern | 4767.47 | 456.6 | 52 | 27 | Disputed | Stage-I Awaited | On Track | Physical progress is at 27.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0679 | 400kV Substation | Northern | 1324.63 | 39.1 | 37 | 22.4 | Pending Local | Approved | Insolvent | Physical progress is at 22.4%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0680 | 220kV D/C Line | Western | 132.88 | 233.7 | 29 | 18.4 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 18.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0681 | 765kV Transmission Line | Eastern | 4852.21 | 475.1 | 42 | 21.1 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 21.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0682 | 220kV D/C Line | Southern | 688.36 | 99.4 | 27 | 40.8 | Clear | Stage-I Awaited | On Track | Physical progress is at 40.8%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0683 | 765kV Transmission Line | North-Eastern | 3668.48 | 429.2 | 56 | 76.7 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 76.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0684 | 220kV D/C Line | Northern | 647.85 | 62.4 | 26 | 12.5 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 12.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0685 | 400kV Substation | Eastern | 782.02 | 65.6 | 37 | 19.6 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 19.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0686 | 400kV Substation | Northern | 844.89 | 39.5 | 30 | 80.8 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 80.8% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 0 | Low
GRID-0687 | 400kV Substation | Eastern | 877.68 | 65.9 | 29 | 64.5 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 64.5% with all statutory clearances in place. | 0 | Low
GRID-0688 | 220kV D/C Line | North-Eastern | 642.85 | 79.5 | 21 | 11.4 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 11.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0689 | 765kV Transmission Line | Western | 3741.94 | 260.4 | 38 | 27.3 | Pending Local | Approved | Insolvent | Physical progress is at 27.3%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0690 | 220kV D/C Line | North-Eastern | 774.15 | 173.2 | 25 | 75 | Pending Local | Approved | On Track | Physical progress is at 75.0%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0691 | 400kV Substation | Western | 1403.94 | 67.5 | 46 | 22 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 22.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0692 | 765kV Transmission Line | Eastern | 2144.86 | 497 | 47 | 62.2 | Clear | Approved | Equipment Delayed | Physical progress is at 62.2%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0693 | 400kV Substation | Eastern | 533.28 | 62.7 | 48 | 47.9 | Pending Local | Approved | On Track | Physical progress is at 47.9%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-0694 | 765kV Transmission Line | Southern | 4015.93 | 301.9 | 53 | 66.2 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 66.2% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 0 | Low
GRID-0695 | 400kV Substation | Northern | 706.06 | 28.9 | 38 | 32 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 32.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0696 | 765kV Transmission Line | Western | 4282.14 | 257.5 | 48 | 33 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.0%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0697 | 400kV Substation | Western | 363.91 | 81.6 | 28 | 29.8 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 29.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0698 | 220kV D/C Line | Eastern | 625.92 | 179 | 28 | 27.8 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 27.8%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-0699 | 400kV Substation | Southern | 997.42 | 67.4 | 42 | 75.8 | Disputed | Approved | On Track | Physical progress is at 75.8%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0700 | 765kV Transmission Line | Eastern | 2265.08 | 327.5 | 48 | 25.4 | Disputed | Approved | Equipment Delayed | Physical progress is at 25.4%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0701 | 400kV Substation | North-Eastern | 721.89 | 62.6 | 38 | 20.8 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 20.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0702 | 400kV Substation | Eastern | 329.66 | 49.8 | 32 | 53.7 | Disputed | Approved | Equipment Delayed | Physical progress is at 53.7%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0703 | 765kV Transmission Line | Northern | 1915.06 | 308.1 | 53 | 30 | Clear | Stage-I Awaited | On Track | Physical progress is at 30.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0704 | 765kV Transmission Line | North-Eastern | 4992.98 | 499.5 | 60 | 17.5 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 17.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-0705 | 220kV D/C Line | Northern | 430.4 | 152.5 | 36 | 48.9 | Clear | Stage-I Awaited | On Track | Physical progress is at 48.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0706 | 400kV Substation | Western | 918.99 | 80.7 | 48 | 53.8 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 53.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0707 | 765kV Transmission Line | Eastern | 3074.9 | 367.5 | 47 | 77.7 | Clear | Stage-II Awaited | On Track | Physical progress is at 77.7%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0708 | 400kV Substation | Southern | 707.79 | 47.7 | 45 | 10.6 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 10.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0709 | 400kV Substation | North-Eastern | 1055.81 | 64.3 | 43 | 23.4 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 23.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0710 | 400kV Substation | North-Eastern | 1454.33 | 67.5 | 33 | 61.1 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 61.1% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 0 | Low
GRID-0711 | 765kV Transmission Line | Eastern | 2493.36 | 269.9 | 57 | 40.7 | Disputed | Approved | Equipment Delayed | Physical progress is at 40.7%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0712 | 400kV Substation | Eastern | 488.44 | 20 | 41 | 15.2 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 15.2%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0713 | 220kV D/C Line | Eastern | 211.15 | 165 | 21 | 15 | Disputed | Approved | Insolvent | Physical progress is at 15.0%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0714 | 765kV Transmission Line | Eastern | 3616.97 | 274.1 | 46 | 17.2 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 17.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0715 | 400kV Substation | North-Eastern | 1288.12 | 86.5 | 37 | 20.8 | Clear | Approved | Insolvent | Physical progress is at 20.8%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0716 | 220kV D/C Line | Western | 588.97 | 69.1 | 34 | 75.3 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 75.3% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 1 | Medium
GRID-0717 | 400kV Substation | Eastern | 1490.87 | 59.8 | 35 | 29.5 | Clear | Approved | Insolvent | Physical progress is at 29.5%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0718 | 400kV Substation | Western | 603.32 | 55.5 | 38 | 26.9 | Clear | Approved | Insolvent | Physical progress is at 26.9%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0719 | 400kV Substation | Southern | 1195.15 | 87 | 36 | 68.4 | Clear | Approved | Equipment Delayed | Physical progress is at 68.4%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0720 | 400kV Substation | Eastern | 881.71 | 16.1 | 41 | 21.8 | Disputed | Approved | Insolvent | Physical progress is at 21.8%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0721 | 765kV Transmission Line | Northern | 3624.46 | 253.2 | 39 | 47.1 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 47.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0722 | 765kV Transmission Line | Western | 4000.44 | 467.8 | 53 | 25.9 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 25.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-0723 | 220kV D/C Line | Southern | 410.79 | 169.6 | 13 | 76.4 | Pending Local | Approved | On Track | Physical progress is at 76.4%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0724 | 765kV Transmission Line | Northern | 2975.89 | 496.8 | 46 | 34 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 34.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0725 | 220kV D/C Line | Western | 130.81 | 152.5 | 22 | 33.4 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 33.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0726 | 765kV Transmission Line | Western | 1870.6 | 297 | 36 | 38.4 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 38.4%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0727 | 220kV D/C Line | North-Eastern | 358.29 | 63.5 | 18 | 23.4 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 23.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0728 | 220kV D/C Line | Southern | 786.99 | 189.3 | 33 | 59.1 | Disputed | Approved | Equipment Delayed | Physical progress is at 59.1%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0729 | 400kV Substation | Northern | 1030.24 | 62.7 | 36 | 10.5 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 10.5%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0730 | 220kV D/C Line | Eastern | 630.07 | 174 | 13 | 13.8 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 13.8%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0731 | 765kV Transmission Line | North-Eastern | 4959.93 | 333.1 | 46 | 26.2 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 26.2%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0732 | 765kV Transmission Line | Southern | 2699.55 | 261.7 | 37 | 31.8 | Disputed | Approved | Insolvent | Physical progress is at 31.8%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0733 | 400kV Substation | Northern | 377.54 | 54.2 | 30 | 45 | Clear | Stage-II Awaited | On Track | Physical progress is at 45.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0734 | 220kV D/C Line | North-Eastern | 681.85 | 236.4 | 19 | 14.1 | Disputed | Approved | Equipment Delayed | Physical progress is at 14.1%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0735 | 400kV Substation | Western | 1027.02 | 37.3 | 42 | 23.2 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 23.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0736 | 400kV Substation | Western | 864.86 | 48 | 43 | 29 | Disputed | Stage-I Awaited | On Track | Physical progress is at 29.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0737 | 400kV Substation | North-Eastern | 944.64 | 59.8 | 29 | 19.4 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 19.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0738 | 765kV Transmission Line | Eastern | 2185.01 | 474.8 | 36 | 20.1 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 20.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0739 | 220kV D/C Line | Southern | 368.83 | 111.6 | 30 | 35.4 | Clear | Stage-I Awaited | On Track | Physical progress is at 35.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0740 | 765kV Transmission Line | Eastern | 4849.84 | 431.4 | 60 | 11.4 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 11.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 32 | High
GRID-0741 | 765kV Transmission Line | Eastern | 1620.78 | 443.9 | 56 | 44.2 | Disputed | Stage-II Awaited | On Track | Physical progress is at 44.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0742 | 400kV Substation | Western | 1022.58 | 95.7 | 29 | 55.9 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 55.9% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 1 | Medium
GRID-0743 | 765kV Transmission Line | Eastern | 2385.05 | 290.7 | 53 | 31.9 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 31.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 33 | High
GRID-0744 | 765kV Transmission Line | Southern | 4120.56 | 479 | 48 | 10 | Disputed | Stage-I Awaited | On Track | Physical progress is at 10.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0745 | 220kV D/C Line | Eastern | 558.16 | 196.6 | 17 | 27.9 | Clear | Stage-I Awaited | On Track | Physical progress is at 27.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0746 | 220kV D/C Line | Northern | 415.46 | 212.9 | 17 | 30.2 | Clear | Approved | Insolvent | Physical progress is at 30.2%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0747 | 400kV Substation | Eastern | 828.88 | 92.2 | 27 | 23.4 | Disputed | Approved | On Track | Physical progress is at 23.4%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0748 | 400kV Substation | Northern | 710.58 | 62.7 | 39 | 50.6 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 50.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0749 | 220kV D/C Line | Northern | 167.79 | 154.5 | 12 | 28.9 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 28.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0750 | 400kV Substation | Southern | 1499.33 | 83.5 | 35 | 31.8 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 31.8%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0751 | 220kV D/C Line | Eastern | 607.65 | 227.6 | 16 | 78 | Clear | Stage-II Awaited | On Track | Physical progress is at 78.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0752 | 400kV Substation | Eastern | 1042.02 | 69.3 | 39 | 33.9 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 33.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0753 | 765kV Transmission Line | Southern | 3872.75 | 270.1 | 51 | 33.5 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 33.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0754 | 220kV D/C Line | Eastern | 305.7 | 89 | 16 | 29.9 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 29.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0755 | 400kV Substation | Northern | 878.6 | 58.7 | 31 | 12.2 | Clear | Approved | Insolvent | Physical progress is at 12.2%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0756 | 220kV D/C Line | Northern | 212.16 | 235.8 | 24 | 21.9 | Pending Local | Approved | Insolvent | Physical progress is at 21.9%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0757 | 220kV D/C Line | Western | 745.92 | 176.7 | 27 | 45.8 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 45.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0758 | 220kV D/C Line | North-Eastern | 776.37 | 137.4 | 19 | 23.5 | Clear | Stage-I Awaited | On Track | Physical progress is at 23.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0759 | 400kV Substation | North-Eastern | 1424.65 | 77 | 27 | 24.4 | Disputed | Stage-I Awaited | On Track | Physical progress is at 24.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0760 | 765kV Transmission Line | North-Eastern | 3374.61 | 454.1 | 49 | 25 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 25.0%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0761 | 765kV Transmission Line | North-Eastern | 4483.27 | 294.8 | 45 | 25 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 25.0%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0762 | 220kV D/C Line | Southern | 316.22 | 248.1 | 15 | 15.4 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 15.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-0763 | 765kV Transmission Line | Southern | 2034.46 | 415 | 59 | 29.4 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 29.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0764 | 400kV Substation | Western | 1489.28 | 59.3 | 34 | 11.8 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 11.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0765 | 220kV D/C Line | Western | 590.78 | 159.6 | 15 | 33.4 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 33.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-0766 | 220kV D/C Line | Western | 504.01 | 138.4 | 27 | 72.2 | Pending Local | Approved | On Track | Physical progress is at 72.2%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-0767 | 220kV D/C Line | Northern | 353.56 | 221.2 | 15 | 57 | Disputed | Approved | Equipment Delayed | Physical progress is at 57.0%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0768 | 400kV Substation | Western | 1434.08 | 20.6 | 40 | 28.1 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 28.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 31 | High
GRID-0769 | 765kV Transmission Line | Eastern | 3210.19 | 406.4 | 41 | 16.9 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 16.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0770 | 765kV Transmission Line | Northern | 1908.2 | 236.6 | 56 | 30.9 | Disputed | Stage-II Awaited | On Track | Physical progress is at 30.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0771 | 220kV D/C Line | Western | 368.77 | 250 | 34 | 11.6 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 11.6%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0772 | 400kV Substation | North-Eastern | 1280.96 | 80.5 | 40 | 27.8 | Pending Local | Approved | Insolvent | Physical progress is at 27.8%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0773 | 765kV Transmission Line | Northern | 2132.32 | 379.7 | 41 | 21.6 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 21.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0774 | 220kV D/C Line | Western | 161.47 | 101.4 | 36 | 54.5 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 54.5% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 1 | Medium
GRID-0775 | 400kV Substation | Northern | 1435.46 | 56.7 | 33 | 23.1 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 23.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0776 | 220kV D/C Line | Northern | 265.97 | 87.6 | 21 | 15.4 | Clear | Approved | Insolvent | Physical progress is at 15.4%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0777 | 400kV Substation | Western | 1174.93 | 48 | 41 | 12.1 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 12.1%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0778 | 220kV D/C Line | Western | 475.13 | 64.1 | 35 | 24.1 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 24.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0779 | 400kV Substation | Western | 679.63 | 80.9 | 36 | 50.8 | Clear | Stage-II Awaited | On Track | Physical progress is at 50.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0780 | 765kV Transmission Line | North-Eastern | 2923.73 | 298.8 | 38 | 10.2 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 10.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0781 | 765kV Transmission Line | Northern | 2115.06 | 418.5 | 45 | 27.5 | Disputed | Stage-I Awaited | On Track | Physical progress is at 27.5%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0782 | 220kV D/C Line | Northern | 727.6 | 84.1 | 36 | 39.1 | Pending Local | Approved | Equipment Delayed | Physical progress is at 39.1%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0783 | 765kV Transmission Line | North-Eastern | 3996.28 | 397.3 | 40 | 26 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 26.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0784 | 220kV D/C Line | North-Eastern | 392.77 | 141.6 | 26 | 23 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 23.0%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-0785 | 400kV Substation | Eastern | 1224.69 | 86.1 | 44 | 33.6 | Clear | Approved | Insolvent | Physical progress is at 33.6%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0786 | 220kV D/C Line | Northern | 159.21 | 107.2 | 27 | 13.4 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 13.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0787 | 400kV Substation | Northern | 1039.54 | 92 | 47 | 59.8 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 59.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0788 | 220kV D/C Line | Eastern | 775.25 | 184.9 | 36 | 54.7 | Disputed | Approved | On Track | Physical progress is at 54.7%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0789 | 220kV D/C Line | Southern | 766.74 | 134.5 | 24 | 56.6 | Clear | Stage-I Awaited | On Track | Physical progress is at 56.6%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0790 | 220kV D/C Line | Northern | 303.05 | 146.6 | 20 | 24.2 | Clear | Approved | Insolvent | Physical progress is at 24.2%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0791 | 400kV Substation | North-Eastern | 1290.87 | 13.2 | 38 | 25.4 | Disputed | Stage-I Awaited | On Track | Physical progress is at 25.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0792 | 400kV Substation | Northern | 306.19 | 90.1 | 29 | 39.7 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 39.7%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0793 | 220kV D/C Line | Western | 387.5 | 232.6 | 12 | 35.8 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 35.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0794 | 400kV Substation | Western | 943.71 | 34.3 | 38 | 28.7 | Disputed | Stage-I Awaited | On Track | Physical progress is at 28.7%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0795 | 220kV D/C Line | Western | 177.47 | 107 | 16 | 26.7 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 26.7%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0796 | 765kV Transmission Line | Eastern | 3211.74 | 348.7 | 57 | 13.3 | Disputed | Approved | Equipment Delayed | Physical progress is at 13.3%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0797 | 765kV Transmission Line | Western | 2704.42 | 204.1 | 57 | 18.6 | Clear | Approved | Insolvent | Physical progress is at 18.6%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0798 | 400kV Substation | Eastern | 647.36 | 53.7 | 48 | 22.8 | Pending Local | Approved | Insolvent | Physical progress is at 22.8%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0799 | 765kV Transmission Line | Southern | 4979.9 | 274.2 | 49 | 28.3 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 28.3%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0800 | 220kV D/C Line | Western | 260.57 | 76.5 | 13 | 40.7 | Pending Local | Approved | On Track | Physical progress is at 40.7%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0801 | 765kV Transmission Line | Northern | 2831.23 | 357.5 | 58 | 37 | Disputed | Approved | On Track | Physical progress is at 37.0%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0802 | 220kV D/C Line | Eastern | 550.71 | 110.9 | 20 | 32.4 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 32.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0803 | 765kV Transmission Line | Southern | 2241.92 | 341.6 | 55 | 57.9 | Clear | Stage-I Awaited | On Track | Physical progress is at 57.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0804 | 400kV Substation | Southern | 433.83 | 70.2 | 45 | 49.7 | Disputed | Approved | Equipment Delayed | Physical progress is at 49.7%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0805 | 220kV D/C Line | Southern | 247.02 | 126.8 | 15 | 24.7 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 24.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0806 | 765kV Transmission Line | Eastern | 4739.25 | 222.5 | 53 | 11.1 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 11.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0807 | 220kV D/C Line | Southern | 726.44 | 139.7 | 34 | 20.5 | Clear | Stage-I Awaited | On Track | Physical progress is at 20.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0808 | 765kV Transmission Line | North-Eastern | 2459.52 | 490.2 | 45 | 69.6 | Clear | Stage-II Awaited | On Track | Physical progress is at 69.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0809 | 400kV Substation | North-Eastern | 1344.31 | 97.4 | 29 | 15.2 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 15.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0810 | 220kV D/C Line | Northern | 715.41 | 208.1 | 26 | 15.5 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 15.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-0811 | 765kV Transmission Line | Western | 1659.64 | 271.5 | 37 | 54.9 | Disputed | Approved | Equipment Delayed | Physical progress is at 54.9%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0812 | 765kV Transmission Line | North-Eastern | 1906.65 | 394.6 | 56 | 20.2 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 20.2%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0813 | 220kV D/C Line | Northern | 676.75 | 93.9 | 20 | 26.4 | Clear | Stage-I Awaited | On Track | Physical progress is at 26.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0814 | 220kV D/C Line | Eastern | 761.96 | 101.5 | 32 | 18.1 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 18.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0815 | 400kV Substation | Western | 1175.77 | 49.1 | 28 | 27.4 | Pending Local | Approved | Equipment Delayed | Physical progress is at 27.4%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0816 | 220kV D/C Line | Eastern | 760.35 | 86.1 | 21 | 52.7 | Clear | Stage-I Awaited | On Track | Physical progress is at 52.7%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0817 | 765kV Transmission Line | Western | 1752.17 | 273.6 | 56 | 28.2 | Pending Local | Approved | Insolvent | Physical progress is at 28.2%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0818 | 400kV Substation | Eastern | 324.86 | 84.4 | 48 | 70.8 | Disputed | Approved | On Track | Physical progress is at 70.8%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0819 | 765kV Transmission Line | North-Eastern | 1547.24 | 489.9 | 39 | 22 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 22.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0820 | 400kV Substation | Southern | 874.69 | 31.9 | 41 | 30.6 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 30.6%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0821 | 220kV D/C Line | Eastern | 199.28 | 232.4 | 12 | 26.4 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 26.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0822 | 220kV D/C Line | Northern | 444.27 | 248.2 | 19 | 13 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 13.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0823 | 220kV D/C Line | Western | 224.65 | 156.1 | 31 | 45 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 45.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0824 | 765kV Transmission Line | Southern | 4706.82 | 398.5 | 44 | 71.1 | Disputed | Approved | On Track | Physical progress is at 71.1%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0825 | 400kV Substation | Western | 768.72 | 74.9 | 39 | 34 | Clear | Approved | Insolvent | Physical progress is at 34.0%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0826 | 765kV Transmission Line | Northern | 2630.69 | 238.3 | 60 | 27.3 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 27.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0827 | 765kV Transmission Line | Western | 2841.15 | 364.8 | 53 | 12.1 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 12.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 30 | High
GRID-0828 | 765kV Transmission Line | Southern | 1510.03 | 498.2 | 36 | 56.5 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 56.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0829 | 400kV Substation | Western | 1302.3 | 59.6 | 37 | 86.1 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 86.1% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 0 | Low
GRID-0830 | 220kV D/C Line | Northern | 587.29 | 134.9 | 13 | 30.9 | Disputed | Approved | Insolvent | Physical progress is at 30.9%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0831 | 765kV Transmission Line | Southern | 1994.47 | 273.5 | 36 | 28.6 | Disputed | Stage-I Awaited | On Track | Physical progress is at 28.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0832 | 400kV Substation | Southern | 832.77 | 68 | 24 | 75.2 | Pending Local | Approved | On Track | Physical progress is at 75.2%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-0833 | 220kV D/C Line | Western | 452.31 | 52.2 | 25 | 15.7 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 15.7%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 31 | High
GRID-0834 | 220kV D/C Line | Eastern | 784.55 | 75 | 18 | 27.3 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 27.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0835 | 220kV D/C Line | Northern | 671.59 | 143.7 | 22 | 30.1 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 30.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0836 | 400kV Substation | Northern | 425.28 | 42.6 | 48 | 46.5 | Pending Local | Approved | On Track | Physical progress is at 46.5%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0837 | 765kV Transmission Line | Western | 3589.89 | 427 | 45 | 49.6 | Clear | Stage-II Awaited | On Track | Physical progress is at 49.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0838 | 220kV D/C Line | North-Eastern | 131.41 | 247.3 | 27 | 77.7 | Clear | Approved | Equipment Delayed | Physical progress is at 77.7%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0839 | 400kV Substation | Southern | 1450.49 | 55 | 34 | 33.3 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 33.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0840 | 220kV D/C Line | Western | 116.58 | 209.2 | 27 | 47.3 | Disputed | Approved | Equipment Delayed | Physical progress is at 47.3%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0841 | 220kV D/C Line | Western | 719.08 | 211.5 | 32 | 57.9 | Clear | Stage-II Awaited | On Track | Physical progress is at 57.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0842 | 400kV Substation | Southern | 732.38 | 87 | 37 | 15.2 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 15.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0843 | 765kV Transmission Line | North-Eastern | 3697.26 | 349.3 | 36 | 12.4 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 12.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0844 | 400kV Substation | Western | 381.79 | 61.9 | 35 | 50.3 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 50.3% with all statutory clearances in place. | 1 | Medium
GRID-0845 | 765kV Transmission Line | North-Eastern | 3208.91 | 309 | 45 | 22.8 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 22.8%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0846 | 220kV D/C Line | Eastern | 454.16 | 102.6 | 33 | 29.8 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 29.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0847 | 765kV Transmission Line | Northern | 2517.31 | 247.5 | 48 | 66.8 | Clear | Approved | Equipment Delayed | Physical progress is at 66.8%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0848 | 400kV Substation | Eastern | 1070.98 | 91 | 38 | 92.1 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 92.1% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 0 | Low
GRID-0849 | 400kV Substation | Northern | 680.74 | 99.7 | 39 | 17 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 17.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0850 | 400kV Substation | Western | 1068.26 | 38.8 | 25 | 34.5 | Disputed | Stage-I Awaited | On Track | Physical progress is at 34.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0851 | 765kV Transmission Line | Northern | 4834.26 | 405.1 | 44 | 42.8 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 42.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0852 | 400kV Substation | Eastern | 1345.55 | 57.2 | 45 | 75.8 | Pending Local | Approved | On Track | Physical progress is at 75.8%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-0853 | 400kV Substation | Southern | 497.44 | 41.4 | 37 | 18.9 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 18.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-0854 | 765kV Transmission Line | North-Eastern | 3657.79 | 297.1 | 59 | 32.4 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 32.4%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0855 | 765kV Transmission Line | Eastern | 2419.81 | 416.7 | 50 | 48.7 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 48.7%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0856 | 220kV D/C Line | North-Eastern | 642.07 | 170.2 | 18 | 63.1 | Pending Local | Approved | On Track | Physical progress is at 63.1%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0857 | 400kV Substation | Southern | 319.43 | 90.7 | 40 | 20.3 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 20.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0858 | 220kV D/C Line | Southern | 179.37 | 85.2 | 25 | 23.6 | Pending Local | Approved | Insolvent | Physical progress is at 23.6%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0859 | 220kV D/C Line | Eastern | 543.88 | 190.4 | 15 | 81.6 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 81.6% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 0 | Low
GRID-0860 | 220kV D/C Line | Eastern | 452.35 | 211.2 | 33 | 23.8 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 23.8%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0861 | 400kV Substation | Northern | 720.74 | 81.4 | 38 | 29.6 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 29.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0862 | 220kV D/C Line | Southern | 315.18 | 230.5 | 25 | 21.3 | Disputed | Approved | On Track | Physical progress is at 21.3%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0863 | 765kV Transmission Line | Southern | 4442.69 | 355.7 | 59 | 23.9 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 23.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0864 | 765kV Transmission Line | North-Eastern | 3001.86 | 481.8 | 48 | 37.5 | Disputed | Approved | Equipment Delayed | Physical progress is at 37.5%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0865 | 220kV D/C Line | Northern | 542.01 | 206.9 | 36 | 12.3 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 12.3%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0866 | 220kV D/C Line | North-Eastern | 207.13 | 173.6 | 29 | 59.3 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 59.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0867 | 765kV Transmission Line | Western | 3783.83 | 266.5 | 42 | 16.5 | Disputed | Approved | Insolvent | Physical progress is at 16.5%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0868 | 765kV Transmission Line | Western | 3696.03 | 391.5 | 54 | 44.3 | Clear | Approved | Equipment Delayed | Physical progress is at 44.3%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0869 | 400kV Substation | Western | 411.33 | 54.5 | 35 | 29.9 | Clear | Stage-I Awaited | On Track | Physical progress is at 29.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0870 | 765kV Transmission Line | Eastern | 4857.26 | 222.9 | 57 | 17.5 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 17.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0871 | 765kV Transmission Line | Southern | 4978.09 | 345.2 | 55 | 57.1 | Disputed | Stage-II Awaited | On Track | Physical progress is at 57.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0872 | 220kV D/C Line | Northern | 462.6 | 202.2 | 18 | 53.1 | Pending Local | Approved | On Track | Physical progress is at 53.1%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-0873 | 765kV Transmission Line | Western | 2436.57 | 344.5 | 38 | 30.2 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 30.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-0874 | 765kV Transmission Line | Southern | 2105.36 | 406.1 | 58 | 17.8 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 17.8%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0875 | 400kV Substation | Eastern | 1359.43 | 48.1 | 47 | 20.7 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 20.7%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-0876 | 400kV Substation | Western | 1367.34 | 96.2 | 32 | 10.7 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 10.7%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0877 | 765kV Transmission Line | Southern | 2358.61 | 264.6 | 47 | 52.7 | Pending Local | Approved | Equipment Delayed | Physical progress is at 52.7%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0878 | 765kV Transmission Line | Eastern | 3486.14 | 296.5 | 43 | 41.1 | Disputed | Approved | Equipment Delayed | Physical progress is at 41.1%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0879 | 220kV D/C Line | North-Eastern | 762.39 | 211.5 | 33 | 28.9 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 28.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0880 | 765kV Transmission Line | Western | 1673.81 | 348.2 | 37 | 26.8 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 26.8%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0881 | 400kV Substation | Western | 991.7 | 35.7 | 44 | 53.7 | Disputed | Approved | Equipment Delayed | Physical progress is at 53.7%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0882 | 220kV D/C Line | North-Eastern | 127.38 | 179 | 14 | 31 | Pending Local | Approved | Equipment Delayed | Physical progress is at 31.0%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0883 | 765kV Transmission Line | North-Eastern | 4211.15 | 348.1 | 37 | 26 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 26.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 29 | High
GRID-0884 | 765kV Transmission Line | Western | 1667.42 | 203.1 | 39 | 12.2 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 12.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0885 | 220kV D/C Line | Northern | 281.78 | 207 | 15 | 33.2 | Clear | Stage-I Awaited | On Track | Physical progress is at 33.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0886 | 400kV Substation | Western | 1409.83 | 62.5 | 27 | 32.2 | Clear | Stage-I Awaited | On Track | Physical progress is at 32.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0887 | 220kV D/C Line | Eastern | 567.76 | 154.4 | 19 | 29.3 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 29.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 29 | High
GRID-0888 | 400kV Substation | Southern | 1153.66 | 41.8 | 31 | 34.3 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 34.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0889 | 220kV D/C Line | Western | 427.71 | 127 | 27 | 29 | Clear | Stage-I Awaited | On Track | Physical progress is at 29.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0890 | 400kV Substation | Eastern | 1086.35 | 86.3 | 27 | 79 | Clear | Approved | Equipment Delayed | Physical progress is at 79.0%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0891 | 400kV Substation | Western | 382.37 | 48.1 | 45 | 31.9 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 31.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0892 | 765kV Transmission Line | Eastern | 2154.6 | 208.6 | 57 | 18.9 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 18.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0893 | 220kV D/C Line | Eastern | 455.55 | 60.6 | 20 | 55.3 | Pending Local | Approved | On Track | Physical progress is at 55.3%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0894 | 765kV Transmission Line | Southern | 2163.07 | 253 | 44 | 26.2 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 26.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0895 | 765kV Transmission Line | Northern | 3513.31 | 271.6 | 53 | 27.5 | Clear | Stage-I Awaited | On Track | Physical progress is at 27.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0896 | 400kV Substation | Eastern | 421.57 | 76.1 | 46 | 33.9 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 33.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0897 | 220kV D/C Line | Southern | 613.72 | 68.8 | 28 | 17.9 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 17.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0898 | 400kV Substation | Eastern | 470.2 | 11.1 | 39 | 32 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 32.0%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0899 | 765kV Transmission Line | North-Eastern | 2732.5 | 342.1 | 36 | 72.8 | Pending Local | Approved | Equipment Delayed | Physical progress is at 72.8%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0900 | 765kV Transmission Line | North-Eastern | 3261.01 | 426.5 | 60 | 58.1 | Clear | Approved | Equipment Delayed | Physical progress is at 58.1%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0901 | 220kV D/C Line | Southern | 564.39 | 100.7 | 26 | 12.8 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 12.8%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0902 | 400kV Substation | Western | 1091.24 | 22.7 | 39 | 27.4 | Clear | Approved | Insolvent | Physical progress is at 27.4%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0903 | 400kV Substation | Western | 1193.24 | 27.4 | 36 | 30.6 | Disputed | Approved | Equipment Delayed | Physical progress is at 30.6%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0904 | 400kV Substation | North-Eastern | 800.75 | 99.5 | 33 | 27.5 | Clear | Approved | Insolvent | Physical progress is at 27.5%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0905 | 400kV Substation | Eastern | 979.99 | 81.3 | 35 | 77.1 | Pending Local | Approved | On Track | Physical progress is at 77.1%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0906 | 400kV Substation | Western | 927.82 | 36.1 | 41 | 11.6 | Disputed | Approved | Equipment Delayed | Physical progress is at 11.6%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0907 | 400kV Substation | Northern | 560.79 | 84.3 | 27 | 18.8 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 18.8%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0908 | 400kV Substation | Western | 720.26 | 35.5 | 40 | 25.7 | Disputed | Stage-II Awaited | On Track | Physical progress is at 25.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0909 | 400kV Substation | North-Eastern | 1401.91 | 36.2 | 25 | 20 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 20.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-0910 | 400kV Substation | North-Eastern | 672.88 | 60.8 | 45 | 25.4 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 25.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0911 | 400kV Substation | Southern | 402.72 | 61 | 44 | 23.8 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 23.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0912 | 220kV D/C Line | Southern | 452.67 | 187 | 23 | 21.5 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 21.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0913 | 765kV Transmission Line | North-Eastern | 4673.97 | 436 | 54 | 11.3 | Disputed | Stage-I Awaited | On Track | Physical progress is at 11.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0914 | 400kV Substation | Northern | 855.37 | 78.7 | 40 | 50.8 | Pending Local | Approved | On Track | Physical progress is at 50.8%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-0915 | 765kV Transmission Line | Southern | 3580.19 | 446.6 | 54 | 48.1 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 48.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0916 | 765kV Transmission Line | Western | 4632.68 | 391.9 | 40 | 24.6 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 24.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0917 | 220kV D/C Line | Northern | 273.04 | 70.7 | 12 | 20.1 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 20.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0918 | 220kV D/C Line | Eastern | 701.52 | 173.4 | 25 | 45.7 | Clear | Stage-II Awaited | On Track | Physical progress is at 45.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0919 | 220kV D/C Line | Western | 219.54 | 198.3 | 29 | 26.7 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 26.7%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0920 | 220kV D/C Line | Southern | 373.83 | 189.5 | 15 | 21.4 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 21.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0921 | 765kV Transmission Line | North-Eastern | 3055.68 | 472.4 | 47 | 10.2 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 10.2%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0922 | 220kV D/C Line | North-Eastern | 247.55 | 230.5 | 28 | 26.1 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 26.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0923 | 220kV D/C Line | Southern | 421.64 | 221.7 | 16 | 19.4 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 19.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0924 | 220kV D/C Line | North-Eastern | 642.78 | 155.1 | 16 | 25.4 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 25.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 32 | High
GRID-0925 | 765kV Transmission Line | Western | 2310.97 | 399.6 | 51 | 32.5 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 32.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0926 | 765kV Transmission Line | Northern | 3641.66 | 234.3 | 59 | 33.1 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.1%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0927 | 220kV D/C Line | Eastern | 364.34 | 247.8 | 30 | 39.6 | Disputed | Approved | On Track | Physical progress is at 39.6%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0928 | 765kV Transmission Line | Western | 4097.54 | 330.2 | 52 | 45.2 | Clear | Approved | Insolvent | Physical progress is at 45.2%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0929 | 765kV Transmission Line | Northern | 4335.03 | 468 | 47 | 27.1 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 27.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0930 | 765kV Transmission Line | Western | 3496.3 | 342.1 | 47 | 20.7 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 20.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0931 | 765kV Transmission Line | North-Eastern | 2543.79 | 235.4 | 43 | 15.6 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 15.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-0932 | 400kV Substation | Southern | 381.54 | 88.4 | 33 | 22.9 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 22.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0933 | 400kV Substation | North-Eastern | 367.98 | 72.8 | 27 | 20.5 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 20.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0934 | 765kV Transmission Line | Western | 3414.81 | 420.2 | 60 | 22.9 | Disputed | Approved | On Track | Physical progress is at 22.9%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0935 | 400kV Substation | Northern | 1439.89 | 63.8 | 43 | 48.9 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 48.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0936 | 400kV Substation | North-Eastern | 570.29 | 41.5 | 39 | 41.1 | Pending Local | Approved | On Track | Physical progress is at 41.1%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-0937 | 220kV D/C Line | North-Eastern | 702.21 | 186.4 | 35 | 50.6 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 50.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0938 | 400kV Substation | Eastern | 959.45 | 20.4 | 27 | 33 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.0%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0939 | 220kV D/C Line | Northern | 258.99 | 199.5 | 29 | 72.5 | Disputed | Approved | On Track | Physical progress is at 72.5%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0940 | 765kV Transmission Line | Western | 3034.95 | 284.8 | 46 | 25.2 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 25.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0941 | 220kV D/C Line | Northern | 153.46 | 237.7 | 18 | 27.8 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 27.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0942 | 220kV D/C Line | Western | 468.79 | 103.5 | 34 | 56 | Disputed | Stage-II Awaited | On Track | Physical progress is at 56.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0943 | 400kV Substation | Northern | 544.27 | 22.3 | 40 | 13.1 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 13.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0944 | 765kV Transmission Line | Eastern | 3774.68 | 336.1 | 39 | 31.1 | Clear | Stage-I Awaited | On Track | Physical progress is at 31.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0945 | 400kV Substation | Northern | 371.66 | 86.9 | 36 | 21.8 | Pending Local | Approved | Equipment Delayed | Physical progress is at 21.8%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0946 | 765kV Transmission Line | Eastern | 3363.72 | 398.1 | 37 | 33.1 | Disputed | Stage-I Awaited | On Track | Physical progress is at 33.1%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0947 | 765kV Transmission Line | Southern | 4040.25 | 386.5 | 49 | 58.1 | Disputed | Stage-II Awaited | On Track | Physical progress is at 58.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0948 | 220kV D/C Line | Eastern | 396.68 | 193.8 | 36 | 28.6 | Disputed | Stage-I Awaited | On Track | Physical progress is at 28.6%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0949 | 765kV Transmission Line | Southern | 4298.56 | 485.3 | 38 | 21.5 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 21.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0950 | 400kV Substation | Southern | 1238.91 | 82.9 | 43 | 73.4 | Clear | Approved | Equipment Delayed | Physical progress is at 73.4%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0951 | 400kV Substation | Eastern | 320.72 | 10.8 | 25 | 11.5 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 11.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0952 | 765kV Transmission Line | Eastern | 2129.31 | 429.8 | 44 | 14.4 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 14.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0953 | 765kV Transmission Line | Northern | 2144.89 | 352 | 50 | 11.5 | Disputed | Stage-I Awaited | On Track | Physical progress is at 11.5%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-0954 | 765kV Transmission Line | Southern | 3391.54 | 213.4 | 43 | 57.8 | Pending Local | Approved | On Track | Physical progress is at 57.8%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-0955 | 765kV Transmission Line | Western | 2214.15 | 371.1 | 57 | 13.6 | Pending Local | Approved | Insolvent | Physical progress is at 13.6%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0956 | 400kV Substation | Eastern | 1376.87 | 43.7 | 33 | 21.8 | Disputed | Approved | On Track | Physical progress is at 21.8%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0957 | 220kV D/C Line | Northern | 174.36 | 92.3 | 22 | 30.8 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 30.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-0958 | 220kV D/C Line | Northern | 768.63 | 241.7 | 19 | 32 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 32.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0959 | 400kV Substation | Southern | 534.03 | 61.8 | 31 | 32.6 | Pending Local | Approved | Equipment Delayed | Physical progress is at 32.6%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-0960 | 400kV Substation | Eastern | 734.26 | 41.7 | 40 | 15.8 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 15.8%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-0961 | 220kV D/C Line | Western | 748 | 99 | 25 | 17.2 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 17.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-0962 | 400kV Substation | Eastern | 906.03 | 23.4 | 39 | 20.6 | Disputed | Approved | On Track | Physical progress is at 20.6%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0963 | 400kV Substation | Southern | 1218.61 | 74 | 39 | 73.4 | Disputed | Approved | On Track | Physical progress is at 73.4%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-0964 | 220kV D/C Line | Western | 792.95 | 76.5 | 28 | 27.8 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 27.8%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0965 | 220kV D/C Line | North-Eastern | 531.64 | 248.8 | 13 | 25.8 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 25.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0966 | 400kV Substation | Eastern | 1140.14 | 76 | 47 | 43.7 | Disputed | Stage-II Awaited | On Track | Physical progress is at 43.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0967 | 400kV Substation | Southern | 826.3 | 55.8 | 42 | 59.7 | Pending Local | Approved | On Track | Physical progress is at 59.7%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0968 | 220kV D/C Line | North-Eastern | 728.11 | 166 | 25 | 11 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 11.0%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0969 | 220kV D/C Line | North-Eastern | 320.06 | 119.5 | 17 | 15.6 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 15.6%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-0970 | 400kV Substation | North-Eastern | 1204.16 | 93.2 | 45 | 62.1 | Pending Local | Approved | On Track | Physical progress is at 62.1%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-0971 | 765kV Transmission Line | Northern | 3594.37 | 211.9 | 53 | 53.3 | Disputed | Approved | On Track | Physical progress is at 53.3%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0972 | 400kV Substation | Western | 638.21 | 95.3 | 37 | 32.9 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 32.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-0973 | 400kV Substation | Southern | 404.24 | 22.3 | 32 | 49.8 | Disputed | Stage-II Awaited | On Track | Physical progress is at 49.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-0974 | 400kV Substation | Western | 908.47 | 34.8 | 44 | 20.8 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 20.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0975 | 220kV D/C Line | Northern | 764.43 | 175.5 | 19 | 30.6 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 30.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0976 | 765kV Transmission Line | Eastern | 2489.1 | 259.6 | 38 | 11.7 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 11.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0977 | 765kV Transmission Line | Eastern | 3907.94 | 384 | 56 | 23.3 | Disputed | Approved | Insolvent | Physical progress is at 23.3%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0978 | 765kV Transmission Line | Southern | 3837.92 | 347.1 | 56 | 28.8 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 28.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-0979 | 400kV Substation | Western | 1094.9 | 20.4 | 38 | 35.9 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 35.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-0980 | 400kV Substation | North-Eastern | 794.4 | 31.1 | 33 | 42.5 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 42.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-0981 | 220kV D/C Line | Southern | 387.86 | 211.8 | 25 | 28.2 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 28.2%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-0982 | 765kV Transmission Line | Southern | 3066.73 | 266.4 | 41 | 25.3 | Disputed | Approved | Insolvent | Physical progress is at 25.3%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0983 | 220kV D/C Line | Northern | 661.69 | 68.1 | 34 | 23 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 23.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0984 | 765kV Transmission Line | North-Eastern | 2884.34 | 415.3 | 45 | 23.8 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 23.8%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0985 | 765kV Transmission Line | Northern | 4142.93 | 358 | 52 | 17.5 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 17.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0986 | 220kV D/C Line | Western | 123.64 | 200 | 24 | 11.9 | Disputed | Stage-I Awaited | On Track | Physical progress is at 11.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-0987 | 765kV Transmission Line | North-Eastern | 3617.05 | 245.6 | 59 | 29.6 | Disputed | Stage-I Awaited | On Track | Physical progress is at 29.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-0988 | 400kV Substation | Southern | 850.69 | 19 | 44 | 15.6 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 15.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-0989 | 400kV Substation | North-Eastern | 907.91 | 44.4 | 39 | 15.6 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 15.6%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-0990 | 400kV Substation | Southern | 872.17 | 19.8 | 33 | 24 | Pending Local | Approved | Insolvent | Physical progress is at 24.0%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-0991 | 220kV D/C Line | Western | 158.72 | 130.6 | 27 | 22.3 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 22.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-0992 | 765kV Transmission Line | Northern | 2625.05 | 369.6 | 49 | 24.1 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 24.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-0993 | 400kV Substation | Western | 686.21 | 73.8 | 40 | 27.5 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 27.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-0994 | 765kV Transmission Line | North-Eastern | 4118.52 | 249.9 | 50 | 46.8 | Clear | Approved | Equipment Delayed | Physical progress is at 46.8%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-0995 | 765kV Transmission Line | North-Eastern | 2963.52 | 202.8 | 39 | 25.4 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 25.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-0996 | 765kV Transmission Line | Southern | 3331.38 | 261.3 | 55 | 21.6 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 21.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 31 | High
GRID-0997 | 220kV D/C Line | Eastern | 106.87 | 133.3 | 16 | 68.1 | Pending Local | Approved | On Track | Physical progress is at 68.1%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-0998 | 220kV D/C Line | Northern | 476.41 | 116.2 | 13 | 25.9 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 25.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-0999 | 765kV Transmission Line | Southern | 2494.66 | 473.5 | 49 | 24 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 24.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1000 | 220kV D/C Line | Western | 172.08 | 93.3 | 17 | 43.5 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 43.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1001 | 220kV D/C Line | North-Eastern | 523.34 | 243.3 | 35 | 29.6 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 29.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1002 | 765kV Transmission Line | Western | 3164.12 | 200.1 | 38 | 21 | Clear | Approved | Insolvent | Physical progress is at 21.0%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1003 | 400kV Substation | Southern | 900.45 | 20.6 | 41 | 31 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 31.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1004 | 220kV D/C Line | Western | 768.75 | 239.1 | 20 | 27.4 | Disputed | Approved | Equipment Delayed | Physical progress is at 27.4%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1005 | 220kV D/C Line | Eastern | 556.46 | 85.6 | 23 | 35.3 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 35.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1006 | 765kV Transmission Line | Eastern | 2763.47 | 258.5 | 54 | 22.6 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 22.6%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1007 | 400kV Substation | Northern | 1076.66 | 67.8 | 36 | 25.6 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 25.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1008 | 220kV D/C Line | Eastern | 798.06 | 176.4 | 27 | 12.6 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 12.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-1009 | 220kV D/C Line | Western | 593.95 | 85.4 | 16 | 37.7 | Clear | Stage-I Awaited | On Track | Physical progress is at 37.7%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1010 | 400kV Substation | Northern | 1329.47 | 35 | 30 | 26.8 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 26.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1011 | 220kV D/C Line | Northern | 758.38 | 130.6 | 33 | 73 | Disputed | Approved | On Track | Physical progress is at 73.0%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1012 | 220kV D/C Line | Southern | 158.78 | 138.7 | 20 | 25.9 | Disputed | Approved | Insolvent | Physical progress is at 25.9%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1013 | 400kV Substation | North-Eastern | 720.82 | 40.7 | 42 | 12.9 | Disputed | Approved | Insolvent | Physical progress is at 12.9%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1014 | 220kV D/C Line | Northern | 229.96 | 168.2 | 12 | 58.4 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 58.4% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 1 | Medium
GRID-1015 | 400kV Substation | Northern | 755.17 | 35.8 | 32 | 53.4 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 53.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1016 | 765kV Transmission Line | Southern | 2407.74 | 331.9 | 38 | 26 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 26.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-1017 | 765kV Transmission Line | North-Eastern | 2849.88 | 361.4 | 42 | 27.5 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 27.5%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1018 | 400kV Substation | Western | 861.23 | 12.8 | 27 | 21.7 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 21.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1019 | 220kV D/C Line | North-Eastern | 730.89 | 114.5 | 15 | 21.9 | Disputed | Stage-I Awaited | On Track | Physical progress is at 21.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1020 | 765kV Transmission Line | Southern | 2571.96 | 340.1 | 41 | 24.4 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 24.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1021 | 400kV Substation | Western | 603.09 | 43.6 | 34 | 50.5 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 50.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1022 | 400kV Substation | Southern | 1444.78 | 46.1 | 24 | 75.5 | Clear | Stage-II Awaited | On Track | Physical progress is at 75.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1023 | 220kV D/C Line | Western | 766.05 | 163.6 | 16 | 52.4 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 52.4%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1024 | 400kV Substation | Eastern | 498.41 | 10.1 | 28 | 43.2 | Clear | Approved | Equipment Delayed | Physical progress is at 43.2%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1025 | 765kV Transmission Line | Eastern | 1815.58 | 273.4 | 57 | 18.6 | Disputed | Stage-I Awaited | On Track | Physical progress is at 18.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1026 | 220kV D/C Line | Western | 738.98 | 183.7 | 26 | 25.1 | Disputed | Approved | On Track | Physical progress is at 25.1%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1027 | 400kV Substation | Southern | 1377.63 | 83.8 | 47 | 46.8 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 46.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1028 | 220kV D/C Line | Western | 637.49 | 123.8 | 22 | 26.1 | Disputed | Approved | Insolvent | Physical progress is at 26.1%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1029 | 765kV Transmission Line | Northern | 2239.31 | 330.6 | 46 | 31.4 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 31.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1030 | 400kV Substation | Northern | 613.22 | 96 | 29 | 12.7 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 12.7%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-1031 | 220kV D/C Line | Northern | 559.11 | 130.9 | 12 | 22.7 | Clear | Stage-I Awaited | On Track | Physical progress is at 22.7%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1032 | 765kV Transmission Line | Eastern | 3788.36 | 401.1 | 49 | 25.1 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 25.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1033 | 400kV Substation | Southern | 1313 | 97.5 | 27 | 26.9 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 26.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-1034 | 400kV Substation | North-Eastern | 609.4 | 56.3 | 43 | 11 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 11.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1035 | 765kV Transmission Line | North-Eastern | 3902.36 | 275.7 | 46 | 14.5 | Disputed | Stage-I Awaited | On Track | Physical progress is at 14.5%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1036 | 765kV Transmission Line | Eastern | 2636.21 | 390.8 | 55 | 28.5 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 28.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1037 | 765kV Transmission Line | North-Eastern | 1831 | 418 | 56 | 33 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1038 | 400kV Substation | Southern | 345.94 | 64.8 | 47 | 57.1 | Disputed | Approved | Equipment Delayed | Physical progress is at 57.1%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1039 | 400kV Substation | Northern | 520.72 | 77.2 | 47 | 51.7 | Disputed | Stage-II Awaited | On Track | Physical progress is at 51.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1040 | 400kV Substation | North-Eastern | 916.85 | 86.9 | 31 | 50.4 | Disputed | Approved | Equipment Delayed | Physical progress is at 50.4%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1041 | 220kV D/C Line | Western | 293.8 | 184.3 | 31 | 10.1 | Pending Local | Approved | Insolvent | Physical progress is at 10.1%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1042 | 400kV Substation | Western | 629.72 | 51.6 | 44 | 40.7 | Pending Local | Approved | On Track | Physical progress is at 40.7%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-1043 | 765kV Transmission Line | Northern | 3639.85 | 418.4 | 55 | 21.9 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 21.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1044 | 400kV Substation | Southern | 715.64 | 50 | 38 | 26.8 | Disputed | Stage-I Awaited | On Track | Physical progress is at 26.8%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1045 | 765kV Transmission Line | North-Eastern | 4887.03 | 389.4 | 53 | 79.4 | Pending Local | Approved | On Track | Physical progress is at 79.4%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1046 | 400kV Substation | Southern | 1201.03 | 50.6 | 38 | 14.2 | Clear | Approved | Insolvent | Physical progress is at 14.2%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1047 | 220kV D/C Line | Eastern | 390.78 | 203 | 36 | 33 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 33.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1048 | 765kV Transmission Line | Eastern | 2264.07 | 497.6 | 54 | 79.2 | Pending Local | Approved | On Track | Physical progress is at 79.2%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1049 | 400kV Substation | Southern | 1201.54 | 47.6 | 43 | 22.6 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 22.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1050 | 400kV Substation | Eastern | 643.54 | 93.2 | 29 | 29.1 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 29.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1051 | 400kV Substation | North-Eastern | 1083.73 | 97.7 | 37 | 45.5 | Clear | Stage-II Awaited | On Track | Physical progress is at 45.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1052 | 220kV D/C Line | Northern | 519.7 | 196.4 | 12 | 45 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 45.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1053 | 400kV Substation | Northern | 1191.56 | 89.5 | 44 | 19.2 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 19.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1054 | 220kV D/C Line | Western | 325.91 | 108.6 | 12 | 47.3 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 47.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1055 | 765kV Transmission Line | Eastern | 3250.75 | 233.3 | 55 | 68.9 | Pending Local | Approved | On Track | Physical progress is at 68.9%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-1056 | 765kV Transmission Line | Northern | 3887.08 | 321.9 | 52 | 32.1 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 32.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1057 | 220kV D/C Line | North-Eastern | 600.33 | 137.7 | 35 | 20 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 20.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1058 | 765kV Transmission Line | Northern | 2010.94 | 278.7 | 54 | 56.5 | Clear | Stage-II Awaited | On Track | Physical progress is at 56.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1059 | 765kV Transmission Line | Western | 4284.44 | 263 | 39 | 22.3 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 22.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1060 | 400kV Substation | Eastern | 696.79 | 50.5 | 32 | 23 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 23.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1061 | 220kV D/C Line | Southern | 599.66 | 111.3 | 34 | 27.8 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 27.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1062 | 765kV Transmission Line | Western | 2012.84 | 287.7 | 48 | 63.3 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 63.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1063 | 765kV Transmission Line | Southern | 2774.57 | 352.6 | 52 | 13.9 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 13.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-1064 | 400kV Substation | Eastern | 1078.05 | 88.4 | 39 | 33.7 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.7%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1065 | 765kV Transmission Line | Western | 2474.1 | 433.4 | 39 | 24.2 | Disputed | Approved | Equipment Delayed | Physical progress is at 24.2%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1066 | 220kV D/C Line | Western | 354.49 | 56.6 | 32 | 23.8 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 23.8%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1067 | 400kV Substation | North-Eastern | 927.54 | 32 | 47 | 27.2 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 27.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1068 | 765kV Transmission Line | North-Eastern | 2430.17 | 283.2 | 59 | 60.9 | Clear | Stage-II Awaited | On Track | Physical progress is at 60.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1069 | 765kV Transmission Line | Western | 2353.79 | 428.5 | 51 | 29.8 | Pending Local | Approved | Insolvent | Physical progress is at 29.8%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1070 | 400kV Substation | Northern | 830.28 | 52.8 | 27 | 24.2 | Disputed | Stage-II Awaited | On Track | Physical progress is at 24.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1071 | 765kV Transmission Line | Eastern | 4220.89 | 258.4 | 56 | 25 | Disputed | Stage-I Awaited | On Track | Physical progress is at 25.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1072 | 400kV Substation | North-Eastern | 879.94 | 35.5 | 44 | 26.9 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 26.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1073 | 765kV Transmission Line | Western | 3206.53 | 295.8 | 52 | 50.4 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 50.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1074 | 400kV Substation | Southern | 1065.46 | 58.5 | 29 | 70.8 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 70.8% with all statutory clearances in place. | 0 | Low
GRID-1075 | 220kV D/C Line | Southern | 749.29 | 92.1 | 33 | 50.7 | Clear | Stage-I Awaited | On Track | Physical progress is at 50.7%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1076 | 765kV Transmission Line | North-Eastern | 3819.07 | 297.7 | 52 | 15.7 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 15.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1077 | 400kV Substation | Western | 667.48 | 75.4 | 47 | 29.1 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 29.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1078 | 400kV Substation | Southern | 1074.95 | 22.6 | 38 | 26.6 | Pending Local | Approved | Insolvent | Physical progress is at 26.6%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1079 | 400kV Substation | Northern | 686.21 | 81.2 | 34 | 22.6 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 22.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1080 | 765kV Transmission Line | Western | 2639.19 | 343.9 | 59 | 16.2 | Disputed | Stage-I Awaited | On Track | Physical progress is at 16.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1081 | 765kV Transmission Line | Northern | 3738.7 | 282.8 | 47 | 32 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 32.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1082 | 220kV D/C Line | Eastern | 677.02 | 224.8 | 30 | 49.8 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 49.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1083 | 220kV D/C Line | Southern | 489.67 | 213.5 | 34 | 78.3 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 78.3% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 1 | Medium
GRID-1084 | 400kV Substation | Eastern | 573.22 | 42.6 | 30 | 13 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 13.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1085 | 400kV Substation | Northern | 1298.01 | 15.4 | 40 | 34 | Pending Local | Approved | Insolvent | Physical progress is at 34.0%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1086 | 400kV Substation | North-Eastern | 700.5 | 16 | 26 | 14 | Disputed | Approved | Insolvent | Physical progress is at 14.0%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1087 | 220kV D/C Line | Western | 626.34 | 203.4 | 25 | 11.8 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 11.8%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1088 | 765kV Transmission Line | Eastern | 3511.58 | 201.9 | 48 | 57.1 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 57.1% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 1 | Medium
GRID-1089 | 220kV D/C Line | Western | 638.95 | 164.9 | 23 | 28.2 | Disputed | Stage-II Awaited | On Track | Physical progress is at 28.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1090 | 765kV Transmission Line | North-Eastern | 3606.73 | 453.4 | 60 | 54.8 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 54.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1091 | 765kV Transmission Line | Southern | 2071.51 | 497.3 | 43 | 55.1 | Clear | Stage-I Awaited | On Track | Physical progress is at 55.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1092 | 765kV Transmission Line | Eastern | 1588.98 | 460.3 | 59 | 21 | Clear | Stage-I Awaited | On Track | Physical progress is at 21.0%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1093 | 765kV Transmission Line | Eastern | 3565.76 | 237.4 | 41 | 15.2 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 15.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1094 | 400kV Substation | Western | 552.39 | 18.2 | 40 | 10.4 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 10.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1095 | 765kV Transmission Line | Southern | 2761.37 | 293 | 38 | 46 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 46.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1096 | 400kV Substation | Southern | 354.44 | 86.3 | 29 | 45.6 | Disputed | Approved | On Track | Physical progress is at 45.6%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1097 | 765kV Transmission Line | Northern | 3586.72 | 262.9 | 59 | 20.5 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 20.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1098 | 400kV Substation | Northern | 1243.87 | 12.7 | 30 | 18 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 18.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-1099 | 400kV Substation | Northern | 1181.94 | 23 | 37 | 24 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 24.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1100 | 765kV Transmission Line | Eastern | 4958.67 | 233.7 | 51 | 25.1 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 25.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-1101 | 400kV Substation | Southern | 453.84 | 69.1 | 35 | 28.7 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 28.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1102 | 765kV Transmission Line | North-Eastern | 1954.33 | 482.7 | 43 | 20.1 | Disputed | Approved | Insolvent | Physical progress is at 20.1%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1103 | 765kV Transmission Line | Southern | 2146.19 | 397.8 | 46 | 32.5 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 32.5%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 34 | High
GRID-1104 | 220kV D/C Line | Western | 505.56 | 236.9 | 13 | 10.4 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 10.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1105 | 400kV Substation | Southern | 314.06 | 53.3 | 35 | 34.8 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 34.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1106 | 220kV D/C Line | Eastern | 182.47 | 105.9 | 36 | 30.2 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 30.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1107 | 220kV D/C Line | Southern | 634.29 | 102.6 | 23 | 49.1 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 49.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1108 | 765kV Transmission Line | North-Eastern | 3994.43 | 237.9 | 47 | 19.9 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 19.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1109 | 765kV Transmission Line | Western | 4066.94 | 306.2 | 55 | 23.3 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 23.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1110 | 220kV D/C Line | North-Eastern | 216.73 | 81.7 | 33 | 33.3 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 33.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1111 | 220kV D/C Line | North-Eastern | 396.81 | 90.4 | 13 | 21.7 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 21.7%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1112 | 765kV Transmission Line | Northern | 2379.65 | 366.7 | 45 | 28.9 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 28.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1113 | 400kV Substation | Western | 1217.51 | 82.6 | 31 | 24.8 | Pending Local | Approved | Insolvent | Physical progress is at 24.8%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1114 | 765kV Transmission Line | Western | 4871.75 | 282.9 | 48 | 21.1 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 21.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1115 | 400kV Substation | Northern | 1064.11 | 56.9 | 40 | 26.5 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 26.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1116 | 220kV D/C Line | North-Eastern | 418.06 | 64.1 | 36 | 12.8 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 12.8%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1117 | 220kV D/C Line | Eastern | 630.92 | 94.9 | 15 | 31.7 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 31.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1118 | 220kV D/C Line | Eastern | 395.17 | 177.6 | 36 | 22.7 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 22.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1119 | 400kV Substation | Northern | 315.51 | 74.2 | 39 | 46.6 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 46.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1120 | 220kV D/C Line | North-Eastern | 686.19 | 125.2 | 28 | 24.8 | Disputed | Stage-I Awaited | On Track | Physical progress is at 24.8%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1121 | 765kV Transmission Line | Western | 2762.45 | 401.8 | 55 | 29.7 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 29.7%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1122 | 400kV Substation | Eastern | 1102.88 | 12.3 | 42 | 12.5 | Clear | Approved | Insolvent | Physical progress is at 12.5%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1123 | 765kV Transmission Line | Eastern | 4473.01 | 276.1 | 57 | 29.6 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 29.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1124 | 220kV D/C Line | Southern | 638.03 | 82.1 | 29 | 31.1 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 31.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1125 | 220kV D/C Line | North-Eastern | 617.9 | 217.2 | 19 | 20.2 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 20.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1126 | 765kV Transmission Line | Eastern | 2207.52 | 456.8 | 51 | 18.1 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 18.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1127 | 220kV D/C Line | North-Eastern | 307.34 | 162 | 17 | 12.3 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 12.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1128 | 400kV Substation | Western | 1159.07 | 58 | 36 | 44.5 | Clear | Stage-I Awaited | On Track | Physical progress is at 44.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1129 | 400kV Substation | Western | 831.04 | 13.7 | 41 | 29 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 29.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1130 | 765kV Transmission Line | Western | 3041.25 | 443.5 | 40 | 54.3 | Clear | Stage-I Awaited | On Track | Physical progress is at 54.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1131 | 400kV Substation | Eastern | 967.59 | 99.9 | 30 | 25.7 | Pending Local | Approved | Insolvent | Physical progress is at 25.7%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1132 | 220kV D/C Line | Southern | 662.4 | 102.7 | 23 | 23.1 | Pending Local | Approved | Equipment Delayed | Physical progress is at 23.1%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1133 | 400kV Substation | Western | 1254.67 | 62.1 | 27 | 28 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 28.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1134 | 400kV Substation | North-Eastern | 1303.94 | 51.4 | 38 | 42.4 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 42.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1135 | 400kV Substation | Eastern | 1341.09 | 23.3 | 45 | 16.3 | Pending Local | Approved | Insolvent | Physical progress is at 16.3%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1136 | 220kV D/C Line | North-Eastern | 443.57 | 190.8 | 16 | 23.5 | Pending Local | Approved | Insolvent | Physical progress is at 23.5%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1137 | 400kV Substation | Western | 983.83 | 88.8 | 37 | 10.2 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 10.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1138 | 220kV D/C Line | Southern | 511.21 | 204.9 | 14 | 14 | Disputed | Approved | Insolvent | Physical progress is at 14.0%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1139 | 220kV D/C Line | Western | 685.02 | 55.9 | 27 | 57.8 | Disputed | Approved | Equipment Delayed | Physical progress is at 57.8%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1140 | 400kV Substation | Eastern | 466.21 | 40.9 | 27 | 22.5 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 22.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1141 | 400kV Substation | Western | 571.97 | 98.7 | 44 | 10.5 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 10.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1142 | 220kV D/C Line | Southern | 166.84 | 50.3 | 28 | 52.3 | Clear | Approved | Equipment Delayed | Physical progress is at 52.3%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1143 | 765kV Transmission Line | Western | 2159.69 | 386.3 | 41 | 44 | Disputed | Approved | Equipment Delayed | Physical progress is at 44.0%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1144 | 220kV D/C Line | Western | 455.13 | 212.9 | 26 | 72.3 | Clear | Stage-II Awaited | On Track | Physical progress is at 72.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1145 | 400kV Substation | Northern | 718.86 | 26.2 | 40 | 64.1 | Clear | Approved | Equipment Delayed | Physical progress is at 64.1%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1146 | 400kV Substation | North-Eastern | 1298.12 | 80.6 | 27 | 34.6 | Disputed | Stage-II Awaited | On Track | Physical progress is at 34.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1147 | 765kV Transmission Line | Eastern | 1645.57 | 217.6 | 51 | 26.4 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 26.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1148 | 400kV Substation | Southern | 462.57 | 78.7 | 33 | 22.3 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 22.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1149 | 220kV D/C Line | Eastern | 526.76 | 111.2 | 36 | 11 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 11.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1150 | 220kV D/C Line | Southern | 617.48 | 156.9 | 13 | 11.3 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 11.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1151 | 220kV D/C Line | North-Eastern | 694.45 | 151.7 | 33 | 58.3 | Disputed | Approved | On Track | Physical progress is at 58.3%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1152 | 765kV Transmission Line | Southern | 1755.37 | 261.1 | 42 | 15.2 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 15.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1153 | 765kV Transmission Line | Western | 3808.58 | 474.6 | 46 | 56.7 | Clear | Stage-I Awaited | On Track | Physical progress is at 56.7%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1154 | 765kV Transmission Line | Western | 1995.84 | 273.9 | 57 | 32.6 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 32.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 31 | High
GRID-1155 | 400kV Substation | Northern | 799.06 | 47.2 | 32 | 25.7 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 25.7%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1156 | 220kV D/C Line | Eastern | 190.22 | 187.9 | 14 | 76.1 | Disputed | Approved | On Track | Physical progress is at 76.1%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1157 | 765kV Transmission Line | Western | 3379.29 | 250.2 | 59 | 17.2 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 17.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1158 | 765kV Transmission Line | Eastern | 4380.07 | 465.2 | 38 | 21.7 | Disputed | Stage-I Awaited | On Track | Physical progress is at 21.7%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1159 | 765kV Transmission Line | Northern | 4415.83 | 255.3 | 60 | 44.6 | Disputed | Approved | On Track | Physical progress is at 44.6%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1160 | 220kV D/C Line | Western | 409.42 | 203.8 | 33 | 21.8 | Disputed | Approved | On Track | Physical progress is at 21.8%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1161 | 765kV Transmission Line | Southern | 4508.21 | 275.2 | 41 | 35.2 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 35.2%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1162 | 765kV Transmission Line | Western | 2143.87 | 258.3 | 57 | 31.1 | Disputed | Stage-I Awaited | On Track | Physical progress is at 31.1%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1163 | 765kV Transmission Line | North-Eastern | 4874.62 | 217 | 57 | 25.5 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 25.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1164 | 400kV Substation | Northern | 472.18 | 19.3 | 31 | 11.5 | Clear | Stage-I Awaited | On Track | Physical progress is at 11.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1165 | 220kV D/C Line | Northern | 699.9 | 202.4 | 13 | 57.5 | Disputed | Stage-II Awaited | On Track | Physical progress is at 57.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1166 | 400kV Substation | North-Eastern | 764.12 | 91.9 | 31 | 21.4 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 21.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 31 | High
GRID-1167 | 765kV Transmission Line | Western | 2504.02 | 419.3 | 48 | 57.3 | Pending Local | Approved | Equipment Delayed | Physical progress is at 57.3%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1168 | 765kV Transmission Line | Eastern | 2936.3 | 463.9 | 43 | 33.5 | Pending Local | Approved | Insolvent | Physical progress is at 33.5%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1169 | 400kV Substation | Eastern | 832.67 | 45 | 35 | 23.2 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 23.2%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-1170 | 220kV D/C Line | Western | 763.6 | 195.9 | 31 | 17.7 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 17.7%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-1171 | 765kV Transmission Line | North-Eastern | 3782.83 | 290.1 | 60 | 18.4 | Disputed | Stage-I Awaited | On Track | Physical progress is at 18.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1172 | 220kV D/C Line | Eastern | 226.22 | 138.6 | 34 | 34.6 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 34.6%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1173 | 220kV D/C Line | Western | 205.48 | 113.3 | 19 | 47 | Disputed | Approved | Equipment Delayed | Physical progress is at 47.0%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1174 | 765kV Transmission Line | Northern | 4720.6 | 460.8 | 46 | 33.9 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1175 | 400kV Substation | North-Eastern | 1391.09 | 62.5 | 38 | 12.5 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 12.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1176 | 400kV Substation | Northern | 938.77 | 65.6 | 29 | 31.2 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 31.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-1177 | 400kV Substation | Northern | 1206.81 | 22.2 | 36 | 33.3 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.3%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1178 | 400kV Substation | North-Eastern | 712.59 | 40.6 | 26 | 65 | Pending Local | Approved | On Track | Physical progress is at 65.0%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-1179 | 400kV Substation | Western | 433.17 | 94.2 | 45 | 34.2 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 34.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1180 | 220kV D/C Line | North-Eastern | 392.42 | 83.8 | 20 | 32.7 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 32.7%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1181 | 220kV D/C Line | Western | 590.36 | 102.6 | 25 | 46.4 | Pending Local | Approved | Equipment Delayed | Physical progress is at 46.4%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1182 | 765kV Transmission Line | North-Eastern | 1537.37 | 372.1 | 45 | 21.4 | Pending Local | Approved | Equipment Delayed | Physical progress is at 21.4%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1183 | 220kV D/C Line | Eastern | 334.94 | 210.6 | 25 | 42.1 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 42.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1184 | 765kV Transmission Line | Eastern | 4715.72 | 225.4 | 57 | 72.2 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 72.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1185 | 765kV Transmission Line | Western | 2806.86 | 246.2 | 43 | 85.8 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 85.8% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 0 | Low
GRID-1186 | 220kV D/C Line | Eastern | 541.7 | 116.2 | 33 | 68.2 | Clear | Stage-II Awaited | On Track | Physical progress is at 68.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1187 | 220kV D/C Line | Northern | 229.9 | 193.7 | 14 | 11.2 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 11.2%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1188 | 400kV Substation | North-Eastern | 531.17 | 83.6 | 46 | 28.3 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 28.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1189 | 765kV Transmission Line | North-Eastern | 1522.1 | 252.8 | 42 | 27.5 | Pending Local | Approved | Insolvent | Physical progress is at 27.5%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1190 | 765kV Transmission Line | Western | 4470.16 | 426.9 | 43 | 25 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 25.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1191 | 400kV Substation | Southern | 1289.36 | 76.2 | 40 | 28.9 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 28.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1192 | 765kV Transmission Line | Eastern | 2704.78 | 419.9 | 55 | 10.3 | Pending Local | Approved | Insolvent | Physical progress is at 10.3%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1193 | 400kV Substation | North-Eastern | 1225.66 | 92.3 | 46 | 31 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 31.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1194 | 400kV Substation | Eastern | 660.3 | 54 | 41 | 41.7 | Disputed | Approved | On Track | Physical progress is at 41.7%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1195 | 400kV Substation | Eastern | 1355.97 | 39.2 | 36 | 20.5 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 20.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1196 | 400kV Substation | Western | 779.3 | 11.3 | 45 | 15.4 | Clear | Approved | Insolvent | Physical progress is at 15.4%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1197 | 400kV Substation | Eastern | 479.88 | 40.4 | 24 | 16.9 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 16.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1198 | 220kV D/C Line | Eastern | 403 | 239.5 | 17 | 22.7 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 22.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1199 | 400kV Substation | North-Eastern | 647.19 | 31.2 | 39 | 25.8 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 25.8%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1200 | 220kV D/C Line | North-Eastern | 400.3 | 74.4 | 16 | 24.1 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 24.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1201 | 400kV Substation | Southern | 800.4 | 28.9 | 34 | 23.9 | Disputed | Approved | Equipment Delayed | Physical progress is at 23.9%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1202 | 765kV Transmission Line | Southern | 4235.58 | 371.7 | 43 | 24.1 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 24.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1203 | 400kV Substation | Western | 1048.33 | 17.3 | 39 | 19.7 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 19.7%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1204 | 400kV Substation | Northern | 868.5 | 30.1 | 24 | 29.6 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 29.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1205 | 220kV D/C Line | North-Eastern | 240.04 | 212.1 | 18 | 49.4 | Disputed | Stage-II Awaited | On Track | Physical progress is at 49.4%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1206 | 765kV Transmission Line | Eastern | 2980.47 | 445.6 | 36 | 10.6 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 10.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1207 | 400kV Substation | Eastern | 1230.96 | 99.4 | 38 | 17.9 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 17.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 32 | High
GRID-1208 | 765kV Transmission Line | North-Eastern | 3086.67 | 248.9 | 40 | 74.7 | Pending Local | Approved | On Track | Physical progress is at 74.7%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-1209 | 400kV Substation | Southern | 470.1 | 84.9 | 36 | 18.1 | Disputed | Approved | Insolvent | Physical progress is at 18.1%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1210 | 220kV D/C Line | Northern | 550.53 | 114.8 | 36 | 27.9 | Disputed | Approved | Insolvent | Physical progress is at 27.9%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1211 | 765kV Transmission Line | Northern | 1989.69 | 230.7 | 41 | 58.9 | Disputed | Approved | On Track | Physical progress is at 58.9%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1212 | 765kV Transmission Line | Eastern | 2702.51 | 220.9 | 48 | 29.7 | Disputed | Approved | Insolvent | Physical progress is at 29.7%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1213 | 765kV Transmission Line | Eastern | 2056.71 | 428.8 | 44 | 61.8 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 61.8% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 0 | Low
GRID-1214 | 765kV Transmission Line | Western | 4824.88 | 486.3 | 40 | 22.8 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 22.8%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1215 | 220kV D/C Line | Eastern | 485.02 | 58 | 30 | 40.3 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 40.3% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 1 | Medium
GRID-1216 | 400kV Substation | Western | 482.71 | 10.7 | 44 | 14 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 14.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1217 | 765kV Transmission Line | Southern | 4642.75 | 317.8 | 56 | 34.2 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 34.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1218 | 765kV Transmission Line | Northern | 1645.81 | 441.4 | 59 | 28.7 | Clear | Approved | Insolvent | Physical progress is at 28.7%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1219 | 220kV D/C Line | Southern | 352.66 | 60.9 | 32 | 32.4 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 32.4%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1220 | 400kV Substation | Western | 899.51 | 74.8 | 47 | 22 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 22.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1221 | 765kV Transmission Line | North-Eastern | 1875.42 | 200.1 | 36 | 57.2 | Disputed | Approved | On Track | Physical progress is at 57.2%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1222 | 400kV Substation | Eastern | 1174.5 | 96.5 | 27 | 58.8 | Clear | Stage-I Awaited | On Track | Physical progress is at 58.8%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1223 | 765kV Transmission Line | Southern | 2961.2 | 206.7 | 60 | 50.5 | Clear | Approved | Equipment Delayed | Physical progress is at 50.5%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1224 | 765kV Transmission Line | Northern | 4581.02 | 479.6 | 41 | 75.9 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 75.9% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 0 | Low
GRID-1225 | 765kV Transmission Line | Western | 2254.16 | 319.3 | 48 | 73.2 | Clear | Approved | Equipment Delayed | Physical progress is at 73.2%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1226 | 765kV Transmission Line | Northern | 3518.66 | 213.2 | 38 | 10.6 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 10.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1227 | 220kV D/C Line | Eastern | 667.25 | 249.2 | 13 | 31.2 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 31.2%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 31 | High
GRID-1228 | 765kV Transmission Line | North-Eastern | 2785.54 | 446.2 | 53 | 23.8 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 23.8%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1229 | 220kV D/C Line | Southern | 384.9 | 166 | 23 | 26.9 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 26.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1230 | 765kV Transmission Line | North-Eastern | 2386.2 | 241.3 | 47 | 18.6 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 18.6%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1231 | 220kV D/C Line | Western | 784.06 | 208.5 | 34 | 60.8 | Pending Local | Approved | Equipment Delayed | Physical progress is at 60.8%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1232 | 400kV Substation | North-Eastern | 1097.56 | 24.8 | 31 | 28.3 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 28.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1233 | 765kV Transmission Line | North-Eastern | 2728.97 | 322.4 | 60 | 21.3 | Clear | Approved | Insolvent | Physical progress is at 21.3%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1234 | 220kV D/C Line | Northern | 725.23 | 243.9 | 15 | 78 | Pending Local | Approved | On Track | Physical progress is at 78.0%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1235 | 400kV Substation | Southern | 1290.28 | 58.8 | 27 | 70.4 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 70.4% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 0 | Low
GRID-1236 | 400kV Substation | Eastern | 1441.22 | 48 | 35 | 18.6 | Disputed | Stage-I Awaited | On Track | Physical progress is at 18.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1237 | 400kV Substation | Eastern | 1043.11 | 92.8 | 44 | 40 | Disputed | Stage-II Awaited | On Track | Physical progress is at 40.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1238 | 400kV Substation | Eastern | 1333.41 | 44.5 | 41 | 32 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 32.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-1239 | 400kV Substation | Northern | 1455.32 | 78.3 | 26 | 28.1 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 28.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1240 | 220kV D/C Line | Southern | 268.97 | 246.8 | 13 | 20.3 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 20.3%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-1241 | 220kV D/C Line | Northern | 754.88 | 138.9 | 28 | 30 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 30.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1242 | 220kV D/C Line | Northern | 588.75 | 148.2 | 26 | 64 | Pending Local | Approved | On Track | Physical progress is at 64.0%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-1243 | 765kV Transmission Line | Western | 4889.98 | 223 | 51 | 71 | Pending Local | Approved | On Track | Physical progress is at 71.0%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-1244 | 765kV Transmission Line | Eastern | 1653.56 | 254.8 | 46 | 12.5 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 12.5%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1245 | 400kV Substation | Eastern | 740.01 | 72.9 | 24 | 21.8 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 21.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1246 | 765kV Transmission Line | Northern | 1805.35 | 463.3 | 57 | 13 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 13.0%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1247 | 220kV D/C Line | Western | 412.27 | 249.3 | 23 | 12.9 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 12.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1248 | 765kV Transmission Line | Southern | 1966.25 | 410.4 | 36 | 23.1 | Pending Local | Approved | Insolvent | Physical progress is at 23.1%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1249 | 400kV Substation | Western | 683.44 | 31.9 | 39 | 22 | Clear | Approved | Insolvent | Physical progress is at 22.0%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1250 | 765kV Transmission Line | Western | 2857.5 | 390 | 53 | 31.4 | Clear | Approved | Insolvent | Physical progress is at 31.4%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1251 | 765kV Transmission Line | Eastern | 3296.85 | 496.2 | 54 | 20.3 | Clear | Approved | Insolvent | Physical progress is at 20.3%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1252 | 765kV Transmission Line | Southern | 2922.37 | 425.7 | 37 | 28.2 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 28.2%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1253 | 400kV Substation | North-Eastern | 1303.65 | 30.2 | 28 | 28.9 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 28.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1254 | 400kV Substation | Northern | 819.29 | 12.8 | 26 | 26 | Disputed | Approved | Insolvent | Physical progress is at 26.0%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1255 | 400kV Substation | Southern | 857.41 | 82.6 | 34 | 33.7 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 33.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1256 | 220kV D/C Line | North-Eastern | 586.67 | 234.7 | 31 | 12.3 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 12.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1257 | 400kV Substation | Southern | 1420.99 | 88.7 | 43 | 42.6 | Disputed | Approved | Equipment Delayed | Physical progress is at 42.6%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1258 | 765kV Transmission Line | Southern | 3311.85 | 323.5 | 44 | 29.2 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 29.2%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 30 | High
GRID-1259 | 220kV D/C Line | North-Eastern | 487.03 | 90.9 | 26 | 45.5 | Disputed | Stage-II Awaited | On Track | Physical progress is at 45.5%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1260 | 765kV Transmission Line | Eastern | 2812.5 | 317.5 | 58 | 44.2 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 44.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1261 | 220kV D/C Line | Eastern | 102.29 | 87.8 | 20 | 24.2 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 24.2%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-1262 | 400kV Substation | Eastern | 1014.33 | 52.9 | 36 | 44.9 | Pending Local | Approved | On Track | Physical progress is at 44.9%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-1263 | 765kV Transmission Line | Northern | 2470.75 | 364.5 | 44 | 20.6 | Clear | Approved | Insolvent | Physical progress is at 20.6%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1264 | 220kV D/C Line | North-Eastern | 141.92 | 72.3 | 31 | 15.5 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 15.5%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1265 | 765kV Transmission Line | Northern | 3437.99 | 295 | 43 | 25.4 | Clear | Stage-I Awaited | On Track | Physical progress is at 25.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1266 | 765kV Transmission Line | North-Eastern | 4091.6 | 493.6 | 44 | 73.8 | Pending Local | Approved | On Track | Physical progress is at 73.8%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-1267 | 765kV Transmission Line | Eastern | 3633.63 | 467.6 | 43 | 66.8 | Pending Local | Approved | On Track | Physical progress is at 66.8%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-1268 | 220kV D/C Line | North-Eastern | 694.71 | 139.2 | 19 | 57.7 | Clear | Approved | Equipment Delayed | Physical progress is at 57.7%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1269 | 220kV D/C Line | Eastern | 116.12 | 203 | 18 | 10.5 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 10.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1270 | 400kV Substation | Western | 1144.15 | 64.1 | 46 | 15.4 | Disputed | Stage-I Awaited | On Track | Physical progress is at 15.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1271 | 400kV Substation | Western | 1157.92 | 90.9 | 36 | 26.1 | Disputed | Stage-I Awaited | On Track | Physical progress is at 26.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1272 | 220kV D/C Line | Northern | 372.21 | 119 | 24 | 12.2 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 12.2%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1273 | 765kV Transmission Line | Southern | 2783.08 | 499.1 | 51 | 89.6 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 89.6% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 0 | Low
GRID-1274 | 765kV Transmission Line | Western | 1823.32 | 408.6 | 37 | 13.7 | Pending Local | Approved | Insolvent | Physical progress is at 13.7%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1275 | 400kV Substation | Western | 574.91 | 38 | 40 | 80 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 80.0% with all statutory clearances in place. | 0 | Low
GRID-1276 | 765kV Transmission Line | Western | 1560.14 | 488.4 | 55 | 50.8 | Disputed | Approved | On Track | Physical progress is at 50.8%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1277 | 220kV D/C Line | Northern | 645.34 | 160.7 | 23 | 49.8 | Disputed | Approved | On Track | Physical progress is at 49.8%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1278 | 400kV Substation | Western | 1219.62 | 56.2 | 24 | 14.2 | Disputed | Stage-II Awaited | On Track | Physical progress is at 14.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1279 | 765kV Transmission Line | Western | 4515.91 | 450.3 | 54 | 27.8 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 27.8%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1280 | 220kV D/C Line | North-Eastern | 628.16 | 63.4 | 24 | 61.2 | Clear | Approved | Equipment Delayed | Physical progress is at 61.2%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1281 | 220kV D/C Line | Eastern | 485.22 | 195.2 | 28 | 28 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 28.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1282 | 220kV D/C Line | Eastern | 216.83 | 221.6 | 16 | 73.7 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 73.7% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 1 | Medium
GRID-1283 | 400kV Substation | Southern | 748.35 | 38.3 | 30 | 58 | Clear | Approved | Equipment Delayed | Physical progress is at 58.0%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1284 | 220kV D/C Line | Southern | 377.45 | 78.5 | 19 | 19.3 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 19.3%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1285 | 400kV Substation | Northern | 594.44 | 23.1 | 44 | 21.6 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 21.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1286 | 765kV Transmission Line | North-Eastern | 2528.83 | 446.3 | 53 | 53.3 | Pending Local | Approved | Equipment Delayed | Physical progress is at 53.3%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1287 | 765kV Transmission Line | Northern | 2010.79 | 413.3 | 44 | 25.8 | Clear | Approved | Insolvent | Physical progress is at 25.8%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1288 | 765kV Transmission Line | Eastern | 2911.94 | 439.6 | 50 | 52 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 52.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1289 | 400kV Substation | Eastern | 1216.37 | 13.3 | 48 | 19.4 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 19.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1290 | 765kV Transmission Line | Western | 4167.38 | 258.9 | 55 | 17.6 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 17.6%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1291 | 220kV D/C Line | Western | 392.31 | 215.2 | 16 | 34.8 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 34.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1292 | 220kV D/C Line | Eastern | 650.91 | 93.8 | 17 | 30.3 | Disputed | Stage-I Awaited | On Track | Physical progress is at 30.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1293 | 400kV Substation | Southern | 992.45 | 59.3 | 47 | 26.7 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 26.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1294 | 220kV D/C Line | Western | 258.34 | 54.4 | 27 | 34.8 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 34.8%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-1295 | 400kV Substation | Northern | 1288.88 | 60 | 31 | 47.9 | Clear | Stage-I Awaited | On Track | Physical progress is at 47.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1296 | 400kV Substation | Eastern | 803.15 | 39.8 | 26 | 33.7 | Clear | Approved | Insolvent | Physical progress is at 33.7%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1297 | 400kV Substation | Northern | 822.75 | 83.4 | 28 | 13 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 13.0%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1298 | 400kV Substation | Eastern | 1006.11 | 46.5 | 31 | 14 | Pending Local | Approved | Insolvent | Physical progress is at 14.0%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1299 | 765kV Transmission Line | Northern | 1787.33 | 438.9 | 36 | 57.4 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 57.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1300 | 765kV Transmission Line | Northern | 3149.23 | 209.8 | 45 | 12.2 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 12.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1301 | 765kV Transmission Line | Northern | 4987.1 | 224.7 | 37 | 75.9 | Disputed | Approved | On Track | Physical progress is at 75.9%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1302 | 765kV Transmission Line | Southern | 3576.8 | 384.6 | 52 | 38.5 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 38.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1303 | 220kV D/C Line | North-Eastern | 167.28 | 171.3 | 34 | 67.8 | Pending Local | Approved | Equipment Delayed | Physical progress is at 67.8%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1304 | 220kV D/C Line | Southern | 305.56 | 191.1 | 24 | 28.4 | Pending Local | Approved | Equipment Delayed | Physical progress is at 28.4%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1305 | 220kV D/C Line | Western | 125.76 | 61.7 | 15 | 46 | Clear | Approved | Equipment Delayed | Physical progress is at 46.0%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1306 | 400kV Substation | Southern | 1125.27 | 62.1 | 46 | 33.4 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1307 | 400kV Substation | Western | 768.95 | 41.1 | 25 | 21.6 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 21.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1308 | 400kV Substation | Western | 1278.94 | 77.1 | 46 | 58.2 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 58.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1309 | 400kV Substation | Western | 350.43 | 22.6 | 40 | 11 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 11.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1310 | 220kV D/C Line | Southern | 336.03 | 70.9 | 36 | 53.3 | Disputed | Approved | On Track | Physical progress is at 53.3%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1311 | 220kV D/C Line | Eastern | 722.71 | 248.7 | 31 | 58.6 | Disputed | Approved | Equipment Delayed | Physical progress is at 58.6%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1312 | 765kV Transmission Line | Southern | 2664.12 | 322.2 | 56 | 33.1 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1313 | 400kV Substation | Southern | 1369.82 | 86.7 | 31 | 23.3 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 23.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1314 | 765kV Transmission Line | Eastern | 1507.88 | 214.3 | 38 | 31.7 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 31.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1315 | 220kV D/C Line | Northern | 447.64 | 166 | 29 | 24 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 24.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1316 | 765kV Transmission Line | Eastern | 1778.87 | 394.1 | 51 | 46.8 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 46.8% with all statutory clearances in place. | 1 | Medium
GRID-1317 | 765kV Transmission Line | Eastern | 2214.33 | 249.2 | 39 | 11.9 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 11.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1318 | 765kV Transmission Line | Northern | 4225.33 | 438.3 | 44 | 44.9 | Clear | Approved | Equipment Delayed | Physical progress is at 44.9%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1319 | 220kV D/C Line | Northern | 436.87 | 172.9 | 14 | 52.3 | Pending Local | Approved | Equipment Delayed | Physical progress is at 52.3%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1320 | 220kV D/C Line | Northern | 737.64 | 174.1 | 36 | 72 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 72.0% with all statutory clearances in place. | 0 | Low
GRID-1321 | 400kV Substation | Eastern | 1251.2 | 48.9 | 40 | 64.8 | Pending Local | Approved | On Track | Physical progress is at 64.8%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-1322 | 220kV D/C Line | Northern | 783.3 | 198.9 | 33 | 15 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 15.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1323 | 765kV Transmission Line | Northern | 3498.29 | 205.1 | 57 | 34.2 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 34.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1324 | 765kV Transmission Line | North-Eastern | 3321.8 | 429.8 | 54 | 13 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 13.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1325 | 765kV Transmission Line | Southern | 3379.79 | 327.7 | 37 | 67.8 | Clear | Approved | Equipment Delayed | Physical progress is at 67.8%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1326 | 765kV Transmission Line | Southern | 2689.79 | 323.6 | 38 | 28.5 | Disputed | Stage-I Awaited | On Track | Physical progress is at 28.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1327 | 765kV Transmission Line | Southern | 2647.14 | 413.5 | 40 | 12.4 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 12.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1328 | 765kV Transmission Line | Western | 3517.44 | 374.7 | 38 | 73.7 | Clear | Approved | Equipment Delayed | Physical progress is at 73.7%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1329 | 220kV D/C Line | North-Eastern | 754.65 | 224.1 | 29 | 28.8 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 28.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1330 | 765kV Transmission Line | Southern | 2441.67 | 215.6 | 38 | 75.7 | Clear | Stage-II Awaited | On Track | Physical progress is at 75.7%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1331 | 400kV Substation | Southern | 787.19 | 19.6 | 29 | 26.7 | Disputed | Stage-II Awaited | On Track | Physical progress is at 26.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1332 | 220kV D/C Line | Northern | 429.22 | 195.7 | 16 | 10.1 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 10.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1333 | 220kV D/C Line | Western | 444.86 | 97.6 | 25 | 30.6 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 30.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1334 | 765kV Transmission Line | Eastern | 4908.03 | 323.5 | 54 | 27.7 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 27.7%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1335 | 220kV D/C Line | Eastern | 101.02 | 72.9 | 30 | 52.6 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 52.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1336 | 220kV D/C Line | Western | 192.71 | 58 | 19 | 19.9 | Disputed | Approved | Insolvent | Physical progress is at 19.9%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1337 | 765kV Transmission Line | North-Eastern | 1509.86 | 263.1 | 39 | 28.3 | Disputed | Approved | Equipment Delayed | Physical progress is at 28.3%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1338 | 220kV D/C Line | Northern | 708.16 | 115 | 25 | 15 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 15.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1339 | 400kV Substation | Southern | 525.6 | 69.9 | 45 | 11.2 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 11.2%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1340 | 400kV Substation | Western | 373.69 | 90 | 25 | 12.8 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 12.8%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-1341 | 400kV Substation | Western | 811.38 | 11.2 | 48 | 17.6 | Disputed | Approved | Insolvent | Physical progress is at 17.6%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1342 | 765kV Transmission Line | Southern | 4438.14 | 489.1 | 44 | 32.6 | Clear | Stage-I Awaited | On Track | Physical progress is at 32.6%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1343 | 765kV Transmission Line | Eastern | 2846.04 | 495.9 | 53 | 48.8 | Disputed | Stage-II Awaited | On Track | Physical progress is at 48.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1344 | 220kV D/C Line | Northern | 290.27 | 181.7 | 21 | 16 | Disputed | Stage-I Awaited | On Track | Physical progress is at 16.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1345 | 765kV Transmission Line | North-Eastern | 4495.48 | 372.3 | 52 | 58.3 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 58.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1346 | 220kV D/C Line | Southern | 101.02 | 88.7 | 15 | 30.1 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 30.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 32 | High
GRID-1347 | 765kV Transmission Line | Eastern | 3151.49 | 258.9 | 43 | 50.4 | Pending Local | Approved | Equipment Delayed | Physical progress is at 50.4%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1348 | 400kV Substation | Western | 816.99 | 60.6 | 46 | 15.8 | Clear | Approved | Insolvent | Physical progress is at 15.8%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1349 | 765kV Transmission Line | Eastern | 2943.26 | 498.8 | 38 | 13.4 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 13.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1350 | 765kV Transmission Line | Southern | 1839 | 276.9 | 54 | 55.7 | Pending Local | Approved | Equipment Delayed | Physical progress is at 55.7%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1351 | 765kV Transmission Line | North-Eastern | 1915.73 | 441.6 | 55 | 27.2 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 27.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1352 | 400kV Substation | Western | 1254.87 | 89.9 | 27 | 16.9 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 16.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1353 | 400kV Substation | Eastern | 967.54 | 24.8 | 47 | 16.9 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 16.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1354 | 765kV Transmission Line | Northern | 4063.54 | 258.8 | 42 | 42.5 | Clear | Approved | Equipment Delayed | Physical progress is at 42.5%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1355 | 765kV Transmission Line | North-Eastern | 1970.8 | 235.4 | 59 | 27.2 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 27.2%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-1356 | 765kV Transmission Line | Eastern | 2823.3 | 251.4 | 37 | 12.1 | Disputed | Approved | Insolvent | Physical progress is at 12.1%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1357 | 765kV Transmission Line | Western | 2952.68 | 330.4 | 58 | 23.9 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 23.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-1358 | 765kV Transmission Line | North-Eastern | 3364.97 | 370.2 | 50 | 17.9 | Pending Local | Approved | Insolvent | Physical progress is at 17.9%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1359 | 220kV D/C Line | Northern | 237.39 | 109.1 | 36 | 29.9 | Disputed | Stage-I Awaited | On Track | Physical progress is at 29.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1360 | 765kV Transmission Line | North-Eastern | 4823.47 | 233.9 | 51 | 14.5 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 14.5%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1361 | 765kV Transmission Line | North-Eastern | 4504.06 | 363.1 | 38 | 23.1 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 23.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1362 | 400kV Substation | Southern | 958.69 | 84.5 | 25 | 48 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 48.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1363 | 765kV Transmission Line | North-Eastern | 3048.22 | 326.6 | 56 | 14.1 | Disputed | Approved | Insolvent | Physical progress is at 14.1%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1364 | 765kV Transmission Line | Northern | 4179.18 | 434 | 60 | 32.9 | Disputed | Stage-II Awaited | On Track | Physical progress is at 32.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1365 | 765kV Transmission Line | Western | 3182.73 | 441.6 | 50 | 59.5 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 59.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1366 | 220kV D/C Line | Southern | 626.77 | 102.2 | 14 | 22.3 | Disputed | Approved | Insolvent | Physical progress is at 22.3%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1367 | 765kV Transmission Line | Southern | 3254.95 | 436.5 | 46 | 21.7 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 21.7%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1368 | 765kV Transmission Line | Northern | 3817.13 | 465.7 | 48 | 41.2 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 41.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1369 | 765kV Transmission Line | Eastern | 2022.46 | 280.8 | 43 | 30.5 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 30.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1370 | 220kV D/C Line | Northern | 537.51 | 60.6 | 18 | 21.5 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 21.5%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-1371 | 220kV D/C Line | North-Eastern | 229.34 | 62.9 | 20 | 73.4 | Clear | Approved | Equipment Delayed | Physical progress is at 73.4%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1372 | 220kV D/C Line | North-Eastern | 616.95 | 102.3 | 35 | 55.2 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 55.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1373 | 765kV Transmission Line | Eastern | 4013.63 | 256.3 | 56 | 26.8 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 26.8%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1374 | 220kV D/C Line | Southern | 608.19 | 154.3 | 32 | 14 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 14.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1375 | 400kV Substation | North-Eastern | 817.07 | 19.4 | 48 | 31.7 | Pending Local | Approved | Equipment Delayed | Physical progress is at 31.7%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1376 | 765kV Transmission Line | Southern | 4811.5 | 312.1 | 45 | 68.8 | Clear | Approved | Equipment Delayed | Physical progress is at 68.8%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1377 | 400kV Substation | North-Eastern | 1119.82 | 36.4 | 47 | 35.1 | Clear | Stage-II Awaited | On Track | Physical progress is at 35.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1378 | 400kV Substation | Southern | 915.58 | 96.4 | 40 | 54.7 | Disputed | Approved | On Track | Physical progress is at 54.7%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1379 | 400kV Substation | Southern | 1170.59 | 22.1 | 43 | 17.2 | Disputed | Approved | Insolvent | Physical progress is at 17.2%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1380 | 765kV Transmission Line | Western | 4707.7 | 262.7 | 60 | 17.9 | Pending Local | Approved | Insolvent | Physical progress is at 17.9%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1381 | 400kV Substation | Western | 1268.05 | 82.5 | 26 | 21.7 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 21.7%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1382 | 220kV D/C Line | Western | 268.77 | 68.3 | 33 | 36.2 | Clear | Stage-I Awaited | On Track | Physical progress is at 36.2%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1383 | 765kV Transmission Line | Northern | 4588.34 | 456.4 | 59 | 22.6 | Clear | Approved | Insolvent | Physical progress is at 22.6%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1384 | 400kV Substation | Northern | 854.06 | 55.1 | 37 | 15.2 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 15.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1385 | 400kV Substation | Eastern | 434.42 | 21.5 | 43 | 33.4 | Disputed | Approved | On Track | Physical progress is at 33.4%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1386 | 400kV Substation | Southern | 1287.65 | 63.6 | 47 | 19.8 | Pending Local | Approved | Insolvent | Physical progress is at 19.8%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1387 | 765kV Transmission Line | Northern | 1766.88 | 381.1 | 39 | 17.3 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 17.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1388 | 400kV Substation | Northern | 1003.87 | 78.1 | 37 | 33.5 | Clear | Approved | Insolvent | Physical progress is at 33.5%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1389 | 765kV Transmission Line | Western | 3079.52 | 300.6 | 49 | 67.8 | Clear | Approved | Equipment Delayed | Physical progress is at 67.8%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-1390 | 765kV Transmission Line | North-Eastern | 3376.37 | 482.2 | 37 | 39.7 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 39.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1391 | 400kV Substation | Northern | 923.21 | 18.6 | 47 | 57.8 | Clear | Stage-I Awaited | On Track | Physical progress is at 57.8%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1392 | 220kV D/C Line | Western | 352.93 | 129.6 | 31 | 67.4 | Clear | Approved | Equipment Delayed | Physical progress is at 67.4%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1393 | 400kV Substation | Western | 419.93 | 25.8 | 30 | 20.9 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 20.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1394 | 400kV Substation | North-Eastern | 1072.98 | 22.8 | 30 | 17.6 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 17.6%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1395 | 400kV Substation | Southern | 584.91 | 87.7 | 41 | 28.5 | Disputed | Stage-II Awaited | On Track | Physical progress is at 28.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1396 | 220kV D/C Line | Northern | 137.38 | 183.4 | 26 | 59.7 | Disputed | Stage-II Awaited | On Track | Physical progress is at 59.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1397 | 400kV Substation | Southern | 988.9 | 94.1 | 46 | 24.9 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 24.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-1398 | 220kV D/C Line | Southern | 681.2 | 178.3 | 36 | 17.4 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 17.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1399 | 220kV D/C Line | North-Eastern | 273.74 | 116.1 | 15 | 25.5 | Pending Local | Approved | Insolvent | Physical progress is at 25.5%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1400 | 765kV Transmission Line | Northern | 2147.34 | 434.1 | 43 | 56.3 | Pending Local | Approved | Equipment Delayed | Physical progress is at 56.3%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1401 | 220kV D/C Line | Eastern | 208.5 | 178 | 26 | 28.7 | Pending Local | Approved | Insolvent | Physical progress is at 28.7%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1402 | 220kV D/C Line | North-Eastern | 254.28 | 184 | 31 | 55.9 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 55.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1403 | 765kV Transmission Line | Southern | 4860.07 | 466.2 | 39 | 10.7 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 10.7%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1404 | 220kV D/C Line | Southern | 481.15 | 79.3 | 33 | 19.5 | Pending Local | Approved | Insolvent | Physical progress is at 19.5%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1405 | 765kV Transmission Line | Northern | 3466.28 | 442.6 | 39 | 42.9 | Disputed | Stage-II Awaited | On Track | Physical progress is at 42.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1406 | 765kV Transmission Line | Southern | 2895.35 | 244.7 | 54 | 39.1 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 39.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1407 | 220kV D/C Line | North-Eastern | 403.97 | 128.1 | 24 | 60.2 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 60.2% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 1 | Medium
GRID-1408 | 765kV Transmission Line | Northern | 4808.7 | 312.6 | 37 | 31.4 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 31.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1409 | 400kV Substation | Western | 1335.48 | 57 | 42 | 28.8 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 28.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1410 | 400kV Substation | Eastern | 831.23 | 35.3 | 29 | 50.5 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 50.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1411 | 220kV D/C Line | Western | 341.19 | 161.1 | 14 | 34.5 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 34.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-1412 | 400kV Substation | North-Eastern | 1109.56 | 33.7 | 30 | 43.6 | Clear | Approved | Equipment Delayed | Physical progress is at 43.6%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1413 | 400kV Substation | Southern | 1157.9 | 25.4 | 35 | 58.6 | Pending Local | Approved | Equipment Delayed | Physical progress is at 58.6%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1414 | 220kV D/C Line | Northern | 155.02 | 82.7 | 24 | 73 | Clear | Approved | Equipment Delayed | Physical progress is at 73.0%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1415 | 765kV Transmission Line | Eastern | 3235.12 | 372 | 47 | 57.9 | Pending Local | Approved | On Track | Physical progress is at 57.9%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-1416 | 220kV D/C Line | Southern | 314.97 | 168.5 | 35 | 54.6 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 54.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1417 | 765kV Transmission Line | Eastern | 2463.87 | 498.5 | 43 | 12.5 | Pending Local | Approved | Insolvent | Physical progress is at 12.5%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1418 | 765kV Transmission Line | Eastern | 4093.21 | 349.9 | 52 | 89.2 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 89.2% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 0 | Low
GRID-1419 | 220kV D/C Line | Western | 282.77 | 236.1 | 25 | 30.7 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 30.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1420 | 765kV Transmission Line | Eastern | 4533.04 | 269.5 | 53 | 23.6 | Clear | Approved | Insolvent | Physical progress is at 23.6%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1421 | 400kV Substation | Northern | 706.17 | 61.5 | 38 | 27 | Disputed | Approved | Equipment Delayed | Physical progress is at 27.0%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1422 | 400kV Substation | Northern | 783.19 | 94.4 | 31 | 70.6 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 70.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1423 | 765kV Transmission Line | Northern | 3806.19 | 251.3 | 43 | 27 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 27.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1424 | 220kV D/C Line | Eastern | 755.94 | 187.3 | 24 | 26.3 | Disputed | Approved | Insolvent | Physical progress is at 26.3%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1425 | 220kV D/C Line | Western | 329.17 | 129.6 | 26 | 20.7 | Disputed | Approved | Insolvent | Physical progress is at 20.7%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1426 | 765kV Transmission Line | Western | 4622.62 | 211.3 | 46 | 31 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 31.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1427 | 220kV D/C Line | Southern | 553.86 | 109.6 | 31 | 17.1 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 17.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1428 | 765kV Transmission Line | Eastern | 1820.83 | 477.1 | 43 | 23.5 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 23.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1429 | 400kV Substation | Eastern | 1236.3 | 96.7 | 26 | 23.3 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 23.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-1430 | 220kV D/C Line | Eastern | 602.98 | 80.8 | 16 | 11 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 11.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1431 | 220kV D/C Line | North-Eastern | 100.46 | 178.7 | 33 | 55.3 | Disputed | Approved | Equipment Delayed | Physical progress is at 55.3%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1432 | 400kV Substation | North-Eastern | 698.25 | 51.1 | 25 | 51.2 | Clear | Stage-II Awaited | On Track | Physical progress is at 51.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1433 | 765kV Transmission Line | Southern | 4483.69 | 280.5 | 41 | 13.5 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 13.5%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1434 | 220kV D/C Line | Western | 578.47 | 197.9 | 20 | 78.4 | Pending Local | Approved | On Track | Physical progress is at 78.4%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1435 | 765kV Transmission Line | Southern | 2917.15 | 278.2 | 57 | 28.1 | Disputed | Stage-I Awaited | On Track | Physical progress is at 28.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1436 | 400kV Substation | Eastern | 501.22 | 61.8 | 36 | 23.2 | Disputed | Approved | Insolvent | Physical progress is at 23.2%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1437 | 765kV Transmission Line | North-Eastern | 1871.74 | 413.2 | 47 | 16.6 | Pending Local | Approved | Insolvent | Physical progress is at 16.6%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1438 | 765kV Transmission Line | North-Eastern | 2621.54 | 346.3 | 57 | 32.3 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 32.3%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1439 | 220kV D/C Line | North-Eastern | 152.16 | 216.5 | 27 | 23 | Disputed | Stage-I Awaited | On Track | Physical progress is at 23.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1440 | 400kV Substation | Northern | 403.21 | 42.8 | 36 | 24.3 | Pending Local | Approved | Equipment Delayed | Physical progress is at 24.3%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1441 | 765kV Transmission Line | Western | 4051.26 | 309.8 | 42 | 30 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 30.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1442 | 765kV Transmission Line | North-Eastern | 2430.14 | 454 | 58 | 51.1 | Disputed | Approved | Equipment Delayed | Physical progress is at 51.1%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1443 | 400kV Substation | North-Eastern | 935.05 | 99.8 | 46 | 10.2 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 10.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1444 | 220kV D/C Line | North-Eastern | 490.46 | 203.4 | 24 | 56.6 | Clear | Approved | Equipment Delayed | Physical progress is at 56.6%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1445 | 220kV D/C Line | North-Eastern | 390.86 | 200.9 | 29 | 27.7 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 27.7%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1446 | 220kV D/C Line | Southern | 613.02 | 134.4 | 23 | 13.2 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 13.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1447 | 220kV D/C Line | Eastern | 789.77 | 55.1 | 12 | 54.9 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 54.9% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 1 | Medium
GRID-1448 | 765kV Transmission Line | Western | 3749.28 | 447.7 | 39 | 33 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 33.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1449 | 220kV D/C Line | Western | 543.39 | 135.1 | 35 | 52.1 | Clear | Stage-II Awaited | On Track | Physical progress is at 52.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1450 | 220kV D/C Line | North-Eastern | 368.15 | 167.3 | 34 | 36.9 | Pending Local | Approved | Equipment Delayed | Physical progress is at 36.9%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1451 | 220kV D/C Line | Southern | 550.2 | 79.9 | 12 | 17.2 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 17.2%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1452 | 765kV Transmission Line | North-Eastern | 4327.05 | 231.8 | 40 | 81.2 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 81.2% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 0 | Low
GRID-1453 | 765kV Transmission Line | Eastern | 4084.04 | 465.6 | 52 | 15.1 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 15.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1454 | 765kV Transmission Line | North-Eastern | 2077.71 | 341.5 | 52 | 29.7 | Disputed | Approved | Insolvent | Physical progress is at 29.7%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1455 | 400kV Substation | Southern | 612.41 | 97.6 | 41 | 31.6 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 31.6%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1456 | 220kV D/C Line | Northern | 457.65 | 205.1 | 33 | 19.8 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 19.8%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1457 | 220kV D/C Line | Eastern | 222.88 | 141.4 | 18 | 26.4 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 26.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1458 | 400kV Substation | Western | 507.05 | 61.9 | 42 | 33.9 | Disputed | Approved | Insolvent | Physical progress is at 33.9%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1459 | 220kV D/C Line | North-Eastern | 152.75 | 110.6 | 29 | 53 | Disputed | Approved | On Track | Physical progress is at 53.0%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1460 | 220kV D/C Line | Western | 652.55 | 221.1 | 29 | 20.4 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 20.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1461 | 220kV D/C Line | Eastern | 253.21 | 211.6 | 21 | 16.5 | Clear | Approved | Insolvent | Physical progress is at 16.5%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1462 | 220kV D/C Line | Eastern | 527.85 | 195 | 17 | 24.3 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 24.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1463 | 765kV Transmission Line | Southern | 2362.71 | 470.3 | 50 | 27.7 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 27.7%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-1464 | 765kV Transmission Line | Western | 1598.27 | 402.6 | 39 | 14.3 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 14.3%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1465 | 220kV D/C Line | Eastern | 524.61 | 237.9 | 26 | 15.3 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 15.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-1466 | 765kV Transmission Line | Western | 3730.99 | 318.3 | 37 | 79.1 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 79.1% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 1 | Medium
GRID-1467 | 765kV Transmission Line | Eastern | 1732.43 | 450.6 | 41 | 29.5 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 29.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1468 | 220kV D/C Line | North-Eastern | 624.49 | 182.8 | 14 | 42.3 | Pending Local | Approved | Equipment Delayed | Physical progress is at 42.3%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1469 | 220kV D/C Line | Eastern | 794.52 | 66.5 | 33 | 13.6 | Disputed | Stage-I Awaited | On Track | Physical progress is at 13.6%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1470 | 220kV D/C Line | Western | 180.89 | 81.5 | 33 | 12.9 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 12.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1471 | 400kV Substation | Eastern | 425.41 | 92.2 | 25 | 13.4 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 13.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1472 | 765kV Transmission Line | Western | 4739.19 | 424 | 42 | 19.5 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 19.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1473 | 220kV D/C Line | Western | 418.74 | 225.4 | 21 | 27 | Disputed | Approved | On Track | Physical progress is at 27.0%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1474 | 400kV Substation | Northern | 1247.8 | 71.5 | 44 | 59.3 | Disputed | Approved | Equipment Delayed | Physical progress is at 59.3%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1475 | 400kV Substation | Western | 320.54 | 84.1 | 30 | 30.1 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 30.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1476 | 220kV D/C Line | North-Eastern | 447.59 | 53.4 | 15 | 31 | Clear | Stage-I Awaited | On Track | Physical progress is at 31.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1477 | 400kV Substation | North-Eastern | 691.97 | 43 | 33 | 77.7 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 77.7% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 1 | Medium
GRID-1478 | 765kV Transmission Line | Eastern | 1930.89 | 384.3 | 51 | 26.7 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 26.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1479 | 400kV Substation | Northern | 817.47 | 87.6 | 24 | 74.4 | Pending Local | Approved | On Track | Physical progress is at 74.4%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-1480 | 220kV D/C Line | Northern | 339.67 | 102.2 | 17 | 27.8 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 27.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1481 | 765kV Transmission Line | Northern | 1559.01 | 309 | 48 | 32.3 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 32.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1482 | 400kV Substation | Eastern | 1008.15 | 80.1 | 35 | 22 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 22.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1483 | 400kV Substation | Eastern | 303.28 | 14 | 25 | 48.3 | Clear | Stage-II Awaited | On Track | Physical progress is at 48.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1484 | 400kV Substation | North-Eastern | 575.82 | 50.4 | 32 | 22.9 | Clear | Stage-I Awaited | On Track | Physical progress is at 22.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1485 | 220kV D/C Line | Northern | 668.64 | 184 | 26 | 54.7 | Clear | Approved | Insolvent | Physical progress is at 54.7%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1486 | 400kV Substation | Northern | 856.15 | 27.6 | 25 | 38.5 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 38.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1487 | 765kV Transmission Line | Northern | 4345.49 | 286.3 | 52 | 12.9 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 12.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1488 | 220kV D/C Line | Eastern | 227.21 | 156.3 | 28 | 22.4 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 22.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1489 | 400kV Substation | Western | 1499.71 | 82.3 | 48 | 56.9 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 56.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1490 | 400kV Substation | Western | 394.72 | 62.7 | 40 | 21.9 | Clear | Approved | Insolvent | Physical progress is at 21.9%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1491 | 765kV Transmission Line | Southern | 2910.45 | 327.7 | 45 | 12.9 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 12.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1492 | 220kV D/C Line | Eastern | 187.03 | 100.5 | 12 | 24.4 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 24.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1493 | 400kV Substation | Western | 350.76 | 65 | 40 | 29.6 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 29.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1494 | 220kV D/C Line | Western | 553.62 | 89.7 | 30 | 44.1 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 44.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1495 | 765kV Transmission Line | Eastern | 4678.27 | 486.6 | 40 | 22 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 22.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1496 | 765kV Transmission Line | Western | 4167.68 | 331.1 | 42 | 21.2 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 21.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1497 | 765kV Transmission Line | Eastern | 4468.43 | 486.7 | 40 | 60.6 | Clear | Approved | Equipment Delayed | Physical progress is at 60.6%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-1498 | 765kV Transmission Line | Northern | 2937.6 | 452.3 | 57 | 54 | Disputed | Stage-II Awaited | On Track | Physical progress is at 54.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1499 | 765kV Transmission Line | Southern | 3895.21 | 425.3 | 54 | 12.1 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 12.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1500 | 220kV D/C Line | North-Eastern | 121.38 | 214.1 | 14 | 28.9 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 28.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1501 | 220kV D/C Line | Eastern | 780.76 | 124.8 | 12 | 50.4 | Disputed | Approved | On Track | Physical progress is at 50.4%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1502 | 400kV Substation | Eastern | 684.24 | 70 | 29 | 24.9 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 24.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1503 | 765kV Transmission Line | North-Eastern | 4618.46 | 402.3 | 54 | 24 | Pending Local | Approved | Insolvent | Physical progress is at 24.0%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1504 | 400kV Substation | Eastern | 994.32 | 99.9 | 39 | 43.6 | Disputed | Stage-II Awaited | On Track | Physical progress is at 43.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1505 | 400kV Substation | Northern | 1248.14 | 48.1 | 35 | 27.1 | Pending Local | Approved | Equipment Delayed | Physical progress is at 27.1%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1506 | 400kV Substation | Eastern | 724.85 | 80.1 | 38 | 26 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 26.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1507 | 220kV D/C Line | Eastern | 368.61 | 99.7 | 20 | 22.8 | Disputed | Stage-I Awaited | On Track | Physical progress is at 22.8%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1508 | 400kV Substation | Northern | 483.54 | 40.4 | 36 | 73 | Clear | Approved | Equipment Delayed | Physical progress is at 73.0%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1509 | 400kV Substation | North-Eastern | 956.05 | 10 | 42 | 27.4 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 27.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1510 | 400kV Substation | Western | 1482.01 | 45.6 | 28 | 10.6 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 10.6%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 29 | High
GRID-1511 | 765kV Transmission Line | Western | 4995.49 | 233.9 | 60 | 48.6 | Disputed | Approved | Equipment Delayed | Physical progress is at 48.6%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1512 | 765kV Transmission Line | Eastern | 4019 | 468.3 | 46 | 52.8 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 52.8% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 1 | Medium
GRID-1513 | 765kV Transmission Line | Southern | 4672.5 | 283.5 | 45 | 57.2 | Pending Local | Approved | Equipment Delayed | Physical progress is at 57.2%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1514 | 765kV Transmission Line | Southern | 2457.6 | 436.3 | 49 | 55.9 | Pending Local | Approved | Equipment Delayed | Physical progress is at 55.9%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1515 | 220kV D/C Line | Western | 590.14 | 168.9 | 30 | 38.5 | Disputed | Stage-II Awaited | On Track | Physical progress is at 38.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1516 | 765kV Transmission Line | Southern | 1778.67 | 281.3 | 52 | 76.8 | Clear | Approved | Equipment Delayed | Physical progress is at 76.8%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1517 | 400kV Substation | North-Eastern | 806.62 | 69.7 | 43 | 25.5 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 25.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1518 | 220kV D/C Line | Eastern | 497.05 | 187.7 | 14 | 26.5 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 26.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-1519 | 220kV D/C Line | North-Eastern | 575.67 | 61.7 | 33 | 11.1 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 11.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1520 | 400kV Substation | Northern | 806.98 | 75.5 | 31 | 17.9 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 17.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1521 | 220kV D/C Line | North-Eastern | 281.93 | 124.5 | 13 | 43.8 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 43.8%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1522 | 400kV Substation | North-Eastern | 1465.53 | 32.5 | 25 | 20.8 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 20.8%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1523 | 400kV Substation | Southern | 494.2 | 83.8 | 33 | 23.4 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 23.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1524 | 400kV Substation | Southern | 1457.71 | 27.3 | 40 | 54.3 | Disputed | Approved | Equipment Delayed | Physical progress is at 54.3%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1525 | 400kV Substation | Eastern | 1239.93 | 86.9 | 29 | 19.9 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 19.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1526 | 765kV Transmission Line | Northern | 1532.05 | 479.6 | 49 | 65.3 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 65.3% with all statutory clearances in place. | 0 | Low
GRID-1527 | 220kV D/C Line | Eastern | 317.43 | 76.9 | 22 | 23.2 | Disputed | Approved | Equipment Delayed | Physical progress is at 23.2%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1528 | 765kV Transmission Line | Southern | 4687.52 | 455.5 | 44 | 29 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 29.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1529 | 400kV Substation | North-Eastern | 919.52 | 45.6 | 46 | 46.9 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 46.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1530 | 400kV Substation | Northern | 1417.18 | 34.6 | 28 | 13.7 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 13.7%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1531 | 765kV Transmission Line | North-Eastern | 2379.3 | 420.6 | 51 | 54.7 | Pending Local | Approved | Equipment Delayed | Physical progress is at 54.7%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1532 | 400kV Substation | North-Eastern | 720.43 | 83.7 | 29 | 13.1 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 13.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1533 | 400kV Substation | Southern | 1256.3 | 98.2 | 32 | 16.4 | Clear | Approved | Insolvent | Physical progress is at 16.4%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1534 | 400kV Substation | Eastern | 706.25 | 23.1 | 30 | 65.4 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 65.4% with all statutory clearances in place. | 0 | Low
GRID-1535 | 400kV Substation | Eastern | 1381.4 | 45.8 | 30 | 26.8 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 26.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1536 | 220kV D/C Line | Western | 673.75 | 229.5 | 23 | 31.2 | Disputed | Approved | Insolvent | Physical progress is at 31.2%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1537 | 765kV Transmission Line | Southern | 2651.33 | 390.6 | 37 | 41.8 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 41.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1538 | 220kV D/C Line | Western | 331.72 | 95.9 | 21 | 25.9 | Clear | Approved | Insolvent | Physical progress is at 25.9%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1539 | 220kV D/C Line | Northern | 600.61 | 129.3 | 27 | 34.7 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 34.7%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-1540 | 220kV D/C Line | Southern | 283.16 | 135.5 | 29 | 44.1 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 44.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1541 | 220kV D/C Line | North-Eastern | 175.01 | 178.4 | 32 | 23.4 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 23.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1542 | 220kV D/C Line | North-Eastern | 505.5 | 247.6 | 28 | 34.8 | Disputed | Approved | Insolvent | Physical progress is at 34.8%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1543 | 220kV D/C Line | Western | 686.26 | 70.9 | 26 | 21.5 | Disputed | Approved | Equipment Delayed | Physical progress is at 21.5%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1544 | 220kV D/C Line | Southern | 222.52 | 76.4 | 18 | 23 | Disputed | Stage-II Awaited | On Track | Physical progress is at 23.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1545 | 765kV Transmission Line | Northern | 4948.66 | 397.9 | 51 | 15.3 | Clear | Stage-I Awaited | On Track | Physical progress is at 15.3%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1546 | 220kV D/C Line | North-Eastern | 746.91 | 192.3 | 29 | 61.6 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 61.6% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 0 | Low
GRID-1547 | 765kV Transmission Line | Northern | 1556.97 | 407.5 | 48 | 22.7 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 22.7%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1548 | 765kV Transmission Line | Northern | 3417.09 | 445.3 | 42 | 32.9 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 32.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1549 | 400kV Substation | Southern | 1079.85 | 67.7 | 26 | 20.5 | Disputed | Stage-II Awaited | On Track | Physical progress is at 20.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1550 | 765kV Transmission Line | Southern | 2582.66 | 459.9 | 54 | 47.9 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 47.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1551 | 400kV Substation | Western | 304.21 | 83.6 | 32 | 11.9 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 11.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1552 | 400kV Substation | Eastern | 1466.93 | 70.2 | 37 | 76.2 | Pending Local | Approved | On Track | Physical progress is at 76.2%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-1553 | 400kV Substation | Southern | 1341 | 73.8 | 46 | 23.5 | Clear | Stage-I Awaited | On Track | Physical progress is at 23.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1554 | 400kV Substation | North-Eastern | 1281.53 | 92.5 | 32 | 19.2 | Disputed | Stage-I Awaited | On Track | Physical progress is at 19.2%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1555 | 400kV Substation | North-Eastern | 542.76 | 59.9 | 36 | 25.2 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 25.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1556 | 220kV D/C Line | North-Eastern | 464.03 | 177.1 | 15 | 19.1 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 19.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1557 | 765kV Transmission Line | Southern | 3087.37 | 223.3 | 50 | 13.2 | Pending Local | Approved | Insolvent | Physical progress is at 13.2%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1558 | 400kV Substation | Southern | 845.46 | 96.7 | 40 | 32.1 | Disputed | Stage-II Awaited | On Track | Physical progress is at 32.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1559 | 220kV D/C Line | Southern | 754.17 | 238.1 | 26 | 22.2 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 22.2%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1560 | 220kV D/C Line | Western | 441.79 | 127 | 17 | 29.9 | Clear | Approved | Insolvent | Physical progress is at 29.9%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1561 | 400kV Substation | Northern | 1030.26 | 63.3 | 28 | 44.1 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 44.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1562 | 220kV D/C Line | North-Eastern | 152.11 | 60.7 | 34 | 12.6 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 12.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1563 | 400kV Substation | Eastern | 1300.13 | 14.1 | 37 | 45.1 | Disputed | Approved | On Track | Physical progress is at 45.1%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1564 | 400kV Substation | Northern | 1152.37 | 11.6 | 47 | 15.5 | Clear | Approved | Insolvent | Physical progress is at 15.5%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1565 | 400kV Substation | Southern | 1440.77 | 51.3 | 30 | 33 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1566 | 765kV Transmission Line | Northern | 1811.36 | 356.1 | 52 | 27.9 | Clear | Approved | Insolvent | Physical progress is at 27.9%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1567 | 765kV Transmission Line | Western | 4977.9 | 221.7 | 53 | 71.5 | Pending Local | Approved | Equipment Delayed | Physical progress is at 71.5%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1568 | 765kV Transmission Line | Northern | 3510.26 | 492.4 | 55 | 32.6 | Clear | Stage-I Awaited | On Track | Physical progress is at 32.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1569 | 765kV Transmission Line | Northern | 4103.54 | 268.2 | 50 | 41.8 | Clear | Stage-II Awaited | On Track | Physical progress is at 41.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1570 | 765kV Transmission Line | Eastern | 3577.77 | 404.1 | 36 | 29.6 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 29.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1571 | 765kV Transmission Line | Western | 4291.07 | 356.6 | 49 | 13.3 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 13.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1572 | 765kV Transmission Line | Eastern | 4427.16 | 226.4 | 55 | 30.1 | Disputed | Stage-II Awaited | On Track | Physical progress is at 30.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1573 | 765kV Transmission Line | Northern | 1624.33 | 299.7 | 40 | 14.6 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 14.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1574 | 220kV D/C Line | Southern | 406.5 | 154.8 | 19 | 56.2 | Pending Local | Approved | Equipment Delayed | Physical progress is at 56.2%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1575 | 765kV Transmission Line | Eastern | 3067.32 | 376.5 | 43 | 34.2 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 34.2%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1576 | 220kV D/C Line | Southern | 384.12 | 77.6 | 13 | 33.2 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 33.2%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1577 | 400kV Substation | Eastern | 1043.85 | 41.7 | 35 | 47.3 | Pending Local | Approved | On Track | Physical progress is at 47.3%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1578 | 220kV D/C Line | Northern | 478.59 | 116.7 | 36 | 65.2 | Pending Local | Approved | On Track | Physical progress is at 65.2%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-1579 | 220kV D/C Line | Northern | 566.26 | 170 | 19 | 71.2 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 71.2% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 1 | Medium
GRID-1580 | 400kV Substation | Southern | 1144.99 | 50.1 | 36 | 25.8 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 25.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1581 | 765kV Transmission Line | Southern | 4361.5 | 479.7 | 58 | 75.7 | Clear | Stage-II Awaited | On Track | Physical progress is at 75.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1582 | 765kV Transmission Line | Western | 3032.08 | 294.1 | 54 | 74.4 | Pending Local | Approved | On Track | Physical progress is at 74.4%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-1583 | 765kV Transmission Line | Northern | 2618.28 | 301.2 | 59 | 21 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 21.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1584 | 400kV Substation | Southern | 352.59 | 85.1 | 27 | 43.8 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 43.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1585 | 220kV D/C Line | North-Eastern | 571.85 | 178.8 | 19 | 79.3 | Disputed | Approved | On Track | Physical progress is at 79.3%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1586 | 220kV D/C Line | North-Eastern | 251.36 | 110.8 | 35 | 13 | Clear | Approved | Insolvent | Physical progress is at 13.0%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1587 | 400kV Substation | Western | 1425.23 | 89 | 37 | 11.8 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 11.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1588 | 765kV Transmission Line | Southern | 4581.75 | 385 | 41 | 13.7 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 13.7%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1589 | 765kV Transmission Line | Northern | 2926.45 | 346.1 | 54 | 42.8 | Clear | Stage-II Awaited | On Track | Physical progress is at 42.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1590 | 765kV Transmission Line | Northern | 3413.57 | 415.1 | 51 | 22.5 | Pending Local | Approved | Insolvent | Physical progress is at 22.5%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1591 | 220kV D/C Line | Western | 563.55 | 164.1 | 21 | 10.1 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 10.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1592 | 765kV Transmission Line | Southern | 2648.32 | 265.4 | 56 | 48.5 | Pending Local | Approved | On Track | Physical progress is at 48.5%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-1593 | 400kV Substation | Southern | 456.01 | 45.2 | 33 | 24.6 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 24.6%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1594 | 765kV Transmission Line | Western | 2577 | 456.8 | 38 | 65.7 | Clear | Stage-II Awaited | On Track | Physical progress is at 65.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1595 | 220kV D/C Line | Northern | 349.32 | 51.1 | 36 | 13.8 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 13.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1596 | 400kV Substation | Eastern | 563.93 | 22.2 | 24 | 18.1 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 18.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1597 | 765kV Transmission Line | North-Eastern | 4079.31 | 431.3 | 45 | 58.1 | Clear | Stage-I Awaited | On Track | Physical progress is at 58.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1598 | 400kV Substation | Western | 1256.81 | 89.6 | 28 | 16.4 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 16.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1599 | 765kV Transmission Line | Eastern | 1900.87 | 440.3 | 41 | 14.7 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 14.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1600 | 765kV Transmission Line | North-Eastern | 4039.45 | 251.3 | 47 | 10.1 | Disputed | Approved | Insolvent | Physical progress is at 10.1%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1601 | 400kV Substation | Northern | 1227.36 | 55.3 | 30 | 24.2 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 24.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1602 | 220kV D/C Line | Northern | 367.2 | 153.4 | 34 | 23.4 | Clear | Stage-I Awaited | On Track | Physical progress is at 23.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1603 | 765kV Transmission Line | North-Eastern | 4926.81 | 382.6 | 40 | 34 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 34.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1604 | 220kV D/C Line | Western | 217.68 | 200.8 | 17 | 81.5 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 81.5% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 0 | Low
GRID-1605 | 220kV D/C Line | Western | 141.41 | 67.7 | 20 | 33.1 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 33.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1606 | 400kV Substation | North-Eastern | 1022.93 | 27.7 | 24 | 10.9 | Disputed | Approved | Insolvent | Physical progress is at 10.9%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1607 | 400kV Substation | Western | 562.82 | 21.8 | 46 | 16.1 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 16.1%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1608 | 220kV D/C Line | Northern | 392.55 | 227.3 | 25 | 34.6 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 34.6%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1609 | 220kV D/C Line | North-Eastern | 261.57 | 215.6 | 26 | 13.3 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 13.3%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1610 | 220kV D/C Line | Western | 793.47 | 67.9 | 33 | 19.5 | Disputed | Stage-II Awaited | On Track | Physical progress is at 19.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1611 | 765kV Transmission Line | North-Eastern | 4121.76 | 359.3 | 39 | 30.5 | Clear | Stage-I Awaited | On Track | Physical progress is at 30.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1612 | 220kV D/C Line | Eastern | 374.32 | 80.2 | 14 | 40.6 | Clear | Approved | Equipment Delayed | Physical progress is at 40.6%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1613 | 400kV Substation | Eastern | 968.62 | 43.2 | 37 | 27.5 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 27.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1614 | 220kV D/C Line | North-Eastern | 662.93 | 122.4 | 13 | 37.6 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 37.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1615 | 220kV D/C Line | Southern | 523.26 | 87.7 | 19 | 14.2 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 14.2%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1616 | 400kV Substation | Western | 820.61 | 85.1 | 26 | 46.6 | Pending Local | Approved | Equipment Delayed | Physical progress is at 46.6%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1617 | 220kV D/C Line | North-Eastern | 586.8 | 103.3 | 16 | 28.4 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 28.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1618 | 220kV D/C Line | North-Eastern | 751.21 | 79.5 | 19 | 15.5 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 15.5%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-1619 | 220kV D/C Line | Southern | 763.06 | 244.8 | 17 | 29.4 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 29.4%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1620 | 765kV Transmission Line | Northern | 4331.21 | 272.3 | 38 | 10.7 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 10.7%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 32 | High
GRID-1621 | 220kV D/C Line | Eastern | 741.3 | 162.7 | 20 | 28 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 28.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1622 | 765kV Transmission Line | Eastern | 2797.52 | 341.7 | 44 | 34.1 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 34.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-1623 | 400kV Substation | Western | 394.89 | 40.9 | 35 | 18.3 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 18.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1624 | 220kV D/C Line | Northern | 670.34 | 87.1 | 24 | 19.9 | Disputed | Approved | Equipment Delayed | Physical progress is at 19.9%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1625 | 765kV Transmission Line | Western | 1547.41 | 461 | 44 | 50.6 | Clear | Approved | Equipment Delayed | Physical progress is at 50.6%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-1626 | 765kV Transmission Line | Southern | 1684.24 | 400.3 | 44 | 32.4 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 32.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1627 | 400kV Substation | Southern | 556.19 | 82.9 | 38 | 12.6 | Disputed | Stage-I Awaited | On Track | Physical progress is at 12.6%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1628 | 220kV D/C Line | Northern | 446.98 | 156.2 | 23 | 72.9 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 72.9% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 0 | Low
GRID-1629 | 765kV Transmission Line | Western | 2769.62 | 490.8 | 44 | 16.7 | Disputed | Approved | Equipment Delayed | Physical progress is at 16.7%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1630 | 765kV Transmission Line | Eastern | 2178.98 | 489.5 | 56 | 18.5 | Disputed | Approved | Insolvent | Physical progress is at 18.5%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1631 | 400kV Substation | Eastern | 843.56 | 62 | 36 | 10.1 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 10.1%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1632 | 220kV D/C Line | Southern | 670.7 | 212.7 | 29 | 66 | Clear | Approved | Equipment Delayed | Physical progress is at 66.0%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1633 | 765kV Transmission Line | Northern | 4722.71 | 345.2 | 57 | 52.4 | Clear | Stage-II Awaited | On Track | Physical progress is at 52.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1634 | 400kV Substation | Western | 443.9 | 12.4 | 33 | 33 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 33.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1635 | 400kV Substation | Western | 1390.12 | 27.9 | 30 | 23 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 23.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1636 | 220kV D/C Line | Western | 502.93 | 176.2 | 27 | 58.7 | Clear | Stage-I Awaited | On Track | Physical progress is at 58.7%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1637 | 220kV D/C Line | Western | 736.68 | 79.7 | 16 | 10 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 10.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1638 | 400kV Substation | Western | 455.04 | 48.1 | 26 | 12.3 | Disputed | Stage-I Awaited | On Track | Physical progress is at 12.3%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1639 | 765kV Transmission Line | North-Eastern | 2156.03 | 382.1 | 39 | 21.5 | Disputed | Approved | On Track | Physical progress is at 21.5%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1640 | 400kV Substation | Northern | 487.17 | 19 | 44 | 12.2 | Disputed | Approved | Insolvent | Physical progress is at 12.2%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1641 | 220kV D/C Line | Southern | 473.89 | 101.7 | 24 | 25.2 | Pending Local | Approved | Equipment Delayed | Physical progress is at 25.2%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1642 | 220kV D/C Line | Western | 199.14 | 82.3 | 34 | 25.2 | Disputed | Approved | Insolvent | Physical progress is at 25.2%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1643 | 400kV Substation | North-Eastern | 1488.47 | 87.2 | 42 | 28.4 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 28.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1644 | 765kV Transmission Line | Eastern | 2140.64 | 466.5 | 46 | 16.1 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 16.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1645 | 765kV Transmission Line | Northern | 3360.5 | 281.5 | 57 | 39.4 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 39.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1646 | 220kV D/C Line | Southern | 640.52 | 180.6 | 22 | 28.8 | Clear | Approved | Insolvent | Physical progress is at 28.8%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1647 | 765kV Transmission Line | Eastern | 3813.84 | 352.6 | 45 | 26.4 | Disputed | Stage-I Awaited | On Track | Physical progress is at 26.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1648 | 400kV Substation | Southern | 1248.9 | 14.1 | 34 | 46.4 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 46.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1649 | 400kV Substation | Southern | 386.43 | 61 | 45 | 24.4 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 24.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1650 | 220kV D/C Line | Southern | 415.6 | 149.3 | 17 | 20.7 | Clear | Stage-I Awaited | On Track | Physical progress is at 20.7%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1651 | 400kV Substation | Western | 1100 | 16.4 | 44 | 66.5 | Pending Local | Approved | On Track | Physical progress is at 66.5%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1652 | 400kV Substation | Northern | 1428.96 | 61.4 | 48 | 24.2 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 24.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 32 | High
GRID-1653 | 220kV D/C Line | North-Eastern | 432.2 | 64.8 | 25 | 34.6 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 34.6%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1654 | 400kV Substation | Eastern | 1109.94 | 12.5 | 34 | 15.9 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 15.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1655 | 765kV Transmission Line | Northern | 3609.16 | 389 | 48 | 26.8 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 26.8%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1656 | 765kV Transmission Line | Northern | 2006.56 | 247.6 | 54 | 39.5 | Clear | Stage-I Awaited | On Track | Physical progress is at 39.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1657 | 400kV Substation | Southern | 975.65 | 51 | 33 | 13.5 | Pending Local | Approved | Insolvent | Physical progress is at 13.5%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1658 | 400kV Substation | Southern | 671.02 | 69.9 | 37 | 33.1 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1659 | 400kV Substation | Southern | 811.96 | 99.2 | 32 | 49.8 | Pending Local | Approved | On Track | Physical progress is at 49.8%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-1660 | 220kV D/C Line | Western | 429.18 | 57.5 | 35 | 34.1 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 34.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1661 | 220kV D/C Line | North-Eastern | 555.05 | 77.5 | 34 | 67.8 | Pending Local | Approved | Equipment Delayed | Physical progress is at 67.8%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1662 | 220kV D/C Line | Northern | 225.47 | 120 | 17 | 37.1 | Disputed | Approved | Equipment Delayed | Physical progress is at 37.1%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1663 | 400kV Substation | North-Eastern | 647.98 | 57.2 | 41 | 20.3 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 20.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 29 | High
GRID-1664 | 400kV Substation | Southern | 1349.59 | 94.8 | 33 | 51.7 | Disputed | Approved | Equipment Delayed | Physical progress is at 51.7%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1665 | 400kV Substation | North-Eastern | 1413.6 | 63 | 48 | 24.5 | Disputed | Approved | Insolvent | Physical progress is at 24.5%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1666 | 220kV D/C Line | Southern | 713.95 | 102.8 | 28 | 11.2 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 11.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1667 | 220kV D/C Line | Eastern | 606.48 | 93.7 | 30 | 13.9 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 13.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1668 | 765kV Transmission Line | Western | 1903 | 343.6 | 37 | 17.2 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 17.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1669 | 400kV Substation | North-Eastern | 458.29 | 80 | 25 | 51.1 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 51.1% with all statutory clearances in place. | 1 | Medium
GRID-1670 | 765kV Transmission Line | North-Eastern | 2282.06 | 216.4 | 36 | 51.2 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 51.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1671 | 400kV Substation | Eastern | 1337.18 | 57.6 | 43 | 45.1 | Pending Local | Approved | Equipment Delayed | Physical progress is at 45.1%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1672 | 220kV D/C Line | Eastern | 779.6 | 65.8 | 30 | 48.2 | Disputed | Approved | On Track | Physical progress is at 48.2%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1673 | 765kV Transmission Line | Southern | 3935.17 | 319 | 43 | 41.9 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 41.9% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 1 | Medium
GRID-1674 | 400kV Substation | Western | 1419.35 | 76.7 | 25 | 51.7 | Clear | Approved | Equipment Delayed | Physical progress is at 51.7%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1675 | 400kV Substation | Western | 1087.23 | 11.7 | 31 | 28.5 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 28.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 33 | High
GRID-1676 | 220kV D/C Line | Southern | 597.53 | 229.4 | 30 | 26.3 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 26.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1677 | 765kV Transmission Line | Eastern | 2422.24 | 498.1 | 45 | 29.1 | Clear | Stage-I Awaited | On Track | Physical progress is at 29.1%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1678 | 765kV Transmission Line | Western | 2066.95 | 367.7 | 44 | 28.2 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 28.2%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1679 | 765kV Transmission Line | North-Eastern | 4979.06 | 387.1 | 43 | 71.6 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 71.6% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 0 | Low
GRID-1680 | 765kV Transmission Line | Northern | 2268.11 | 276.1 | 50 | 26.8 | Pending Local | Approved | Insolvent | Physical progress is at 26.8%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1681 | 400kV Substation | Northern | 825.05 | 48.4 | 48 | 32.5 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 32.5%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1682 | 220kV D/C Line | Southern | 247.43 | 65.6 | 17 | 22.2 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 22.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1683 | 765kV Transmission Line | Southern | 4008.59 | 485.2 | 40 | 21.5 | Clear | Approved | Insolvent | Physical progress is at 21.5%. Construction activities are impacted as primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1684 | 765kV Transmission Line | Eastern | 4011.95 | 487.3 | 57 | 22.3 | Clear | Stage-I Awaited | On Track | Physical progress is at 22.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1685 | 400kV Substation | North-Eastern | 855.08 | 79.9 | 27 | 16.5 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 16.5%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1686 | 400kV Substation | Northern | 763.58 | 67.6 | 31 | 18.5 | Disputed | Stage-I Awaited | On Track | Physical progress is at 18.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1687 | 765kV Transmission Line | Southern | 3595.79 | 440.8 | 54 | 32.9 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 32.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1688 | 765kV Transmission Line | Western | 3079.79 | 430.8 | 38 | 63 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 63.0% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 0 | Low
GRID-1689 | 765kV Transmission Line | Southern | 4938.82 | 365.8 | 59 | 31.4 | Disputed | Approved | Insolvent | Physical progress is at 31.4%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1690 | 220kV D/C Line | Northern | 658.56 | 236.5 | 31 | 34.3 | Clear | Stage-I Awaited | On Track | Physical progress is at 34.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1691 | 220kV D/C Line | Southern | 224.74 | 113.7 | 36 | 27 | Clear | Stage-I Awaited | On Track | Physical progress is at 27.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1692 | 400kV Substation | Southern | 599.73 | 60.2 | 29 | 46 | Clear | Approved | Equipment Delayed | Physical progress is at 46.0%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1693 | 400kV Substation | Western | 752.26 | 38.8 | 32 | 27.3 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 27.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1694 | 400kV Substation | Southern | 831.38 | 91.4 | 24 | 24.5 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 24.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1695 | 400kV Substation | Northern | 1265.33 | 10.9 | 35 | 14.7 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 14.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1696 | 400kV Substation | North-Eastern | 1142.39 | 26.3 | 37 | 36.6 | Disputed | Stage-II Awaited | On Track | Physical progress is at 36.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1697 | 400kV Substation | Eastern | 869 | 81.5 | 29 | 43.2 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 43.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1698 | 220kV D/C Line | Northern | 199.23 | 170.9 | 12 | 17.1 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 17.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-1699 | 765kV Transmission Line | Northern | 2030.72 | 295.3 | 60 | 16.1 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 16.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1700 | 765kV Transmission Line | North-Eastern | 4029.52 | 399.2 | 41 | 26.6 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 26.6%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1701 | 765kV Transmission Line | Western | 2216.67 | 232.1 | 56 | 43 | Disputed | Approved | On Track | Physical progress is at 43.0%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1702 | 220kV D/C Line | Western | 144.96 | 178.5 | 17 | 73 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 73.0% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 0 | Low
GRID-1703 | 220kV D/C Line | Western | 708.81 | 158.7 | 29 | 23.3 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 23.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1704 | 400kV Substation | Southern | 1486.59 | 77.5 | 45 | 62.8 | Clear | Approved | Equipment Delayed | Physical progress is at 62.8%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1705 | 400kV Substation | North-Eastern | 876.53 | 84.9 | 40 | 28.7 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 28.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1706 | 220kV D/C Line | Western | 252.4 | 181.7 | 15 | 13.6 | Disputed | Approved | Insolvent | Physical progress is at 13.6%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1707 | 765kV Transmission Line | Northern | 2569.73 | 219.2 | 45 | 31.3 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 31.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1708 | 765kV Transmission Line | Eastern | 4519.45 | 334 | 60 | 23.2 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 23.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1709 | 765kV Transmission Line | North-Eastern | 1569.66 | 265.8 | 49 | 10.1 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 10.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1710 | 765kV Transmission Line | Western | 3387.34 | 258 | 48 | 65.3 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 65.3% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 1 | Medium
GRID-1711 | 220kV D/C Line | Western | 484.88 | 50.4 | 23 | 26.5 | Disputed | Stage-II Awaited | On Track | Physical progress is at 26.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1712 | 765kV Transmission Line | Eastern | 2893.38 | 409.3 | 41 | 53.8 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 53.8%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1713 | 220kV D/C Line | Eastern | 571.22 | 226.6 | 18 | 25.9 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 25.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1714 | 400kV Substation | Eastern | 425.71 | 49.1 | 33 | 65.4 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 65.4% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 0 | Low
GRID-1715 | 765kV Transmission Line | North-Eastern | 4472.02 | 419.3 | 43 | 61.1 | Pending Local | Approved | Equipment Delayed | Physical progress is at 61.1%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1716 | 400kV Substation | Eastern | 891.61 | 18.5 | 25 | 10.2 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 10.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1717 | 220kV D/C Line | Southern | 273.15 | 65 | 16 | 33 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 33.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1718 | 220kV D/C Line | Eastern | 505.69 | 156.6 | 19 | 28.4 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 28.4%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1719 | 400kV Substation | Southern | 1135.12 | 84 | 41 | 30.7 | Pending Local | Approved | Insolvent | Physical progress is at 30.7%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1720 | 400kV Substation | Western | 669.66 | 55.7 | 42 | 26.8 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 26.8%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1721 | 220kV D/C Line | Southern | 720.62 | 165.9 | 31 | 29.1 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 29.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1722 | 220kV D/C Line | Southern | 144.05 | 137.6 | 31 | 23.8 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 23.8%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1723 | 220kV D/C Line | Eastern | 278.44 | 120.4 | 31 | 30.1 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 30.1%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1724 | 400kV Substation | Western | 646.77 | 51.3 | 44 | 79.9 | Pending Local | Approved | Equipment Delayed | Physical progress is at 79.9%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1725 | 400kV Substation | Southern | 679.24 | 81.3 | 29 | 34.1 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 34.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1726 | 400kV Substation | Western | 1453.42 | 13.5 | 36 | 23.6 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 23.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1727 | 400kV Substation | North-Eastern | 425.25 | 29.9 | 41 | 22.1 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 22.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1728 | 400kV Substation | Northern | 964 | 47.4 | 31 | 76.6 | Clear | Approved | Equipment Delayed | Physical progress is at 76.6%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1729 | 765kV Transmission Line | Western | 1660.73 | 303.5 | 48 | 26.1 | Disputed | Stage-I Awaited | On Track | Physical progress is at 26.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1730 | 400kV Substation | Southern | 416.51 | 33.5 | 42 | 21.2 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 21.2%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1731 | 220kV D/C Line | Northern | 557.54 | 156.2 | 17 | 65.2 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 65.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1732 | 400kV Substation | Northern | 357.13 | 34.4 | 33 | 33.5 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 33.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1733 | 400kV Substation | Southern | 1445.63 | 60.3 | 36 | 25.7 | Pending Local | Approved | Equipment Delayed | Physical progress is at 25.7%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1734 | 400kV Substation | Southern | 1033.54 | 49.3 | 39 | 33.5 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1735 | 220kV D/C Line | Northern | 332.25 | 93.1 | 32 | 22.5 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 22.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1736 | 220kV D/C Line | Southern | 579.31 | 115.1 | 31 | 23.9 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 23.9%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1737 | 400kV Substation | Northern | 886.92 | 17.4 | 28 | 14.2 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 14.2%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1738 | 400kV Substation | Western | 1090.09 | 95.2 | 26 | 22.4 | Disputed | Stage-I Awaited | On Track | Physical progress is at 22.4%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1739 | 220kV D/C Line | North-Eastern | 612.05 | 173.5 | 29 | 14.3 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 14.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1740 | 765kV Transmission Line | Southern | 1989.8 | 457.8 | 39 | 19.2 | Pending Local | Approved | Insolvent | Physical progress is at 19.2%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1741 | 765kV Transmission Line | Northern | 2675.96 | 215.7 | 56 | 16.5 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 16.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1742 | 400kV Substation | Eastern | 576.39 | 43 | 30 | 24.5 | Pending Local | Approved | Equipment Delayed | Physical progress is at 24.5%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1743 | 400kV Substation | North-Eastern | 660.34 | 82.5 | 42 | 41.5 | Pending Local | Approved | Equipment Delayed | Physical progress is at 41.5%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1744 | 220kV D/C Line | North-Eastern | 121.2 | 89 | 28 | 47.5 | Clear | Stage-I Awaited | On Track | Physical progress is at 47.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1745 | 220kV D/C Line | North-Eastern | 742.91 | 246.1 | 25 | 34.1 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 34.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1746 | 220kV D/C Line | Eastern | 237.41 | 107 | 29 | 52.5 | Pending Local | Approved | Equipment Delayed | Physical progress is at 52.5%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1747 | 220kV D/C Line | Southern | 386.02 | 216.3 | 18 | 22 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 22.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1748 | 765kV Transmission Line | Southern | 2987 | 343.5 | 45 | 21.1 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 21.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1749 | 220kV D/C Line | Northern | 790.86 | 94.9 | 24 | 25.7 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 25.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1750 | 400kV Substation | Northern | 1031.51 | 61.8 | 24 | 61.3 | Disputed | Approved | On Track | Physical progress is at 61.3%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1751 | 400kV Substation | Western | 992.93 | 57.8 | 31 | 41.6 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 41.6%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1752 | 765kV Transmission Line | Southern | 2864.52 | 420.8 | 52 | 19.3 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 19.3%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 33 | High
GRID-1753 | 400kV Substation | North-Eastern | 718.24 | 56.8 | 40 | 13.6 | Disputed | Approved | Insolvent | Physical progress is at 13.6%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1754 | 220kV D/C Line | North-Eastern | 526.44 | 229.4 | 32 | 65.6 | Clear | Approved | Equipment Delayed | Physical progress is at 65.6%. Construction activities are impacted as equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1755 | 765kV Transmission Line | Eastern | 1550.36 | 298.4 | 54 | 29.9 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 29.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1756 | 765kV Transmission Line | North-Eastern | 4982.2 | 494.6 | 39 | 26 | Clear | Approved | Insolvent | Physical progress is at 26.0%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1757 | 220kV D/C Line | North-Eastern | 339.2 | 136.9 | 29 | 25.2 | Clear | Approved | Insolvent | Physical progress is at 25.2%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1758 | 220kV D/C Line | Northern | 292.57 | 233.3 | 30 | 25.4 | Clear | Approved | Insolvent | Physical progress is at 25.4%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1759 | 765kV Transmission Line | Eastern | 3138.04 | 214.1 | 46 | 28.8 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 28.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1760 | 220kV D/C Line | Southern | 621.16 | 157.7 | 12 | 13.2 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 13.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1761 | 765kV Transmission Line | North-Eastern | 2343.96 | 375.3 | 36 | 32.3 | Clear | Stage-II Awaited | On Track | Physical progress is at 32.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1762 | 400kV Substation | Southern | 445.52 | 75.1 | 25 | 23.4 | Disputed | Approved | Insolvent | Physical progress is at 23.4%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1763 | 765kV Transmission Line | Southern | 2647.09 | 463.8 | 45 | 22.8 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 22.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1764 | 765kV Transmission Line | Eastern | 4151.34 | 242 | 50 | 22.7 | Clear | Approved | Insolvent | Physical progress is at 22.7%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1765 | 220kV D/C Line | Western | 246.29 | 98.4 | 31 | 61.8 | Clear | Stage-II Awaited | On Track | Physical progress is at 61.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1766 | 765kV Transmission Line | Southern | 3715.04 | 287.6 | 57 | 31.5 | Clear | Approved | Insolvent | Physical progress is at 31.5%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1767 | 765kV Transmission Line | North-Eastern | 3205.7 | 255.8 | 47 | 49.8 | Clear | Approved | Equipment Delayed | Physical progress is at 49.8%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1768 | 220kV D/C Line | Western | 686.82 | 232.2 | 27 | 61.8 | Pending Local | Approved | Equipment Delayed | Physical progress is at 61.8%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1769 | 400kV Substation | Northern | 711.74 | 32.4 | 29 | 22.7 | Disputed | Approved | Equipment Delayed | Physical progress is at 22.7%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1770 | 765kV Transmission Line | Northern | 3682.08 | 409 | 46 | 30.7 | Disputed | Approved | Equipment Delayed | Physical progress is at 30.7%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1771 | 765kV Transmission Line | Northern | 2161.18 | 368.1 | 36 | 30.6 | Clear | Stage-I Awaited | On Track | Physical progress is at 30.6%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1772 | 400kV Substation | Western | 806.66 | 94 | 40 | 16.8 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 16.8%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1773 | 220kV D/C Line | Southern | 655.97 | 235.3 | 30 | 36.1 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 36.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1774 | 220kV D/C Line | Northern | 498.77 | 84.6 | 29 | 18 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 18.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1775 | 400kV Substation | North-Eastern | 1198.34 | 50.8 | 39 | 26 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 26.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1776 | 765kV Transmission Line | Eastern | 4437 | 446.2 | 60 | 57.9 | Disputed | Approved | On Track | Physical progress is at 57.9%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1777 | 220kV D/C Line | Eastern | 243.88 | 144 | 32 | 20.1 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 20.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1778 | 400kV Substation | Northern | 579.06 | 10.8 | 24 | 58.8 | Disputed | Approved | Equipment Delayed | Physical progress is at 58.8%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1779 | 400kV Substation | Western | 718.42 | 80.9 | 25 | 31.7 | Pending Local | Approved | Insolvent | Physical progress is at 31.7%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1780 | 220kV D/C Line | Southern | 415.15 | 76.8 | 20 | 68.3 | Pending Local | Approved | On Track | Physical progress is at 68.3%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-1781 | 220kV D/C Line | North-Eastern | 687.21 | 104.4 | 30 | 79.9 | Clear | Approved | Equipment Delayed | Physical progress is at 79.9%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1782 | 220kV D/C Line | Northern | 141.65 | 146.5 | 31 | 28.8 | Pending Local | Approved | Insolvent | Physical progress is at 28.8%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1783 | 765kV Transmission Line | North-Eastern | 4055.66 | 367.4 | 40 | 14.6 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 14.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1784 | 400kV Substation | Western | 522.63 | 11.3 | 46 | 12.5 | Disputed | Stage-II Awaited | On Track | Physical progress is at 12.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1785 | 765kV Transmission Line | Western | 2569.18 | 357.8 | 39 | 10.3 | Disputed | Stage-I Awaited | On Track | Physical progress is at 10.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1786 | 220kV D/C Line | Western | 139.26 | 236 | 36 | 29.5 | Clear | Approved | Insolvent | Physical progress is at 29.5%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1787 | 400kV Substation | Eastern | 1165.73 | 16.3 | 35 | 10.2 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 10.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1788 | 220kV D/C Line | Southern | 121.02 | 69.2 | 19 | 30 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 30.0%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1789 | 765kV Transmission Line | Western | 4134.22 | 210.4 | 50 | 67.1 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 67.1% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 0 | Low
GRID-1790 | 765kV Transmission Line | Eastern | 3234.65 | 255.7 | 36 | 29.8 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 29.8%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-1791 | 220kV D/C Line | Northern | 431.77 | 51.3 | 20 | 73 | Pending Local | Approved | Equipment Delayed | Physical progress is at 73.0%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1792 | 765kV Transmission Line | Western | 2761.91 | 227.9 | 48 | 48.6 | Clear | Approved | Equipment Delayed | Physical progress is at 48.6%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1793 | 765kV Transmission Line | Western | 4840.22 | 474.2 | 57 | 28.5 | Disputed | Approved | Insolvent | Physical progress is at 28.5%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1794 | 765kV Transmission Line | Eastern | 3659.58 | 262.5 | 41 | 15.6 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 15.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1795 | 765kV Transmission Line | Eastern | 3609.37 | 290 | 53 | 77.9 | Clear | Stage-II Awaited | On Track | Physical progress is at 77.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1796 | 400kV Substation | North-Eastern | 948.06 | 20.1 | 25 | 71.2 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 71.2% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 0 | Low
GRID-1797 | 220kV D/C Line | Southern | 612.75 | 210.5 | 25 | 20.5 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 20.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 29 | High
GRID-1798 | 765kV Transmission Line | Northern | 3250.7 | 280.8 | 50 | 21 | Pending Local | Approved | Insolvent | Physical progress is at 21.0%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1799 | 220kV D/C Line | Northern | 500.32 | 148.1 | 31 | 32 | Disputed | Approved | On Track | Physical progress is at 32.0%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1800 | 400kV Substation | North-Eastern | 1184.37 | 78.8 | 48 | 14.9 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 14.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1801 | 400kV Substation | North-Eastern | 622.82 | 49.3 | 38 | 49 | Clear | Stage-II Awaited | On Track | Physical progress is at 49.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1802 | 400kV Substation | Southern | 629.19 | 26.9 | 46 | 67 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 67.0% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 0 | Low
GRID-1803 | 400kV Substation | Southern | 301.79 | 28.7 | 30 | 79.2 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 79.2% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 0 | Low
GRID-1804 | 400kV Substation | Western | 1012.49 | 65.1 | 24 | 13 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 13.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1805 | 400kV Substation | North-Eastern | 1203.56 | 66.5 | 31 | 49.7 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 49.7%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1806 | 220kV D/C Line | North-Eastern | 131.31 | 51.8 | 35 | 22 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 22.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1807 | 765kV Transmission Line | Northern | 1580.7 | 379 | 54 | 13 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 13.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-1808 | 765kV Transmission Line | Northern | 3331.87 | 225.5 | 38 | 22.5 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 22.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1809 | 765kV Transmission Line | Western | 3725.73 | 441.5 | 57 | 53 | Clear | Approved | Equipment Delayed | Physical progress is at 53.0%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1810 | 400kV Substation | Eastern | 793.34 | 50.2 | 36 | 32.3 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 32.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1811 | 400kV Substation | Western | 1159.34 | 18.6 | 41 | 13.5 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 13.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1812 | 765kV Transmission Line | Western | 3296.69 | 378.9 | 60 | 45.6 | Pending Local | Approved | On Track | Physical progress is at 45.6%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-1813 | 400kV Substation | North-Eastern | 1364.69 | 54.7 | 46 | 65.5 | Pending Local | Approved | Equipment Delayed | Physical progress is at 65.5%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1814 | 400kV Substation | Western | 1441.24 | 30 | 38 | 46.4 | Clear | Approved | Equipment Delayed | Physical progress is at 46.4%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-1815 | 220kV D/C Line | Western | 486.16 | 116.4 | 29 | 51.5 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 51.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1816 | 220kV D/C Line | Northern | 300.81 | 223.3 | 24 | 64.1 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 64.1% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 1 | Medium
GRID-1817 | 400kV Substation | Northern | 364.54 | 21.5 | 31 | 23.6 | Disputed | Approved | Equipment Delayed | Physical progress is at 23.6%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1818 | 765kV Transmission Line | North-Eastern | 4072.53 | 477.6 | 49 | 21.2 | Clear | Stage-I Awaited | On Track | Physical progress is at 21.2%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1819 | 220kV D/C Line | Southern | 108.07 | 197.1 | 25 | 19.5 | Pending Local | Approved | Insolvent | Physical progress is at 19.5%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1820 | 220kV D/C Line | Western | 725.68 | 245.7 | 25 | 24.3 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 24.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1821 | 765kV Transmission Line | Northern | 2780.83 | 415.8 | 56 | 30.4 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 30.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1822 | 765kV Transmission Line | Eastern | 4997.11 | 360.4 | 41 | 30.7 | Pending Local | Approved | Insolvent | Physical progress is at 30.7%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1823 | 400kV Substation | Eastern | 1484.24 | 55.8 | 37 | 16.9 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 16.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1824 | 220kV D/C Line | Eastern | 457.45 | 218.9 | 31 | 24.5 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 24.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1825 | 765kV Transmission Line | Eastern | 4912.39 | 232.7 | 52 | 13.1 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 13.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1826 | 400kV Substation | Northern | 668.69 | 47.7 | 47 | 43.5 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 43.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1827 | 400kV Substation | North-Eastern | 1185.91 | 42.1 | 35 | 66.4 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 66.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1828 | 220kV D/C Line | Northern | 636.49 | 70.2 | 34 | 23.3 | Disputed | Stage-I Awaited | On Track | Physical progress is at 23.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1829 | 765kV Transmission Line | Eastern | 2317.26 | 267.6 | 57 | 11.6 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 11.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 32 | High
GRID-1830 | 400kV Substation | Eastern | 611.6 | 79.7 | 35 | 63.2 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 63.2% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 0 | Low
GRID-1831 | 765kV Transmission Line | Western | 2364.97 | 208.8 | 58 | 20.2 | Pending Local | Approved | Equipment Delayed | Physical progress is at 20.2%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1832 | 765kV Transmission Line | Northern | 3997.35 | 392.6 | 52 | 46.5 | Pending Local | Approved | On Track | Physical progress is at 46.5%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-1833 | 765kV Transmission Line | Northern | 3581.36 | 365.2 | 54 | 52.3 | Disputed | Stage-II Awaited | On Track | Physical progress is at 52.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1834 | 765kV Transmission Line | Southern | 4716.44 | 342.5 | 39 | 28.7 | Clear | Approved | Insolvent | Physical progress is at 28.7%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1835 | 220kV D/C Line | North-Eastern | 390.46 | 206.1 | 15 | 28 | Disputed | Stage-I Awaited | On Track | Physical progress is at 28.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1836 | 220kV D/C Line | Southern | 691.78 | 177.2 | 28 | 28.2 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 28.2%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1837 | 765kV Transmission Line | Southern | 3355.38 | 411.9 | 36 | 31.7 | Pending Local | Approved | Insolvent | Physical progress is at 31.7%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1838 | 400kV Substation | Western | 1235.27 | 63.9 | 25 | 24.2 | Disputed | Approved | Equipment Delayed | Physical progress is at 24.2%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1839 | 220kV D/C Line | Eastern | 783.16 | 80.9 | 18 | 22.3 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 22.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1840 | 400kV Substation | Western | 348.38 | 89 | 41 | 61.9 | Clear | Approved | On Track | Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Site inspection conducted. Physical progress stands at 61.9% with all statutory clearances in place. | 1 | Medium
GRID-1841 | 765kV Transmission Line | Western | 3779.66 | 400.7 | 45 | 78.6 | Clear | Approved | On Track | Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 78.6% with all statutory clearances in place. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 1 | Medium
GRID-1842 | 400kV Substation | North-Eastern | 1102.67 | 44.4 | 35 | 30 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 30.0%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1843 | 220kV D/C Line | Northern | 272.14 | 219.9 | 23 | 22.2 | Disputed | Stage-II Awaited | On Track | Physical progress is at 22.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1844 | 400kV Substation | Western | 766.07 | 10.4 | 24 | 79.2 | Clear | Approved | Equipment Delayed | Physical progress is at 79.2%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-1845 | 765kV Transmission Line | Southern | 4469.87 | 410.8 | 58 | 13.4 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 13.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1846 | 220kV D/C Line | Northern | 254.27 | 52 | 15 | 31.5 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 31.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1847 | 400kV Substation | Northern | 752.47 | 74.8 | 48 | 15.8 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 15.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1848 | 400kV Substation | North-Eastern | 408.86 | 10.3 | 24 | 29.2 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 29.2%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1849 | 220kV D/C Line | North-Eastern | 651.07 | 221.1 | 15 | 18 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 18.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1850 | 220kV D/C Line | Northern | 734.08 | 231.5 | 22 | 70.6 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Site inspection conducted. Physical progress stands at 70.6% with all statutory clearances in place. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. | 1 | Medium
GRID-1851 | 400kV Substation | Southern | 485.72 | 86.9 | 44 | 15.7 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 15.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1852 | 765kV Transmission Line | Southern | 4253.69 | 330.5 | 59 | 10.9 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 10.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1853 | 765kV Transmission Line | Eastern | 2212.51 | 448.1 | 50 | 23.3 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 23.3%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1854 | 220kV D/C Line | Northern | 251.56 | 147.3 | 21 | 75.5 | Clear | Stage-II Awaited | On Track | Physical progress is at 75.5%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1855 | 765kV Transmission Line | Southern | 3261.39 | 297.3 | 50 | 42.5 | Disputed | Approved | Equipment Delayed | Physical progress is at 42.5%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1856 | 400kV Substation | North-Eastern | 783.39 | 23.3 | 38 | 21.2 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 21.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1857 | 765kV Transmission Line | Northern | 3058.62 | 467.7 | 57 | 74.4 | Clear | Approved | Equipment Delayed | Physical progress is at 74.4%. Construction activities are impacted as ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-1858 | 400kV Substation | Western | 1171.95 | 97 | 36 | 13.1 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 13.1%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1859 | 220kV D/C Line | Northern | 384.51 | 184.4 | 12 | 15.8 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 15.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1860 | 400kV Substation | Western | 611.65 | 41.2 | 24 | 24.4 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 24.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 22 | High
GRID-1861 | 220kV D/C Line | Eastern | 400.35 | 101.5 | 12 | 18 | Pending Local | Approved | Insolvent | Physical progress is at 18.0%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1862 | 220kV D/C Line | Eastern | 450.13 | 226.4 | 27 | 31.3 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 31.3%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1863 | 765kV Transmission Line | Western | 3169 | 458.1 | 59 | 11.5 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 11.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1864 | 220kV D/C Line | Western | 437.5 | 71.3 | 14 | 13 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 13.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-1865 | 765kV Transmission Line | Northern | 4228.03 | 247.3 | 53 | 43.1 | Pending Local | Approved | Equipment Delayed | Physical progress is at 43.1%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1866 | 400kV Substation | Western | 1428 | 85.2 | 42 | 30.2 | Clear | Approved | Insolvent | Physical progress is at 30.2%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1867 | 765kV Transmission Line | Western | 4114.07 | 498.5 | 54 | 27.4 | Disputed | Approved | On Track | Physical progress is at 27.4%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1868 | 400kV Substation | Eastern | 1294.59 | 15.4 | 41 | 75.3 | Clear | Approved | Equipment Delayed | Physical progress is at 75.3%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1869 | 765kV Transmission Line | Northern | 2900.22 | 258.2 | 60 | 17.3 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 17.3%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1870 | 765kV Transmission Line | Eastern | 4422.96 | 255.1 | 44 | 46.4 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 46.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1871 | 400kV Substation | Western | 1399.06 | 10.5 | 31 | 33.2 | Disputed | Approved | Insolvent | Physical progress is at 33.2%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1872 | 765kV Transmission Line | Southern | 3655.24 | 383.8 | 53 | 28.5 | Pending Local | Approved | Insolvent | Physical progress is at 28.5%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1873 | 400kV Substation | Western | 1489.57 | 54.4 | 41 | 52.9 | Clear | Approved | Insolvent | Physical progress is at 52.9%. Construction activities are impacted as vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1874 | 400kV Substation | Northern | 658.16 | 79.5 | 37 | 58.1 | Clear | Approved | Equipment Delayed | Physical progress is at 58.1%. Construction activities are impacted as transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1875 | 765kV Transmission Line | Eastern | 4520.54 | 365.9 | 45 | 25.6 | Pending Local | Approved | Insolvent | Physical progress is at 25.6%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1876 | 765kV Transmission Line | Eastern | 4029.75 | 351.7 | 53 | 22.4 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 22.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1877 | 765kV Transmission Line | Western | 1656.08 | 203.1 | 58 | 46.6 | Clear | Stage-II Awaited | On Track | Physical progress is at 46.6%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1878 | 400kV Substation | Southern | 1358.54 | 31.4 | 25 | 15.6 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 15.6%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-1879 | 765kV Transmission Line | Western | 2106.6 | 487.2 | 43 | 72.4 | Pending Local | Approved | On Track | Physical progress is at 72.4%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 1 | Medium
GRID-1880 | 400kV Substation | Southern | 1324.21 | 15.3 | 43 | 51.8 | Disputed | Approved | Equipment Delayed | Physical progress is at 51.8%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1881 | 400kV Substation | North-Eastern | 905.15 | 59.9 | 41 | 47.7 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 47.7%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1882 | 765kV Transmission Line | Eastern | 4716.98 | 377.6 | 40 | 62.6 | Clear | Stage-II Awaited | On Track | Physical progress is at 62.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1883 | 220kV D/C Line | Western | 185.71 | 216.3 | 20 | 42.3 | Pending Local | Approved | On Track | Physical progress is at 42.3%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1884 | 220kV D/C Line | Eastern | 319.14 | 224.9 | 31 | 45.7 | Disputed | Approved | On Track | Physical progress is at 45.7%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1885 | 400kV Substation | Western | 390.3 | 51.4 | 42 | 35.4 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 35.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1886 | 765kV Transmission Line | North-Eastern | 2211.02 | 334.4 | 55 | 55.8 | Clear | Stage-II Awaited | On Track | Physical progress is at 55.8%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1887 | 220kV D/C Line | Western | 169.91 | 124.5 | 35 | 32.7 | Pending Local | Approved | Equipment Delayed | Physical progress is at 32.7%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1888 | 400kV Substation | Eastern | 423.46 | 91.5 | 46 | 52.3 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 52.3%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1889 | 765kV Transmission Line | North-Eastern | 3575.82 | 398 | 53 | 14.8 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 14.8%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1890 | 400kV Substation | Western | 1332.07 | 41.9 | 34 | 24 | Clear | Stage-I Awaited | On Track | Physical progress is at 24.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1891 | 400kV Substation | Western | 1099.43 | 14.4 | 38 | 25.1 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 25.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1892 | 765kV Transmission Line | Western | 4897.62 | 350.5 | 43 | 14.5 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 14.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-1893 | 400kV Substation | Northern | 817.71 | 67.1 | 42 | 80.6 | Clear | Approved | On Track | No force majeure conditions observed. Project is expected to be commissioned within original SCOD. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. Site inspection conducted. Physical progress stands at 80.6% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. | 0 | Low
GRID-1894 | 220kV D/C Line | Northern | 216.15 | 143.5 | 29 | 25.9 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 25.9%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1895 | 400kV Substation | Eastern | 1152.72 | 53 | 36 | 16.7 | Clear | Approved | Insolvent | Physical progress is at 16.7%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1896 | 765kV Transmission Line | North-Eastern | 4226.22 | 308.7 | 42 | 24.6 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 24.6%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 30 | High
GRID-1897 | 765kV Transmission Line | Southern | 1530.18 | 231.9 | 41 | 32.1 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 32.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1898 | 220kV D/C Line | Eastern | 232.09 | 202.1 | 17 | 71.7 | Disputed | Approved | On Track | Physical progress is at 71.7%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1899 | 400kV Substation | Northern | 644.97 | 61.6 | 43 | 26.4 | Clear | Approved | Insolvent | Physical progress is at 26.4%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1900 | 765kV Transmission Line | Eastern | 1639.15 | 323 | 36 | 20.8 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 20.8%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1901 | 400kV Substation | Southern | 1076.42 | 11.7 | 31 | 63 | Disputed | Approved | On Track | Physical progress is at 63.0%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1902 | 400kV Substation | Western | 946.49 | 26 | 29 | 15.6 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 15.6%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1903 | 765kV Transmission Line | Eastern | 4877.82 | 479.5 | 40 | 17 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 17.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 23 | High
GRID-1904 | 765kV Transmission Line | Eastern | 4914.66 | 461.1 | 48 | 33.5 | Pending Local | Approved | Insolvent | Physical progress is at 33.5%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1905 | 220kV D/C Line | Southern | 259.79 | 84.7 | 20 | 74.3 | Pending Local | Approved | Equipment Delayed | Physical progress is at 74.3%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1906 | 765kV Transmission Line | Western | 4252.75 | 234.4 | 56 | 13.4 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 13.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1907 | 400kV Substation | Southern | 1379.91 | 35.9 | 47 | 21.7 | Clear | Stage-I Awaited | On Track | Physical progress is at 21.7%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1908 | 220kV D/C Line | Southern | 433.63 | 134 | 36 | 16.3 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 16.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1909 | 220kV D/C Line | Northern | 673.15 | 226 | 14 | 10.5 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 10.5%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1910 | 765kV Transmission Line | Southern | 3940.67 | 212.4 | 41 | 30.7 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 30.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1911 | 400kV Substation | Western | 562.83 | 41.1 | 48 | 16.4 | Pending Local | Approved | Insolvent | Physical progress is at 16.4%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1912 | 765kV Transmission Line | Southern | 4559.51 | 431.8 | 47 | 42.4 | Disputed | Approved | Equipment Delayed | Physical progress is at 42.4%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1913 | 220kV D/C Line | Eastern | 221.07 | 153.1 | 35 | 24.9 | Disputed | Stage-I Awaited | On Track | Physical progress is at 24.9%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1914 | 220kV D/C Line | Southern | 437.2 | 238.7 | 17 | 18 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 18.0%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1915 | 220kV D/C Line | Western | 433.87 | 65.5 | 33 | 49.5 | Pending Local | Approved | Equipment Delayed | Physical progress is at 49.5%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1916 | 400kV Substation | North-Eastern | 1447.42 | 57 | 32 | 28.2 | Clear | Stage-I Awaited | On Track | Physical progress is at 28.2%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1917 | 220kV D/C Line | Eastern | 690.27 | 242.6 | 23 | 28.9 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 28.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1918 | 400kV Substation | Southern | 1358.72 | 17.8 | 35 | 21.3 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 21.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1919 | 765kV Transmission Line | North-Eastern | 2578.23 | 212.3 | 50 | 19.1 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 19.1%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1920 | 765kV Transmission Line | Western | 3970.61 | 333.3 | 49 | 35.9 | Disputed | Stage-II Awaited | On Track | Physical progress is at 35.9%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1921 | 220kV D/C Line | Western | 115.58 | 130.9 | 34 | 69.4 | Clear | Stage-II Awaited | On Track | Physical progress is at 69.4%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1922 | 400kV Substation | Eastern | 1393.47 | 67.8 | 48 | 40.3 | Clear | Stage-II Awaited | On Track | Physical progress is at 40.3%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1923 | 400kV Substation | Southern | 561.64 | 78.4 | 45 | 42.9 | Disputed | Approved | Equipment Delayed | Physical progress is at 42.9%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1924 | 220kV D/C Line | Western | 587.46 | 188.7 | 28 | 18.1 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 18.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1925 | 220kV D/C Line | Southern | 499.7 | 77.8 | 15 | 29.1 | Disputed | Stage-I Awaited | On Track | Physical progress is at 29.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1926 | 220kV D/C Line | Eastern | 120.82 | 128.2 | 17 | 63.1 | Clear | Approved | Equipment Delayed | Physical progress is at 63.1%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1927 | 400kV Substation | Western | 1432.21 | 62.2 | 29 | 13 | Disputed | Stage-II Awaited | On Track | Physical progress is at 13.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1928 | 220kV D/C Line | Southern | 776.04 | 203.9 | 36 | 28.4 | Clear | Stage-I Awaited | On Track | Physical progress is at 28.4%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1929 | 220kV D/C Line | Eastern | 675.65 | 111.6 | 20 | 10.8 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 10.8%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1930 | 220kV D/C Line | Western | 770.35 | 110.5 | 32 | 34.4 | Disputed | Stage-II Awaited | On Track | Physical progress is at 34.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 9 | High
GRID-1931 | 400kV Substation | Northern | 1492.66 | 63.9 | 26 | 19.2 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 19.2%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 26 | High
GRID-1932 | 220kV D/C Line | North-Eastern | 619.75 | 105.6 | 19 | 58.6 | Clear | Stage-II Awaited | On Track | Physical progress is at 58.6%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1933 | 765kV Transmission Line | Eastern | 3150.17 | 458 | 36 | 26.9 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 26.9%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1934 | 765kV Transmission Line | Eastern | 3776.72 | 275.8 | 60 | 10 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 10.0%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1935 | 400kV Substation | Northern | 1424.3 | 98 | 37 | 15.1 | Disputed | Stage-I Awaited | On Track | Physical progress is at 15.1%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1936 | 400kV Substation | Western | 782.53 | 57.6 | 43 | 53.7 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 53.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1937 | 220kV D/C Line | Northern | 420.35 | 153.3 | 33 | 16.9 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 16.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 31 | High
GRID-1938 | 400kV Substation | North-Eastern | 1122.51 | 74.7 | 36 | 55.7 | Clear | Approved | Equipment Delayed | Physical progress is at 55.7%. Construction activities are impacted as critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1939 | 220kV D/C Line | Northern | 471.27 | 218.1 | 19 | 59.8 | Disputed | Approved | Equipment Delayed | Physical progress is at 59.8%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1940 | 220kV D/C Line | Southern | 296.43 | 93.7 | 31 | 18.4 | Pending Local | Stage-II Awaited | Insolvent | Physical progress is at 18.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1941 | 765kV Transmission Line | Northern | 2125.25 | 420.7 | 45 | 46.3 | Disputed | Stage-II Awaited | On Track | Physical progress is at 46.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1942 | 400kV Substation | North-Eastern | 322.28 | 18.1 | 28 | 14.6 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 14.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1943 | 400kV Substation | Northern | 599.91 | 43.9 | 48 | 49.7 | Pending Local | Approved | On Track | Physical progress is at 49.7%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-1944 | 765kV Transmission Line | Southern | 1647.1 | 306.5 | 58 | 30.4 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 30.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 25 | High
GRID-1945 | 765kV Transmission Line | Eastern | 4394.74 | 281.6 | 52 | 55 | Disputed | Approved | On Track | Physical progress is at 55.0%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1946 | 400kV Substation | Western | 921.32 | 34.9 | 46 | 29.2 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 29.2%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1947 | 400kV Substation | Eastern | 1025.18 | 66.2 | 40 | 24.5 | Pending Local | Stage-I Awaited | Insolvent | Physical progress is at 24.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1948 | 765kV Transmission Line | Northern | 4829.61 | 255.8 | 52 | 62.5 | Pending Local | Approved | On Track | Physical progress is at 62.5%. Construction activities are impacted as RoW compensation negotiations are in progress with village panchayats along the corridor. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-1949 | 765kV Transmission Line | Eastern | 2959.34 | 221.8 | 50 | 19.4 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 19.4%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 13 | High
GRID-1950 | 765kV Transmission Line | Southern | 4130.23 | 420.4 | 48 | 19.3 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 19.3%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1951 | 765kV Transmission Line | Western | 2391.82 | 251.8 | 52 | 48 | Pending Local | Stage-II Awaited | On Track | Physical progress is at 48.0%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1952 | 765kV Transmission Line | North-Eastern | 1796.23 | 497.3 | 48 | 70.1 | Clear | Approved | On Track | Site inspection conducted. Physical progress stands at 70.1% with all statutory clearances in place. Vendor mobilisation is satisfactory; equipment receipt and erection are on schedule. Tower erection is progressing as per baseline programme and no encumbrances reported on RoW corridor. No force majeure conditions observed. Project is expected to be commissioned within original SCOD. | 0 | Low
GRID-1953 | 765kV Transmission Line | North-Eastern | 4035.32 | 483.2 | 45 | 17.1 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 17.1%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1954 | 400kV Substation | Northern | 320.02 | 56.5 | 42 | 13.3 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 13.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1955 | 400kV Substation | Eastern | 656.55 | 76.8 | 45 | 44.8 | Disputed | Approved | Equipment Delayed | Physical progress is at 44.8%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1956 | 220kV D/C Line | Western | 263.47 | 216.3 | 12 | 24 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 24.0%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1957 | 220kV D/C Line | Southern | 381.61 | 76.3 | 12 | 25.7 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 25.7%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 21 | High
GRID-1958 | 220kV D/C Line | Eastern | 386.33 | 237.3 | 25 | 17.7 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 17.7%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, transformer delivery from OEM is delayed due to raw material shortage; alternate sourcing being explored. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1959 | 765kV Transmission Line | Western | 2612.96 | 489.3 | 57 | 31.3 | Clear | Stage-I Awaited | Insolvent | Physical progress is at 31.3%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 24 | High
GRID-1960 | 765kV Transmission Line | Eastern | 3215.67 | 258.9 | 41 | 20.5 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 20.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1961 | 765kV Transmission Line | Southern | 4416.64 | 423.3 | 54 | 14.8 | Disputed | Stage-II Awaited | On Track | Physical progress is at 14.8%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 11 | High
GRID-1962 | 765kV Transmission Line | Southern | 4061.17 | 443.1 | 45 | 29.5 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 29.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1963 | 400kV Substation | North-Eastern | 799.18 | 21.6 | 31 | 73.5 | Pending Local | Approved | On Track | Physical progress is at 73.5%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1964 | 400kV Substation | Northern | 1232.87 | 64.7 | 39 | 22.1 | Disputed | Approved | Insolvent | Physical progress is at 22.1%. Construction activities are impacted as RoW corridor is subject to a title dispute among multiple claimants; stay order obtained by affected party; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1965 | 220kV D/C Line | North-Eastern | 342.98 | 103.6 | 24 | 30.3 | Clear | Stage-I Awaited | On Track | Physical progress is at 30.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1966 | 220kV D/C Line | Northern | 341.02 | 158.9 | 14 | 16.5 | Disputed | Stage-II Awaited | On Track | Physical progress is at 16.5%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1967 | 220kV D/C Line | Southern | 274.21 | 183.3 | 24 | 22 | Clear | Stage-II Awaited | Equipment Delayed | Physical progress is at 22.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1968 | 765kV Transmission Line | Southern | 2616.27 | 293.5 | 53 | 76.9 | Pending Local | Approved | On Track | Physical progress is at 76.9%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1969 | 220kV D/C Line | Western | 224.75 | 210.9 | 12 | 29.2 | Disputed | Approved | Insolvent | Physical progress is at 29.2%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, vendor insolvency proceedings initiated; Resolution Professional appointed; contract termination under review. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1970 | 220kV D/C Line | Southern | 740.74 | 158.8 | 24 | 23.5 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 23.5%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 29 | High
GRID-1971 | 765kV Transmission Line | North-Eastern | 3942.35 | 227.2 | 48 | 33.7 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 33.7%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, RoW compensation negotiations are in progress with village panchayats along the corridor; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1972 | 765kV Transmission Line | Western | 3617.15 | 340.5 | 44 | 29.2 | Clear | Stage-II Awaited | Insolvent | Physical progress is at 29.2%. Construction activities are impacted as Stage-II diversion awaited; compensatory afforestation plan has been submitted to state authority; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 19 | High
GRID-1973 | 765kV Transmission Line | North-Eastern | 4019.42 | 381.5 | 51 | 79.2 | Clear | Stage-II Awaited | On Track | Physical progress is at 79.2%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 3 | Medium
GRID-1974 | 765kV Transmission Line | North-Eastern | 3947.52 | 227.8 | 59 | 28 | Disputed | Stage-II Awaited | Equipment Delayed | Physical progress is at 28.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1975 | 765kV Transmission Line | Northern | 2673.5 | 282.7 | 46 | 29.6 | Disputed | Approved | Equipment Delayed | Physical progress is at 29.6%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1976 | 220kV D/C Line | Eastern | 122.64 | 248.8 | 33 | 52.5 | Disputed | Approved | On Track | Physical progress is at 52.5%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1977 | 220kV D/C Line | Northern | 433.23 | 240.4 | 23 | 33 | Disputed | Stage-I Awaited | Equipment Delayed | Physical progress is at 33.0%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 18 | High
GRID-1978 | 765kV Transmission Line | Southern | 2866.41 | 222 | 55 | 31.9 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 31.9%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 28 | High
GRID-1979 | 765kV Transmission Line | Eastern | 2129.31 | 298 | 60 | 34.4 | Disputed | Stage-I Awaited | On Track | Physical progress is at 34.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 15 | High
GRID-1980 | 765kV Transmission Line | North-Eastern | 2554.22 | 238.9 | 51 | 22.9 | Disputed | Stage-I Awaited | On Track | Physical progress is at 22.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, local farmer groups have filed objections against compensation award; matter sub-judice in district court. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1981 | 765kV Transmission Line | Eastern | 2327.76 | 318.9 | 43 | 69.2 | Pending Local | Approved | Equipment Delayed | Physical progress is at 69.2%. Construction activities are impacted as local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 4 | Medium
GRID-1982 | 220kV D/C Line | Eastern | 286.19 | 51.6 | 29 | 63.5 | Disputed | Approved | On Track | Physical progress is at 63.5%. Construction activities are impacted as land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 5 | Medium
GRID-1983 | 765kV Transmission Line | Northern | 4319.23 | 271.2 | 36 | 44.3 | Clear | Stage-I Awaited | On Track | Physical progress is at 44.3%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1984 | 765kV Transmission Line | Western | 4185.87 | 338 | 47 | 31.4 | Disputed | Stage-I Awaited | Insolvent | Physical progress is at 31.4%. Construction activities are impacted as Stage-I forest clearance application submitted but awaited; FAC meeting not yet scheduled; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, primary EPC contractor has been declared insolvent under IBC proceedings; NCLT order received. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 29 | High
GRID-1985 | 765kV Transmission Line | North-Eastern | 4008.13 | 329.1 | 40 | 16.4 | Pending Local | Stage-I Awaited | Equipment Delayed | Physical progress is at 16.4%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 17 | High
GRID-1986 | 765kV Transmission Line | Southern | 2500.4 | 367.1 | 55 | 25 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 25.0%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 8 | High
GRID-1987 | 220kV D/C Line | North-Eastern | 516.67 | 119.6 | 23 | 35.9 | Disputed | Approved | Equipment Delayed | Physical progress is at 35.9%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1988 | 765kV Transmission Line | North-Eastern | 4279.71 | 311.3 | 39 | 35.2 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 35.2%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 10 | High
GRID-1989 | 400kV Substation | Western | 671.52 | 48.1 | 38 | 32.5 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 32.5%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, critical tower sections and disc insulators are delayed at manufacturer's end due to supply chain disruption. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1990 | 765kV Transmission Line | Western | 2736.62 | 498.3 | 47 | 33.9 | Disputed | Stage-I Awaited | On Track | Physical progress is at 33.9%. Construction activities are impacted as forest clearance at Stage-I is yet to be obtained from MoEFCC; DFO site inspection pending; additionally, land acquisition is contested by local landowners with active litigation in civil court under RFCTLARR Act. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 14 | High
GRID-1991 | 400kV Substation | Western | 1115.27 | 67.1 | 26 | 11.3 | Pending Local | Stage-I Awaited | On Track | Physical progress is at 11.3%. Construction activities are impacted as Stage-I forest diversion approval is awaited from PCCF office; nodal officer has been designated; additionally, local RoW settlement pending; 2 gram sabha meetings conducted; resolution expected within a fortnight. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1992 | 765kV Transmission Line | Southern | 1951.32 | 276.7 | 38 | 17.7 | Clear | Approved | Insolvent | Physical progress is at 17.7%. Construction activities are impacted as EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High
GRID-1993 | 765kV Transmission Line | Eastern | 4890.2 | 419.6 | 47 | 18 | Clear | Approved | Insolvent | Physical progress is at 18.0%. Construction activities are impacted as contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1994 | 220kV D/C Line | Northern | 323.52 | 142 | 30 | 34.1 | Disputed | Approved | Insolvent | Physical progress is at 34.1%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 20 | High
GRID-1995 | 220kV D/C Line | Western | 400.78 | 127.7 | 15 | 48.5 | Disputed | Approved | On Track | Physical progress is at 48.5%. Construction activities are impacted as encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 6 | Medium
GRID-1996 | 400kV Substation | North-Eastern | 852.01 | 59.2 | 24 | 59.8 | Pending Local | Stage-II Awaited | Equipment Delayed | Physical progress is at 59.8%. Construction activities are impacted as Stage-II forest clearance is under examination at MoEFCC; NPV payment challan deposited; additionally, joint revenue survey with district officials is ongoing to finalise compensation for affected households; additionally, equipment dispatch from factory held up due to rail wagon non-availability; road transport being arranged. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 7 | High
GRID-1997 | 220kV D/C Line | Northern | 479.44 | 98.9 | 12 | 10.6 | Disputed | Approved | Insolvent | Physical progress is at 10.6%. Construction activities are impacted as local farmer groups have filed objections against compensation award; matter sub-judice in district court; additionally, contractor declared insolvent; performance bank guarantee invoked; PGCIL taking over direct execution. Accordingly, district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 16 | High
GRID-1998 | 400kV Substation | Western | 560.42 | 86.5 | 28 | 27.1 | Disputed | Stage-II Awaited | Insolvent | Physical progress is at 27.1%. Construction activities are impacted as Stage-II forest clearance is pending final approval from state forest department after FAC recommendation; additionally, encroachment dispute on alignment corridor has triggered court-ordered status quo; work halted in 3 spans; additionally, EPC agency has gone into liquidation; TSA termination notice issued; emergency re-tendering in progress. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; district administration has been requested to intervene for early resolution; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 27 | High
GRID-1999 | 400kV Substation | Northern | 523.25 | 60.5 | 28 | 77.4 | Pending Local | Approved | On Track | Physical progress is at 77.4%. Construction activities are impacted as joint revenue survey with district officials is ongoing to finalise compensation for affected households. Accordingly, district administration has been requested to intervene for early resolution. Detailed impediment report submitted to Ministry of Power for escalation. | 2 | Medium
GRID-2000 | 400kV Substation | North-Eastern | 1331.36 | 68.7 | 32 | 15.6 | Clear | Stage-I Awaited | Equipment Delayed | Physical progress is at 15.6%. Construction activities are impacted as forest clearance at Stage-I is blocked pending submission of wildlife impact assessment report to MoEFCC; additionally, ACSR conductor delivery from approved vendor is delayed by 8 weeks; penalty clause invoked on original PO. Accordingly, liaison with forest authorities is ongoing and matter has been escalated to PMD cell; PMD review meeting scheduled with executing agency at CGM level. Detailed impediment report submitted to Ministry of Power for escalation. | 12 | High

## Summary Dashboard
⚡ Grid-Guard Dataset — Summary Dashboard (2,000 Projects)
Risk Level Distribution |  |  |  | Avg Delay by Region
Risk Level | Count | Pct % |  | Region | Avg Delay (Mo)
High | 1542 | 77.1% |  | Eastern | 13.3
Medium | 414 | 20.7% |  | North-Eastern | 12.9
Low | 44 | 2.2% |  | Northern | 12.9
|  |  |  | Southern | 13.2
|  |  |  | Western | 12.9
Avg Delay — Forest Status |  |  | Avg Delay — Vendor Status |  |  | Avg Delay — RoW Status
Forest Status | Avg Delay (Mo) |  | Vendor Status | Avg Delay (Mo) |  | RoW Status | Avg Delay (Mo)
Approved | 8.1 |  | Equipment Delayed | 10.8 |  | Clear | 10.3
Stage-I Awaited | 17.9 |  | Insolvent | 20.3 |  | Disputed | 16
Stage-II Awaited | 13.1 |  | On Track | 7.4 |  | Pending Local | 12.7
Avg Delay — Project Type
Project Type | Avg Delay (Mo)
220kV D/C Line | 13.2
400kV Substation | 13.1
765kV Transmission Line | 12.8